## Slide 1
SAD begins
UITF gun removal preps
Move eqip to ISB
S&A
roll
UITF beam OFF
Crane eqip down
Prep beamline
& cathodes for gun swap
S&A as founds
Leak check
gun swap
S&A
Gun positioning
CEBAF gun swap
Ver. Feb 20, 2023

## Slide 2: Week of March 13 UITF Marcy, Jessica, Phil, Carlos
Coordinate (now, don’t wait) with installation group gun and stuff transport from UITF to tunnel (ATLis?)
Carlos asks (now, don’t wait) DCPWR to disconnect magnets and I&C to disconnect BMPs
Carlos & Jessica remove HV cables, resistor Pig and DecaRads
Jessica and Phil install cleanhood
Marcy, Phil, Jessica remove NEG tube and gun.
Marcy, Phil install gun blank flanges and pump down.
Jessica, Phil, Carlos prepare gun and bake stuff for transport
Gun ready for transport by Friday March 24. But don’t move gun just yet! Move gun very gently last
20th
  Installation group (with Jessica’s help) transport bake + pumps stuff to ISB
  Installation group cranes down stuff including S&A gear
  DC power disconnects magnets, I&C disconnect BPMs
  Joe safes gun valve CLOSED
21st
  S&A as founds
  Joe moves puck from HV to pre chamber
  Suitcase install?
22-24 Joe, Jessica and Carlos prep gun for vacuum work
  Remove HV cables and DecaRads
Week of March 20 CEBAF
Jessica, Joe and Carlos while Phil and Marcy assist with injector beam line work
SAD
begins

## Slide 3
Gun bake
Oven off
Leak check w/prep
Puck manip checks
Oven setup
HV prep
float
ISB breaker checks??
S&A final
HV Start
HV End ?
200 kV soak ‘health’ checks