## Sheet1
Updated on June 17, 2018
Type | Test | Diagnostic | Time Needed | Photocathode | Gun Voltage | Destination | Current
Operation at 130 keV | Restore 130 keV beam w/ chopper to FC1 (130 keV) | n/a | 8 hours | bulk | 130 | FC1 | 200
| Measure PSS kicker @ 130 keV | BPM, Apertures | 2 hours | bulk | 130 | FC1 | Tune
| Stability of gun voltage | Wien ON, BPM's | 2 hours | bulk | 130 | FC1 | <100
| Restore 500 keV beam FC1 (500 keV) | n/a | 8 hours | bulk | 130 | FC1 | 200
| Stability of 500 keV setup | Wien OFF, 1D dump | 2 hours | bulk | 130 | 1D | <100
| Restore 6.3 MeV beam to FC2 | n/a | 8 hours | bulk | 130 | FC2 | 200
Scaling to 180 keV | Scale to 180 keV | n/a | 4 hours | bulk | 180 | FC1 | <10
| PSS kicker configuration | BPM, Apertures | 4 hours | bulk | 180 | FC1 | <10
| Chopper setup at 180 keV | Viewers/Cup | 2 x 4 hours | bulk | 180 | FC1 | <10
130 vs. 180 kV Beam Studies | Steering-magnet field strength required to take out the kick caused by the transverse field in the gap, from the shed | BPM's | 4 hours | bulk | 130 … 180 | FC1 | <10
| bunch length vs current and gun voltage | chopper scan | 2 x 4 hours | Bulk | 130 ... 180 | FC1 | <200
| transmission vs. bunch charge | A1/A2/MS | 2 x 4 hours | Bulk | 130 ... 180 | FC1 | <200
| lifetime vs. gun voltage | FC1 | 2 x 8 hours | SLSP (bulk) | 130 … 180 | FC1 | 0.2-1 mA
| emittance vs. gun voltage | Red quad + IHA1I06 | 2 x 4 hours | Bulk | 130 … 180 | FC1 | <10
| Beam sizes on viewers, to compare against the envelope map the particle tracking code predicts | Viewers | 2 x 2 hours | Any | 130 … 180 | FC1 | <10
| PQB - Position/Charge vs. Voltage | BPM/Current | 2 days | SLSP | 130 v. 180 | FC1 | <70
130 kV ONLY Beam Studies | Mott dump for Compton polarimeter | Mott | 2 x 4 hours | SLSP (bulk) | 130 | Mott/FC2 | <10
| Test autosteer 'spot move' | BPM's | 2 x 2 hours | Any | 130 | FC1 | <10
| PQB - RTP Feedback | BPM/Current | 3 days | SLSP | 130 | FC1 | <70