**CEBAF 6 Month Summer SAD 2017 : 24 Weeks of Fun**

**Week #1: March 20-April 26 –**

**Week #2: March 27-April 2 –**

**Week #3: April 3-April 9 –**

**Week #4: April 10-April 16 – Prep beam tests for coming weeks…**

* Wed – Lock-up, check for 1mA to FC1 w/ choppers OFF
	+ => Made ~450uA
* Thu – PQB check : Hall A @ 499 MHz for 100uA to FC1
	+ => Done

**Week #5: April 17-April 23 – pos differences vs. laser size at PC w/ GaAs/GaAsP**

* Mon-Wed – Laser room work and INJ=BP on Day/Swing for beam to FC1
	+ Laser room + 4 beam setups tests, about 25uA to fc#1
* Thu-Fri – Laser room work and INJ/NL=BP on Day/Swing for beam to FC2
	+ => Did not need beam to fc#2
* #11: 1146-4: GaAsSb/AlGaAsP: blow off arsenic cap?
	+ => Successful on 4/24
* HighP 75104/DBR 75105: prepare in Suitcase
	+ => Deferred to Docking bakeout later on

**Week #6: April 24-April 30 – Baseline GaAs/GaAsP in Gun2**

* Mon: Heat/activate GaAs/GaAsP
	+ => Successful 1.4% QE @ 130keV, uniform QE
* Tue-Wed: Characterize – Measure (QE, SCL, Pol, AP) vs. Charge at high current
	+ => Successful checkout of 1mA to FC#1 (no SCL, POL, AP)
* Thu: Activate 1146-4: GaAsSb/AlGaAsP, and if not successful return to GaAs/GaAsP
	+ => 500C for ~10min, no photocathode QE after 35 min Cs
* Fri: Measure QE and Pol, plan to use for next week’s test
	+ Did not lock-up, but removed Gun HV Switch Software + Tested OK

**Week #7: May 1-May 7 – Radio-isotope measurement 18.5 MeV @ 50uA to 4D**

* Mon – setup beam and calibrate new diagnostics
	+ => Checkout of 4D line, 18.5 MeV @ 4K, B/C tune mode issues
* Tue – Open for installation
	+ => Needed another ~12h setup, align to viewers + spot
* Wed-Sat – Radiate Ga target
	+ => Install Ga target, set P w/ HMIN=2, Sx=Sy=1.2mm, 50uA good tune
* Sun – while tunnel locked up, Measure 1146-4: GaAsSb/AlGaAsP QE and Pol
	+ => Run extended to Monday 8am, + no puck#11 test

**Week #8: May 8-May 14 – Gun3 Removal + PSS Certification (HVPS locked out)**

* Radio-isotope run ends
	+ => SRF @ 4K, 18.5 MeV, produced 70 micro-gram Cu-67 and didn’t break CEBAF
	+ => Separation at VCU unsuccessful
* Mott (0-1000uA) + Mott vs. QE
	+ => P vs. I : <https://logbooks.jlab.org/entry/3472394>
	+ => P vs. QE : <https://logbooks.jlab.org/entry/3472417>
* PSS Lockups on Swing shift
* Gun3 : remove gun, add vacuum diagnostics chamber
	+ => http://devweb.acc.jlab.org/CSUEApps/atlis/task/17327
* LLRF: firmware, board component swap, UPS
	+ => Completed, but took all week long
* Co-align ABCD, 4 tune generators, B RTP
	+ => Tune mode electronics issue solved/addressed
	+ => Laser work deferred (no RF available)

**Week #9: May 15-May 21 – Gun2 Photocathodes + PSS Cert (HVPS locked out)**

* PSS Certifications (Lock-up on Swing shift)
	+ => Completed, next PSS certification end of August after Bubble run
* U Va PQB laser profile measurements (Mon-Wed)
	+ Measured divergence and astigmatism of A/C lasers
	+ => <https://logbooks.jlab.org/entry/3473100>
	+ => <https://logbooks.jlab.org/entry/3473180>
* Gun2: Remove: Bad-DBR, Bad-GaAsSb; Add: HighP+75104, DBR+75105
	+ => Suitcase/Docking station bake successful
	+ => Gun2 photocathode swap deferred until after 200kV HV job
* Gun3: Vacuum check, remove VBV3I02 from valve anti-collision interlock inhibit
	+ => Leaky valve <http://opsweb.acc.jlab.org/CSUEApps/atlis/task/17278>
	+ => Defer 3I/2I valve inhibit work until reasonable time
* Laser Work : Co-align ABCD, Align Hall B RTP
	+ ABC co-aligned (D blocked); different ABC focal length => diff. spot size
	+ Hall B RTP installed, aligned

**Week #10: May 22-May 28 – Beam Tests to FC#1**

* Mon-Tue 8am- 3pm, 4-LLRF
	+ Phase reproducibility vs. LLRF off/on
	+ Beam position drift vs. Ross probe used/not used
	+ Commission Radmon w/ nA’s of beam
	+ Check IHA1I07, IHA0I02 harps; measure emittance for C-big, C-small
* Wed-Fri 8am-11pm INJ=BP, long days for lifetime tests

**Week #11: May 29-June 4 –PSS INJ PM (no beam)**

* PSS INJ PM, no beam
* Electricians add (2) 208VAC circuits for Spellman
	+ John completed already
* Gun3 : Replace right angle valve, bake 3I chamber, anti-collision circuit

**Week #12: June 5-June 11 – Injector Group Beam Tests**

* Injector group tests (bunch length, Wien, setup vs. voltage w/ Gun2)
* Early opportunity: TOSP + Spellman Install/Test

**Week #13: June 12-June 18 – Spellman and TOSP at CEBAF**

* Move Spellman to CEBAF injector
* Complete 225kV TOSP, inspections

**Week #14: June 19-June 25 – Functional 225kV HVPS**

* Functional TOSP + Spellman @ CEBAF
* As-found survey of HV + NEG

**Week #15: June 26-July 2 – 200kV Gun Installation Early Start Date**

* Move HV chamber to CEBAF, Replace HV + NEG + 2A alignment
* Early bake opportunity

**Week #16: July 3-July 9 – 200kV Gun Bakeout**

* Bake, leak check
* Early 2B + laser alignment

**Week #17: July 10-July 16 – 200kV Gun Conditioning**

* 2B + laser alignment
* HV conditioning

**Week #18: July 17-July 23 – 200kV Gun Testing**

**Week #19: July 24-July 30 – 200kV Gun Testing**

* Bubble Installation TBD (Swing)

**Week #20: July 31-August 6 – Bubble Installation**

* Bubble Installation

**Week #21-22: August 7-August 20 – Two weeks of Bubble Eng. Run**

**Week #23-24: August 21-Sepember 3 – Two weeks of PSS Certification**