## Slide 1: Gun Test Stand, why?...WHY???
To demonstrate proof of principle magnetization of high current (mA) electron beam for the JLEIC R&D
  In particular, to support Riad Suleiman’s LDRD award
To provide 350 keV beam for Yan Wang’s thesis work on emittance as a function of photocathode surface
To serve as a test stand for improved gun and diagnostics designs for CEBAF, UITF, LERF.
To demonstrate for the first time high current beam from and inverted gun at 350kV DC with in-house multi-alkali photocathodes

## Slide 2: Timeline
May
June
July
August
September
October
First beam
Beamline & cathode
commissioning
Emittance vs cathode film thickness and roughness
Lifetime vs cathode film thickness and roughness
Shut down for Riad’s magnet installation
Gun & cathode chamber refurbishing
Beamline upgrade
All systems vacuum bake
Beamline diagnostics re-installation
Gun HV conditioning
Magnet commissioning
Cathode chamber commissioning
Beamline commissioning with beam

## Slide 3: Status as of May 2 2016
Viewers
C. Norris finished instrumenting the beam viewers
M. Johnson made the devices are available through the screen FEL -> GTS -> Viewers.
Video
J. Gubeli and C. Gould are working on temporary analog cameras. Update?
Later to be replaced with K. Jordan and B. Freeman’s digital imaging system. Update?
DC power
E. Diggs and J. Delk installed and wired magnets. Update?
Limiting current resistors needs to be installed. Hall probe checks are needed.

## Slide 4: Status continued
Software
M. Johnson made the devices are available through the screen FEL -> GTS -> Viewers, with position sensors?
Laser
S. Zhang is treading the laser beam from the hutch to the gun cathode.
K. Hesse made a new GTS magnet command screen
C. Dubbe generated new nomenclature
M. Joyce created the GTS LED
S. Witherspoon is working on vacuum software for the 6 UHV IP controllers connected to beamline
G. Croke provided channel assignments
Beam Dump
Dump has been electrically isolated and ready for BNC connection to ammeter in control room.
D. Bullard working on LCW water connections. Needs flowmeter from P. Francis to interlock with laser shutter or gun.
Laser is DC BEAM
Need to implement dump and anode ammeter signal in EPICS,.
Need shutter and attenuator EPICS control.
Do we also need ND filter that can be insterted?

## Slide 5: … and our postdoc Mamun
Made the first multi-alkali photocathode in the GTS prep chamber yesterday!