## Slide 1
• Deliverables:
- few ( ¼ -to- 5) nA of 7.6 MeV (Δp/p < 1%) beams on polarized HD (and HD)
• Milestones & Dates:
- QMC conditioning with new Klystrons, Dec’18
- (re) establish 200 keV beam with new gun, Dec’18 – Jan’19
- complete & instrument the MeV beamline, Dec’18 – Feb’19 finish UITF
- complete shielding design & construction, Dec’18 – Feb’19
- reviews and approvals for low-current OPS, Feb’19
- 1st MeV beam through IBC; Raster setup, Mar’19
- beam on unpolarized HD, Apr – May’19
e+HD
- 1st beam on polarized H, July – Aug’19
- 1st beam on polarized D, Jan’20
• Staffing – what skills are needed and when
 Project Schedule
• Issues – LHe from the CTF; N-wall shielding
UITF - 1st application: testing frozen-spin HDice with electrons – Nov 26/18

## Slide 4
• Deliverables:
- few ( ¼ -to- 5) nA of 7.6 MeV (Δp/p < 1%) beams on polarized HD (and HD)
• Milestones & Dates:
- QMC conditioning with new Klystrons, Dec’18
- (re) establish 200 keV beam with new gun, Dec’18 – Jan’19
- complete & instrument the MeV beamline, Dec’18 – Feb’19 finish UITF
- complete shielding design & construction, Dec’18 – Feb’19
- reviews and approvals for low-current OPS, Feb’19
- 1st MeV beam through IBC; Raster setup, Mar’19
- beam on unpolarized HD, Apr – May’19
e+HD
- 1st beam on polarized H, July – Aug’19
- 1st beam on polarized D, Jan’20
• Staffing – what skills are needed and when
 Project Schedule
• Issues – LHe from the CTF; N-wall shielding
• Recommended Mitigation:
- Hall B run-group H, designated highest Impact (PAC 41), remains unscheduled
awaiting UITF studies  it’s time for the Lab to get behind this !
UITF - 1st application: testing frozen-spin HDice with electrons – Nov 26/18