## Slide 1: Re-scoping UITF
Matt Poelker
November 14, 2015

## Slide 2
Proposed UITF re-scoped
What we started with…
Facilities
HDice
New UITF
Cryo Infrastructure
  Facilities
Cryo Infrastructure including some RF
HDIce (polarized target beamline)
New UITF

## Slide 3: Facilities
  Demolition
  Stairs
  Electric Cave1, top of Cave1, Cave2 and control room
  Cave2 structure
  Gate
  Fire protection
  Assorted (LCW, railings, etc.,)
  Procurement Total: $269,000
  Labor: $109,085 (34 PW)

## Slide 4: Facilities
FY16 UITF Facilities Cost Estimate for Procurements (direct costs) – 13 Nov 2015
Structural:
Seismic Anchoring $ 30,000
Steel Pedestal (ODH vents) $ 8,000
Precast Concrete $ 56,000
Structural Total: $ 94,000
Architectural:
Entry Gate $ 5,000
Painting $ 5,000
Architectural Total: $ 10,000
Mechanical:
Compressed Air $ 4,000
Control Room HVAC $ 5,000
Mechanical Total: $ 9,000
Electrical:
Cave 1 Elec $ 78,000
Communications $18,000
Cave 2 Elec $ 50,000
Electrical Total: $ 146,000
Fire Protection:
Cave 2 $ 10,000
Fire Protection Total: $ 10,000
Project Total: $269,000

## Slide 5: Cryo Infrastructure
  Plumbing and controls to connect 1/4CM to CTF
    Includes “spigots” near 1/4CM for supply and return to support other users, including HDIce or anything else needed in future.
  Controls Procurement: $18 to 44
  Controls Labor: $30.8 (14 PW)
  Design and plumbing procurement $50 to 95
  Design and plumbing labor $185.8 (97 PW)
  Totals $68 to 139 and $216.6 (111 PW)
Some of this could move to “HDIce”

## Slide 6: RF part of Cryo Infrastructure
  Include within Cryo Infrastructure all RF (since the ¼ CM is no good without RF)
  RF Procurement Total: $41k
  RF Labor: $74.3 (34 PW)
This rf only for 1/4CM, more rf needed for new UITF (lasers, chopper, buncher, MO)

## Slide 7: Cryo Infrastructure
To CTF
Cryo controls racks
RF

## Slide 8: HDIce (polarized target beamline)
Designer for this part of beamline
Move some of the Cryo costs to here…
The hardware to build this part of beamline

## Slide 9: HDIce (polarized target beamline)
 | To purchase in FY16 | 
viewers | 15 | 
MPS |  | Not defined yet
girder | 20 | 
DC power | 60 | Trim cards…
Magnets |  | Three dipole magnets, two quads, steering magnets
Pneumatic valves |  | 
harp |  | Trying to find harp, magnets and valves….
Machine shop | 35 | 
Total |  | 
3 months design time
Labor to put beamline together

## Slide 10: New UITF re-scoped
  Gun
  Magnets
  Viewers
  Valves
  BPMs
ODH and PSS
Network communications
Software
Rad Con

## Slide 11
Combine the two features that provided incremental success: shed and doped insulator
Getting the gun to work can incur costs

## Slide 12
“Shed” triple-point protection
Doped insulator
SF6
R350 epoxy receptacle
Combination of doped insulator and shed, SF6 and epoxy receptacle, plus added length
Yan Wang has modeled the shed, a good design…
…then in October

## Slide 13: New UITF Procurements
 | To purchase in FY16 | 
Gun | 130 | includes beamline components
I&C | 211.9 | Some could get moved to HDIce portion
SSG | 44.7 | 
DC power | 8 | cable
Magnets | 0 | Spectrometer dipole, trying to find one
Network | 32.5 | IOCs and network switcher
Machine shop | 40 | Always underestimated….
Total | 467.1 | 

## Slide 14
Four “Fences”
Facilities (fairly well defined)
$269k and $109.1 (34 PW)
Cryo Infrastructure (some confusion over procurements, lots of labor)
$68 to $139 and $216.6 (111 PW) for cryo portion
$41k and $74.3 (34 PW) for klystron portion
HDIce (polarized target beamline)
$130k
New UITF
$467k (I’ve double counted procurements…number too large)

## Slide 15
Month by Month Spending Profile
This schedule and cost estimate for “rf applied to cold ¼ CM” seems accurate
I will do the same for the entire project by UITF meeting next week…