The Past – Summer SAD 2017 (March – November)

Hardware

- 4-LLRF

  - Production unit installed (spare in fabrication)

  - Each laser has identical knobs (amplitude, phase shifter, 250/499)

  - FSD latch if RF system is confused on 250/499 => called RF group

- Laserfreek app

  - Tool changes laser rep rate between 250 and 499

  - Sequences the amplifiers ON/OFF while changing laser/RF setpoints

- Repair tune mode generators

  - DC mode for RTP cells backed out

  - Replaced two cells => bad extinction and bad tail

- Repair laser chiller

  - Good news, but local chiller worked fine all summer

- Removed Gun3

  - ALL Gun3 hooks removed and tested

  - VBV3I02 (a.k.a. Gun3 valve behaves like normal valve)

  - Vacuum diagnostic chamber there => will go away w/ new Y chamber

- Chopper amplifier replaced

  - I believe replaced w/ 300W spare unit (might be wrong)

- Suitcase-photocathode swaps

  - Many swaps, but this is what remains in Gun2

    - #9 - SLSP-5756-4 in HV (recent 12 GeV photocathode) – 10/10/17 activation

    - #3 - SLSP-5247-4 in Prep on SM#1-1 (QWeak sibling)

    - #6 - SLSP-75104 in Prep on SM#2-1 (90% photocathode, wet bake)

    - #10 - SLSP-DBR-75105-1 in Prep on SM#2-2 (DBR, wet bake)

The Past – Summer SAD 2017 (March – November)

Beamware

- Tested Brock cavity as a phase detector (like Yao) upstream of chopper

  - Test looked promising => useful for UITF

- Radio-isotope run @ 4K

  - Setup 15.7 MeV w/ 0L02+0L03 @ 4K

  - Injector ran well, bodes well if Bubble @ 4K

- PQB – dependence on laser size and divergence

  - Study sensitivity of pos. diff. to laser size at PC and Photocathode

  - Learned sensitivities to path length and similarity of divergence to set spot sizes

  - Instigated improved control of laser size/divergence and PPLN settings

- PQB – study KD*P PC vs. RTP PC

  - Provide data to evaluate if RTP can be both a feedback for charge & position

  - Finally backed out, returned to standard KD*P configuration

  - Instigated using Elegant to re-normalize pos. diff. results

- Installed resonant ring polarimeter

  - Installed in 1D beam line, ready for testing

  - If ring is limiting we can back out in few days with accesses, or over holiday

- Quad-Solenoid emittance study

  - Took solenoid-harp and quad-harp emittance data at various spot size

  - On Daniel’s plate to fit with provided equations

- mA polarization @ Mott

  - Measured polarizations remains high ~85% from 1 uA to 1 mA

- mA lifetime @ CEBAF

  - Operated up to 2 mA @ 499MHz to FC1

  - Measured lifetime vs. laser spot size => demo. >400C @ 1mA

  - Compared UHV and RadMon => fast loss detectable ~nA level

The Present – Winter Run 2017-2018 (Dec 4th – Mar 21st)

Dec 4th – Dec 21st : 4 Hall Operations for three weeks

| Parameter | Hall A | Hall B | Hall C | Hall D |
| --- | --- | --- | --- | --- |
| Program | E12-11-112 | Engineering | Commissioning | E12-06-102 |
| Passes | 2 | 5 | 3,4 | 5.5 |
| Current | 20 uA | 2-100 nA | 20,80 uA | Run: 150-200 nA Tests: 5-600 nA |
| Polarization | No | Yes/Wien=TBD | No | No |
| Chopper/Slit | 499/A | 250/B | 499/C | 250/D |

Jan 12th – 27th : 4 Halls Operations for two weeks

| Parameter | Hall A | Hall B | Hall C | Hall D |
| --- | --- | --- | --- | --- |
| Program | E12-10-103 | Engineering | E12-06-107 | E12-06-102 |
| Passes | 5 | 5 | 4,5 | 5.5 |
| Current | 20 uA | 100 nA | 80,65 uA | 200 nA |
| Polarization | No | Yes/Wien=TBD | No | No |
| Chopper/Slit | 250/A | 250/B | 499,250/C | 250/D |

Jan 27th – Feb 4th : 3 Hall Operations for one week

| Parameter | Hall A | Hall B | Hall C | Hall D |
| --- | --- | --- | --- | --- |
| Program | E12-10-103 | Maintenance | E12-10-002 E12-10-008 | E12-06-102 |
| Passes | 5 |  | 5 | 5.5 |
| Current | 20 uA |  | 65 uA | 200 nA |
| Polarization | No |  | No | No |
| Chopper/Slit | 250/A |  | 250/C | 250/D |

Feb 5th  – Mar 22nd : 4 Hall Operations for six weeks

| Parameter | Hall A | Hall B | Hall C | Hall D |
| --- | --- | --- | --- | --- |
| Program | E12-10-103 | CLAS12 - Run Group A | E12-10-003 E12-10-017 | E12-06-102 |
| Passes | 5 | 5 | 5 | 5.5 |
| Current | 20 uA | 100 nA | 70 uA | 200 nA |
| Polarization | No | Yes/Wien=TBD | No | No |
| Chopper/Slit | 250/A | 250/B | 250/C | 250/D |

The Present – Winter Run 2017-2018 (Dec 4th – Mar 22st)

WEEK of Nov 6th –

- Fri

  - Gun2 QE scan => same spot, new spot or heat/activate

WEEK of Nov 13th – 4 Beam Setup to ILD

- Mon-Tue to FC2

  - Wien Angle => looking at old 1050 setup, Yves is working B @ 5th pass

  - 4- bunch profile => benchmark ABCD @ 499 and 250

  - 4-laser phases => record ABCD phases @ 499 and 250 to save

  - 4-beam chopper

    - => determine atten/slit values for proposed currents

    - => measure bleed through

- Wed-Fri to ILD

  - Bunch length setup => status of tool and are there new settings ?

  - 0L-0R quad centering => update BPM offsets?

  - Injector match => important to test if new RF settings ?

  - high current setup => explore BD @ 250 & ABCD @ 250 ?

- What else ?

  - 750 MHz BPM detector

  - Managing expectations (halls have priorities)

  - Maybe put beam in the resonant cavity polarimeter on Tuesday…

WEEK of Nov 20th – Week of Thanksgiving – no setup planned

WEEK of Nov 27th – CEBAF setup

- CIS On-Call Support => Please send me your unavailability through March 22nd

WEEK of Dec 4th – Physics begins…

Must – SAD 2018 (Mar 23rd  – September 30th)

200 kV Gun Installation (integrated time is 2-3 weeks)

- 200 kV HV chamber (R28 connector, excellent vacuum, no FE, reliable)

- NEG tube (two BPM’s + FH solenoid)

- 350 kV HVPS (SF6 tank, 350-R28 cable, resistor & short, ENG and software)

200 kV Injector Testing (integrated time is 3-4 weeks)

- Demonstrate HVPS safe and functional operation

- Demonstrate 200kV application to gun at CEBAF (no FE)

- Deliver 200keV beam from gun

- Evaluate existing beam line (magnets, diagnostics)

- Magnet currents increase by 28%

- Evaluate stability of new HVPS (may compare w/ present supply <150kV)

- Evaluate photocathode lifetime

- Assess range/performance of INJTWF (Wiens and solenoids)

- Assess chopper at higher power (Hovater)

- Assess chopping/dechopping with higher voltage beam

- Measure transmission/bunchlength vs. intensity/charge from 100-200kV

- Assess range of compatibility with existing ‘booster’ capture/quarter

Bubble Experiment (integrated time is 5 weeks)

- 1 week installation

- 2 week engineering run

- 2 week physics run

Laser Table Jobs (integrated time 2 weeks)

- STAC5 Upgrade

  - Replace 6 rotational steppers (attenA, attenB, attenC, attenD, RWP)

  - Replace 2 linear steppers + ADC (lensX, lensY, QE scan ADC)

Stretch – SAD 2018 (Mar 23rd  – September 30th)

Rebuild Baked Beamline for 200 kV Operation

- MUST

  - repurpose as many components as possible

  - upgrade/fabricate those that cannot operate at 200kV

  - eliminate unnecessary or unused components (Brock cavity)

  - simplify setup where possible w/o loss of functionality (injsteer, PQB)

  - develop model to assess ME layout

  - coordinate w/ other groups that needs ~weeks for parallel upgrades !!!

- SHOULD

  - replace/fabricate components when obvious performance improvement

  - improve beamline vacuum

- Installation (10-12 wks)

- Disconnects and pull beam line out (1 wk)

- Break down and rebuild new beam line with survey as needed (2 wk)

- Install new beam line with 1A alignment (1 wk)

- Pumpdown, leak check, bake prep and bakeout (2-3 wks)

- Post bake leak check, hookups and HCO (2 wks)

- Beam line commissioning (2 wks)

- Components

- Fabricate new DS dipole magnet w/ AWG16 on DS fixture (need 3A)

- Existing transport solenoids should work (need to check MFG)

- Repurpose existing Wien filters

  - High voltage power supplies ordered

  - Existing feedthrough + barrel polished electrodes ready for UITF test

  - Modest vacuum chamber modifications are reasonable

  - Coil design needs to be improved (too many tight bends)

Must & Stretch – SAD 2018 (Mar 23rd  – September 30th)

| 200kV Gun Capable | MAR | 26 | Bubble Install |
| --- | --- | --- | --- |
|  | APR | 2 | Bubble Engineering |
|  |  | 9 | Bubble Engineering |
|  |  | 16 | Install 200kV Gun / HVPS |
|  |  | 23 | Install 200kV Gun / HVPS |
|  |  | 30 | Install 200kV Gun / HVPS |
|  | MAY | 7 | Slop |
|  |  | 14 | Commission @ 200keV |
|  |  | 21 | Commission @ 200keV |
|  |  | 28 | Commission @ 200keV |
|  | JUN | 4 | Slop |
|  |  | 11 | Restore FC2 |
|  |  | 18 | Bubble Run @ 130 keV |
|  |  | 25 | Bubble Run @ 130 keV |
| Beamline Upgrade | JUL | 2 | Slop |
|  |  | 9 | Disconnect and pull beamline |
|  |  | 16 | Breakdown and rebuild |
|  |  | 22 | Breakdown and rebuild |
|  |  | 30 | Slop |
|  | AUG | 6 | Install and 1A |
|  |  | 13 | Pumpdown, leak check, bakeout |
|  |  | 20 | Pumpdown, leak check, bakeout |
|  |  | 27 | Slop |
|  | SEP | 3 | Hook-ups and HCO |
|  |  | 10 | Hook-ups and HCO |
|  |  | 17 | Commission |
|  |  | 24 | Commission |