## Detailed
|  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  | May 22 |  |  |  | 2022-06-22
Main task | Sub-task | Detailed task | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | Q2 | Q3 | Q4
Beam dynamics simulations
| Define anode tube slot width | Perfrom ion back bombardment simulation with anode/tube bias combination to determine if 1 in wide tube slots can be used, or if we have to use 0.5 in wide tube slots
Electrostatic design
Anode-cathode gap
Use Shaun's latest model for anode cathode gap 2.506 inches with nominal anode to produce field map ane evaluate beam kick
Find anode tilt andle that cancels kick
Produce field maps with aanode-tube biasing combinations for ioon studies to define anode tube slot width
Vacuum modeling
Anyting here, Marcy?
Electrostatic + vacuum design ready
Engineering design
Vacuum chamber + NEG modules
Design and produce engineering drawings
Anode
Design macor spacer to provide -2.5 deg vertical tilt to anode
Anode spacer tube
Design wth 1 inch wide slots (6 slots)
Design with 0.5 inch wide slots (6 slots)
Engineering drawings ready
Fabrication
Vacuum chamber + NEG modules
NEG wiring screens
Anode
2 macor shield tube long version (1 inch long)
4 macor flat spaces (use 2 + 2 spares)
2 macor slanted spacers to provide -2.5 deg angle for anode (usee 1 + spare)
1 anode spacer tube with 6 slots. Slots width TBD
Components ready
Assembly
Vacuum chamber + NEG modules
Install NEG wiring screen
Install extractor gauge
Electrode + triple point junction shield
Dry-fit assembly
UHV clean
Vacuum degas 900 C for x hours
Final assembly
Fiducial
Install in HV chamber
Anode assembly
Dry-fit assembly
UHV clean
Vacuum degas 900 C for x hours
Final assembly
Install in HV chamber
Align to center on cathode axis
Gun rerady for install in beam line

## Broad view
Main task | Task | Year 1 | Year 2 | Year 3
Physics design
Beam dynamics simulations: short, high peak current bunches
Electrostatic design: < 10 MV/m at 350 kV + limit ion damage
Vacuum modeling: limit photocathode ion damage
Engineering design
Vacuum chamber + NEG modules
HV Feedthrough compatible with 350 kV commercial cable
Electrode + triple point junction shield
Electrode support structure
Anode + support frame
Component fabication and gun assembly
Vacuum chamber + NEG modules
HV Feedthrough compatible with 350 kV commercial cable
Electrode + triple point junction shield
Electrode support structure
Anode + support frame
FTEs |  | 1 | 1.5
FTE classification |  | SSI/PD | SSI/PD + ME