## Laser drive 1
CEBAF Laser RF drive system
(simplest/cheapest/system already obsolate)
Task/Milestone |  | SE | EE/CS | ET | ED | PHY | Labor Total | Materials | Shipping | Travel | Start | Finish | Notes
Coceptual design |  |  | 0.4 | 0.4
add 499 MHz LLRF VME module |  |  | 0.2 | 0.2 |  |  |  | 1 |  |  |  |  | old Separator module
modification of the LO/MO system |  |  | 0.4 | 0.8 | 0.4 |  |  | 1000
firmware/software |  |  | 1
modification of the 499/250 MHz drive chassis |  |  | 0.2 | 0.4 |  |  |  | 1000
commisioning |  |  | 1
Total (weeks) |  | 0 | 3.2 | 1.8 | 0.4 | 0 | 5.4
Hourly rate w/fringe* |  | 103 | 88 | 70 | 75 | 120
Weekly rate w/ fringe |  | 4120 | 3520 | 2800 | 3000 | 4800
Labor w/fringe (w/o overhead) & Materials |  | 0 | 11264 | 5040 | 1200 | 0 | 17504 | 2001 | 0 | 0 |  |  | 19505
G&A (TBD)* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Total |  | 0 | 11264 | 5040 | 1200 | 0 | 17504 | 2001 | 0 | 0 |  |  | 19505
Total* | [12 empty] | 19505
SE/MN: Senior Engineer/Manager
EE/CS: Electrical Engineer/ Computer Scientist
ET: Electronic Technician
ED: Electrical Designer
PHY: Physicist
* Subject to change
DRAFT Subject to Change

## Laser drive 2
CEBAF Laser RF drive system
new design
Task/Milestone |  | SE | EE/CS | ET | ED | PHY | Labor Total | Materials | Shipping | Travel | Start | Finish | Notes
Coceptual design |  |  | 3 | 2 | [8 empty] | new design: 4 channel , 499/250/ MHz with full feedback and Epics control
RF Front/End design |  |  | 2 | [9 empty] | TBD/ laser pulse feedback ?
RF Front/End prototype |  |  | 0.4 | 0.4 |  |  |  | 3000
digitizer /COTS or home made ? |  |  | 1 |  |  |  |  | 1500
new 4 channels module / parts |  |  | 1 | 1 |  |  |  | 5000
new 4 channels module / assembly |  |  | 0.2 | 0.4 |  |  |  | 1000
modification of the LO/MO system |  |  | 0.4 | 0.6 | 0.4 |  |  | 1000
frimware/software |  |  | 4
pannels, cables, attenuators etc.. |  |  | 0.1 | 0.1 |  |  |  | 1000
test/commisioning |  |  | 2 | 0.4
Total (weeks) |  | 0 | 14.1 | 4.9 | 0.4 | 0 | 19.4
Hourly rate w/fringe* |  | 103 | 88 | 70 | 75 | 120
Weekly rate w/ fringe |  | 4120 | 3520 | 2800 | 3000 | 4800
Labor w/fringe (w/o overhead) & Materials |  | 0 | 49632 | 13720 | 1200 | 0 | 64552 | 12500 | 0 | 0 |  |  | 77052
G&A (TBD)* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Total |  | 0 | 49632 | 13720 | 1200 | 0 | 64552 | 12500 | 0 | 0 |  |  | 77052
Total* | [12 empty] | 77052
SE/MN: Senior Engineer/Manager
EE/CS: Electrical Engineer/ Computer Scientist
ET: Electronic Technician
ED: Electrical Designer
PHY: Physicist
* Subject to change
DRAFT Subject to Change
DRAFT Subject to Change