## Slide 1: UITF Project Status Meeting
Matt Poelker
October 21, 2015

## Slide 2: Outline
  Purpose: to inform Lab Leadership of the UITF status
  Action Items (from previous meetings)
Project Update
  Progress Update
  Milestones Update
  Budget Update
  Highlights & Concerns
  Next meeting agenda
Notes: RW=Roy Whitney

## Slide 3
To refresh your memory…
What we started with…
UITF as imagined

## Slide 4
Action Items – October 21, 2015 Minutes
Recall, UITF spending lockdown toward end of August…
Cancelled trim card PR, “Electricity to top of Cave1” PR held up
Electricity PR approved Nov. 11
No other procurements since then
20 PW of labor approved, devoted to Cryo and Facilities
UITF costs approaching some DOE project limit….
New Action Items:
Nov. 11, 2015: meet to re-scope the project, distribute costs within four “fences”
Notes: RW=Roy Whitney

## Slide 5: Progress Update
  Major components
  Facilities
  Engineering
    Mech Design
    Cryo
    Safety Systems
    I&C
    DC Power
    Low Level RF systems
    High Power RF
    Survey & Alignment
  SRF
    Commission with RF
  Operations
    Network and communications
Green means we can see progress

## Slide 6: Progress Update
  Major components
  Source Group
    Reliable 350kV ops
    Beam to cup in front of ¼ CM
    Beam to cup in front of HDIce
  EHSQ
    Shielding approval, ODH assessment
    Global hazard review
    FSAD
    Accel Readiness Review
    Commissioning Plan
  HDIce
    Installation at Cave
    Beam on HDIce
Green means we can see progress

## Slide 7
PSS conduit added to wall, more to do still
Racks bolted down, side panels added
Need machine shop help for klystron racks
Cryo has delivered some transfer line
Installation Group (safety related)

## Slide 8
Shielding at Penetrations
Working with Vashek to specify shielding at penetrations

## Slide 9
Cave 2
All big “T” shaped yellow blocks have been moved to building 58. Waiting for “Big Bite” to clear out to complete the labyrinth perimeter, waiting for Facilities to secure 2nd layer

## Slide 10
Facilities (T. Renzo)

## Slide 11
Facilities: Electrical part1
Low bid $78k, hope to complete by end of December (moved off UITF project?)
Another PR for network cables, 18k$, waiting for approval

## Slide 12
Simple ODH solution: passive venting
Large entry/exit with chain-link gate
Large rectangular opening near HDIce
Some added radiation shielding required
Two 30” vent pipes in Cave1
Add pipe to vent the primary and secondary relief valves on ¼ CM through small penetration on wall

## Slide 13
Big Chimney near HDIce
Helium source terms identified for ¼ CM and CTF, and also HDIce
Strategy still focused on using passive exhaust vents to maintain ODH0 (or ODH1) conditions
Large vent 30 ft2 near HDIce, 10 ft2 vents inside Cave1, ceiling penetration with chimney, chain link gate, Test Lab high bay equivalent to “outside”
Will Oren working with Cryo, SRF, HDIce to complete the assessment

## Slide 14
Combine the two features that provided incremental success: shed and doped insulator
Next test late September

## Slide 15
Cathode electrode with screening electrode and dummy photocathode installed, under vacuum, now undergoing HV conditioning
Repeat with black, mildly conductive insulator, now in-house
Will know if we have a gun by end of year
At 305 kV today
Field emitters burning OFF

## Slide 16
J. Hansknecht putting UITF 400 kV power supply together, inside SF6 tank
UITF High Voltage Power Supply

## Slide 17: Milestones Update
WBS | Item | Milestone Description | Start Date | Projected Finish | % Complete | Days Float? | Change (%) | Change (Days)
1.04.xxx | Facilities | Civil work complete | 6-4-15 | Feb 2016 | 50% |  | 10 to 50% | 
 | Gun | Demonstrate gun ok at 350 kW at FEL GTS |  | Dec 2015 | 80% |  | 0 | 
 | CM | Commission cold ¼ CM, no beam |  | Jan 2016 | 20% |  | 10 to 20% | 
 |  | Beam from Gun to Cup in front of ¼ CM |  | Mar 2016 | 20% |  | 10 to 20% | 
 |  | Beam thru ¼ @ MeV energy delivered to cup in front of HDIce |  | Jun 2016 | 0 |  |  | 
 |  | Beam to HDIce |  | Aug 2016 | 0 |  |  | 
Tom Renzo happy with ODH vent plans, now working on aspects of Cave2 structure, taking credit for Electricity procurement
Not as much progress on Gun Plan Y: my guys working on LERF, bubble chamber and CEBAF

## Slide 18
Month by Month Spending Profile

## Slide 20
Proposed re-scoping
Facilities
HDice
New UITF
Cryo Infrastructure
  Facilities
Cryo Infrastructure including some RF
HDIce/Polarized Target Beamline
New UITF

## Slide 21
Four “Fences”
Facilities (fairly well defined)
$269k and 34 PW
Cryo Infrastructure (some confusion over procurements, lots of labor)
$68 to 139 and 111 PW for cryo portion
$41k and 34 PW for klystron portion
HDIce/Polarized Target Beamline
$130k
New UITF
$467k (I’ve double counted procurements…number too large)

## Slide 22: Schedule Ramifications
  Current status:
    Installation Group, under auspices of Safety, continues to do truly useful work (racks, penetrations, shielding, PSS conduit)
    T. Renzo has submitted Cave2 structural package for review, but not in Rusty’s budget scope
    Jason W. thinks electricity can be supplied to racks by end of December. Hope network PR can get approved
    Cryo still thinks they can have the old transfer lines removed and some portion of new plumbing installed by end of 2015. This let’s my group begin installing keV beamline starting January. Creel would love to get past UITF. UITF cryo controls and CTF upgrade are intertwined….
    Source group making progress on gun at LERF GTS
    Will Oren and HDIce have created spec for purchasing helium (our dewar approach to cooling HDIce)
    Oren and Areti finalizing ODH assessment (ODH0)

## Slide 23: Schedule Ramifications
  Current status:
    Proposed re-scoping into four “fences”: Facilities, Cryo infrastructure including high power RF, HDIce/Polarized Target Beamline, and new-UITF
    Facilities and Cryo fairly well defined. Need to itemize the HDIce and new-UITF costs.
    Waiting for charge codes…
    I think schedule has slipped by at least two months
    No final word yet on CTF schedule, or whether Physics will support HDIce budget request for required work that precedes beam tests at UITF. These factor help gauge the relevance of August 2016 schedule milestone.

## Slide 24: Schedule Ramifications
  Recall, next big milestone…commission ¼ CM (no beam), scheduled for Feb. 2016 (cryo, ODH, LL and HP RF, software, adequate shielding, EHS&Q approvals)
  This requires:
    Klystron rack finished, R. Nelson building control panel, rf procurements approved
    Low level rf boards complete, installation in racks begins
    IOCs installed, Software group installing software
    Installation group working opportunistically: shield plates, PSS conduit, cable trays, waveguides, vent stacks for relief valves
    Safety System Group working on ODH system
    Cryo group installing new transfer lines…
    Procurements for Cryo control system approved, installed

## Slide 25: Schedule Ramifications
  Commission ¼ CM (no beam), scheduled for Feb 2016
    Electric/FM – ($78k + $23k for com. conduit) 101 k$
    Control room – -
    SRF checkout of ¼ CM present condition – -
    Low Level RF – 16 k$
    High Power RF – 25 k$
    Network controls – 33 k$
    Software control of RF – -
    adequate shielding (Cave2 with a roof) – -
    Cryo – (controls and pipe) 68 +/- k$
    Installation group 9 k$
    ODH - SSG 2 k$
    EHS&Q approvals… -
    Total 254 k$

## Slide 26
Status Cryo
Related to ¼ Cryomodule
A challenge: appreciating the best way to connect to CTF, so as not to do it again
  How to cool HDIce (need to downselect)
  “Parking” the ¼ CM can influence design
  Anticipated CTF upgrades
Related to HDIce
Purchase LHe (expensive), Cryo group provides dewars (was our Plan A), connect HDIce to CTF
Message1: Need to stop thinking and start marching
Message2: 4K cold box work scheduled for August 2016

## Slide 27: Labor-focused Tasks
  Installation Group
    Cable trays, PSS conduit, penetration shielding, rack prep in advance of electric work, removal of rails and LCW piping Cave2, silver solder the quad magnet cooling tubes, waveguides
  Have our electricians install network cable
  Ops staff to install network switches, IOCs and software
  Magnet Mapping, quads and solenoids
  Mechanical Design: finish keV region, resume MeV region design
  DC Power: refurbish the racks for trim cards, re-install trim cards
  Low Level RF – finish construction of rf control boards
  High Power RF – work on the control panel and klystron rack
  Cryo: remove old transfer lines, install new ones, controls

## Slide 28: Summary
Doing what we can without spending much money
I will go over the procurement and labor estimate again, group by group
Waiting for guidance

## Slide 29: Backup Slides
Backup slides from past meetings, P&C meetings

## Slide 30: Design work was stopped…would like it to continue

## Slide 31
Notes: Interior Page Design 2

## Slide 32
“Shed” triple-point protection
Doped insulator
SF6
R350 epoxy receptacle
Combination of doped insulator and shed, SF6 and epoxy receptacle, plus added length
Yan Wang has modeled the shed, a good design…
…then in October

## Slide 33
Carryover = $81k
Cancelled $71k trim card PR

## Slide 34: FY16 Procurements?
 | ~ required | spent in FY14 FY15 | To purchase in FY16 | 
Facilities: | 300 | 56.2 | 245 | 
Cryo | 90.8 | 0 | 90.8 | waiting for update
RF | 252.5 | 121.4 | 131.1 | 
Gun | 451.2 | 265.5 | 130 | includes beamline components + contract designer
I&C | 219.5 | 7.6 | 211.9 | Hope to reduce this number using PLC technology
SSG | 45.7 | 1 | 44.7 | 
DC power | 144.5 | 100 | 8 | Trim cards…
Magnets | 120 | 119.3 | 0 | shop to make quads, assumed 100k but could be less Still need three dipoles
Network | 58 | 58 | 0 | 
Total | 1682 | 671 | 862 | Of course, hope the number comes in lower: 750 k$

## Slide 35: Original vs Current Cost Estimate
Presented at UITF meeting May 13, 2015:
Total cost estimate. The specific allocations for FY15 and 16 are not correct
Original Est. by Hari Areti |  | FTEs | Labor | Proc | Total |  | Labor | Proc | Total | 
on 2-7-2014 | FY14 | 3.7 | 462.54 | 478.95 | 941.49 |  | 682.70 | 671.23 | 1,353.94 | 
 | FY15 | 2.5 | 312.08 | 557.10 | 869.18 |  | 465.00 | 830.07 | 1,295.07 | 
 | FY16 | 0 | - | - | - |  | - | - | - | 
 | Total | 6.2 | 774.62 | 1,036.05 | 1,810.66 |  | 1,333.458 | 1,501.306 | 2,649.011 | 
Revised Est. |  | FTEs | Labor | Proc | Total |  | Labor | Proc | Total | 
by Matt Poelker | FY14 | 1.2 | 160.32 | 189.48 | 349.80 |  | 233.08 | 274.29 | 507.37 | 47.6%
on 5-13-2015 | FY15 | 8.6 | 937.36 | 611.17 | 1,548.53 |  | 1,396.67 | 907.95 | 2,304.62 | 49.0%
 | FY16 | 7.9 | 940.39 | 881.33 | 1,821.72 |  | 1,422.80 | 1,333.46 | 2,756.26 | 51.3%
 | Total | 17.7 | 2,038.07 | 1,681.98 | 3,720.05 |  | 3,052.56 | 2,515.70 | 5,568.26 | 
Dfference from original estimate |  | (11.5) | (1,263.46) | (645.93) | (1,909.39) |  | (1,719.10) | (1,014.40) | (2,919.25) | 
Loaded $
Direct $

## Slide 36: Revised Estimates Breakdown
Original request to DOE: $2.6M (loaded)
Current estimate for completion: $5.6 M (loaded)
Delta increase of $2.9M (loaded)
Labor estimates
  Underestimated effort by 11.5 FTEs
  Increased labor by $1.7M (loaded)
Procurements
  Underestimated by ~$1M (loaded)
  Several sub-system components were not included in the original estimate and later determined were necessary to complete the scope

## Slide 37: Comparison Procurement Estimates (Direct $)
System | Prev | Now | Delta | Comment
Facilities | 305 | 300 | -5 | (numbers are Proc and Labor)
Safety System | 59 | 46 | -13 | 
RF Systems | 125 | 253 | +128 | rf control boards, klystron PS
Cryogenics | 40 | 91 | +51 | Pipe, heat exchanger
Polarized Source | 255 | 262 | +7 | Gun insulators, beamline parts
I&C | 131 | 220 | +89 | BPMs, viewers, picoammeters
DC Power | 0 | 145 | +145 | Trim cards and parts
Magnets | 58 | 120 | +62 | Addl. quads, correctors, dipoles
SRF | 50 | 0 | -50 | 
HDIce | 5 | 0 | -5 | 
Network, IOCs | 0 | 58 | +58 | 
CIS FY14 Actuals | 0 | 189 | +189 | FY14 actuals
Total | 1,028 | 1,684 | +656 | 

## Slide 38: FY14 and FY15 UITF Procurements
FY14 |  |  |  | FY15 |  |  | Addl. expected FY15 procurements | 
Solid Works CAD |  | 2.2 |  | Insulator flange | 1 |  | Contract Mech Designer | ~ 30
450kV HV power supply |  | 31.1 |  | bpm components | 7.6 |  | stairs | ~ 20
semiconducting R30 insulators |  | 52.6 |  | semiconducting R30 insulators_v2 | 22.3 |  | trim cards | ~100
gun HV chamber |  | 7.8 |  | Klystron HV power supply | 55.5 |  | quad magnets (machine shop) | 70 to 130
ion pumps |  | 15.1 |  | concrete wall removal | 32 |  | Chopper rf amplifiers (x2) | 44
beamline Y chamber |  | 5 |  | LLRF parts | 15.1 |  | water skid for chopper | 3
photocathode prep chamber |  | 4.5 |  | steering magnets | 19.3 |  | keV beamline support structure | 6.5
drill penetrations in concrete |  | 4.2 |  | SF6 tank | 11.3 |  | Addl. FY15 procurement total | 303.5
assorted |  | 3.9 |  | waveguide | 3.8 |  |  | 
Credit card |  | 21.8 |  | SSG sensor | 1 |  |  | 
Machine shop |  | 40.8 |  | assorted | 9.4 |  |  | 
total | 189 |  |  | total | 178.3 |  |  | 
FY14 + FY15 Procurements: 670.8
UITF Total Procurements 1682