## monthly schedule
ALL Procurements Direct Dollars
| October | November | December | January | February | March | April | May | June | July | August
| Facilities: electric Cave1 | Facilities: network | Facilities: structural | Facilities: electric Cave2 | Facilities: Fire | Facilities: Paint, Mech, Gate |  | (51.008k) |  |  |  | Just electricity, nothing else |  |  | 109k$ includes 20% extra for unanticipated Jlab overhead
| Procurement: 109k$ | Procurement: 23k$ | Procurement: 94k$ | Procurement: 50k$ | Procurement: 10k$ | Procurement: 19k$ |  | (15.176k) |  |  |  | Just Cave1, top of Cave1 and control room |  |  | 23k$ in November is for communications (18k$) and stuff we forgot
| Labor FME: 2 PW | Labor FME: 2 PW | Labor | Labor | Labor | Labor: |  | (25.952k) |  |  |  | Cave2 electricity will cost more later
(10.899k)
TOTAL Labor = $103.035k
| Cryo - Controls | Cryo - Controls | Cryo - Controls | Cryo - Controls
| Procurement: 18k$ for controls | Procurement: 0k$ | Procurement | Procurement | 14 weeks total | Buddy has ordered everything he needs for controls….
| Labor EE: 2PW | Labor EE: 2PW | Labor EE: 0.5PW | Labor EE: 0.5PW | (14.175k) | no more procurements necessary
| Labor ET: 2PW | Labor ET: 4PW | Labor ET: 2PW | Labor ET: 1PW | (18.063k)
| ALL Procurements Direct Dollars October: Cryo - Design and Plumbing; ALL Procurements Direct Dollars November: Cryo - Design and Plumbing; ALL Procurements Direct Dollars December: Cryo - Design and Plumbing; ALL Procurements Direct Dollars January: Cryo - Design and Plumbing; ALL Procurements Direct Dollars February: Cryo - Design and Plumbing; ALL Procurements Direct Dollars March: 97 weeks total | After this, there will be additional work for HDIce, which we are still pondering the path forward
| ALL Procurements Direct Dollars October: Procurement: 20k$; ALL Procurements Direct Dollars November: Procurement: 20k$; ALL Procurements Direct Dollars December: Procurement: 10k$; ALL Procurements Direct Dollars January: Procurement: 0k$; ALL Procurements Direct Dollars February: Procurement: 0k$; ALL Procurements Direct Dollars April: Can SRF tech staff help with labor? | i.e., there are different ways we can cool the HDIce target: buying Lhe, creating our own fill station, or attaching directly to CTF
| Labor ME: 3 PW | Labor ME: 2 PW | Labor ME: 1 PW | Labor ME: 2 PW | Labor ME: 0 PW | (20.272K)
| Labor MD: 5 PW | Labor MD: 3 PW | Labor MD: 1 PW | Labor MD: 0 PW | Labor MD: 0 PW | (22.32K)
| Labor MT: 16 PW | Labor MT: 16 PW | Labor MT: 16 PW | Labor MT: 16 PW | Labor MT: 16 PW | (99.52 + 50.48 = 150K) | TOTAL Labor = $224.83k
[5 empty] | Cryo - HDIce | Cryo - HDIce | Cryo - HDIce | Cryo - HDIce
[5 empty] | Procurement: 20k$ | Procurement: 20k$ | Procurement: 10k$ | Procurement: 0k$ | 81 weeks total
[5 empty] | Labor ME: 3 PW | Labor ME: 2 PW | Labor ME: 1 PW | Labor ME: 2 PW | (20.272k)
[5 empty] | Labor MD: 5 PW | Labor MD: 3 PW | Labor MD: 1 PW | Labor MD: 0 PW | (22.32k)
[5 empty] | Labor MT: 16 PW | Labor MT: 16 PW | Labor MT: 16 PW | Labor MT: 16 PW | (79.616 + 40.384 = 120k) | TOTAL Labor = $162.592k
| October | November | December | January | February | March | April | May | June | July | August
[12 empty] | Installation Group tasks: |  | Ricky Taylor, Bern Johnson, Neil Wilson
|  | Installation Group | Installation Group | Installation Group | Installation Group | Installation Group | waveguides, girders, cable trays | waveguides, girders, cable trays |  |  |  | November: | attach rad shielding plates above and below penetrations
|  | Procurement: 3k$ | Procurement: 3k$ | Procurement: 13k$ | Procurement: 3k$ | Procurement: 3k$ | LCW, compressed air, | LCW, compressed air, |  |  |  | December: | SSG conduit for ODH and PSS, cable trays
2/PW |  | Labor TD3: 2.4 PW | Labor TD3: 2.4 PW | Labor TD3: 2.4 PW | Labor TD3: 2.4 PW | Labor TD3: 2.4 PW | Labor TD3: 2.4 PW | Labor TD3: 2.4 PW | (33.6k) |  |  | January: | Finish railings above cave
2.431/PW |  | Labor AC2: 0.6PW | Labor AC2: 0.6PW | Labor AC2: 0.6PW | Labor AC2: 0.6PW | Labor AC2: 0.6PW | Labor AC2: 0.6PW | Labor AC2: 0.6PW | (10.21k)
TOTAL Labor = $43.81k)
|  | Ops Network and Controls | Ops Network and Controls | Ops Software | Ops Software | Ops Software | Ops Software | Ops Software | Ops Software | Ops Software | Ops Software | Ops Network and Controls:
|  | Procurement: 32.5k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | Procurement: 0k$ | (5) VME IOCs @ 3500/ea - $17,500
|  | Labor: 5 PW (Brad Cumbia) | Labor: 5 PW (Adam Carpenter) | Labor CSci: 5 PW (Lahti) | Labor CSci: 5 PW (Lahti) | Labor CSci: 5 PW (Higgins) | Labor CSci: 5 PW (Higgins) | Labor CSci: 5 PW (Higgins) | Labor CSci: 5 PW (Kissee) | Labor CSci: 5 PW (Kissee) | Labor CSci: 5 PW (Kissee) | (1) Network Switch Line Cards $15,000
| November: (12.026k); December: (14.129k); January: (30.068k); May: (51.779k); June: (37.767k) | TOTAL Labor: $145.769k
| November: High Power RF; December: High Power RF; January: High Power RF; February: High Power RF; March: High Power RF | Master oscillator |  | (we will borrow an MO from somewhere) |  | straight waveguide: TBD
| November: Machine shop: 5k$; December: Procurement: 15k$ waveguides; January: Procurement: 15k$; February: Procurement; March: Procurement | Two LL rf control boards |  |  |  | flex: 4 x 1.5k ea = 6k
| November: Procurement: 5k$ HPA controller | klystrons installed in racks |  |  |  | directional couplers: 2 x 1.5k = 3k
| November: Labor EE: 2 PW; December: Labor EE: 2 PW; January: Labor EE: 2 PW; February: Labor EE: 2 PW; March: Labor EE: 2 PW; April: (31.29k) | controls hardware |  |  |  | sweeps/miters; TBD
| November: Labor ET: 2PW; December: Labor ET: 2PW; January: Labor ET: 2PW; February: Labor ET: 2PW; March: Labor ET: 2PW; April: (19.87k) | waveguides (also requires MD support to layout) |  |  |  | gaskets, hangers, hardware
| November: Labor ED: 2 PW; April: (4.19k); May: TOTAL Labor: $55.35k |  |  |  |  | HPA controller: $5k
| Low Level RF | Low Level RF | Low Level RF | Low Level RF | Low Level RF | Low Level RF | Low Level RF | Low Level RF | Low Level RF |  |  | who to build the HP klystron rack and controls? Chad?
| Procurement: 5 k | Procurement: 5 k | Procurement: 2k | Procurement: 2k | Procurement: 2k | Procurement: 2k | Procurement: 2k | Procurement: 2k | Procurement: 2k
| Labor ET: 2 PW (Breisel) | Labor ET: 2 PW (Breisel) | Labor ET: 4 PW (Wisman) | Labor ET: 4 PW (Wisman) | Labor ET: 4 PW (Wisman) | Labor ET: 4 PW (Wisman) | Labor ET: 4 PW | Labor ET: 4 PW | Labor ET: 4 PW | (63.584k)
| boards | boards | Labor EE: 2 PW (Hovater) | Labor EE: 2 PW (Hovater) | Labor EE: 2 PW (Hovater) | Labor EE: 2 PW (Hovater) |  |  |  | (38.768k) | TOTAL Labor = $102.352k
|  |  |  | SRF Institute | SRF Institute
|  |  |  | Procurement: 10k$ vent pipe | Procurement:
|  |  |  | Labor: 2PW (J. Fischer) | Labor: 2PW (M. Drury) |  | TOTAL Labor = $17.65k
| November: SSG: ODH; December: SSG: ODH; January: SSG: ODH | ODH 14 PW
| November: Procurement: 2k$ (tube PR); December: Procurement: 0k$; January: Procurement: 0k$ | 2k$ procurement total, the PR in queue waiting to be signed
| November: Labor: 0 PW; December: Labor: EE 2 PW; January: Labor: EE 0.5 PW; February: (8.4725k) | Neil to help with installation
|  |  | Labor: ET 3 PW | Labor: ET 3 PW | (12.528k)
|  |  | Labor: ED 1PW | Labor: ED | (2.252k) | Note: Install group performed Skilled Trade work
TOTAL Labor = $23.2525k
| October | November | December | January | February | March | April | May | June | July | August
| January: SSG: PSS; TOTAL Labor = $23.2525k February: SSG: PSS; TOTAL Labor = $23.2525k March: SSG: PSS; TOTAL Labor = $23.2525k April: SSG: PSS | [5 empty] | PSS 68 PW, original estimate | Henry said he can't get to PSS till January
| January: Procurement: 35k$; TOTAL Labor = $23.2525k February: Procurement: 0k$; TOTAL Labor = $23.2525k March: Procurement: 0k$; TOTAL Labor = $23.2525k April: Procurement: 0k$ | [5 empty] | 35k$ procurement
|  |  |  | Labor: EE 5 PW | Labor: EE 5 PW | Labor: EE 5 PW | Labor: EE 5 PW | (67.78k)
|  |  |  | Labor: ED 3PW | Labor: ED 0 PW | Labor: ED 0 PW | Labor: ED 0 PW | (6.756k)
| January: Labor: ET 10PW; TOTAL Labor = $23.2525k February: Labor: ET 10PW; TOTAL Labor = $23.2525k March: Labor: ET 10PW; TOTAL Labor = $23.2525k April: Labor: ET 10PW; TOTAL Labor = $23.2525k May: (83.52k); TOTAL Labor = $23.2525k June: Note: Install group performed Skilled Trade work | [5 empty] | Neil to help with installation
TOTAL Labor = $241.576k
|  |  |  | Design: finish keV | Design: finish keV | Design: MeV beamline | Design: MeV beamline | Design: MeV beamline | Design: MeV beamline
|  |  | (17.488k) | Labor: 4 PW (Shaun Gregory) | Labor: 4 PW (Shaun Gregory) | Labor: 4 PW (Shaun Gregory) | Labor: 4 PW (Shaun Gregory) | Labor: 4 PW (Shaun Gregory) | Labor: 4 PW (Shaun Gregory) | (34.976k)
|  |  | (14.452k) | Labor: 1 PW (Danny Machie) | Labor: 1 PW (Danny Machie) | Labor: 1PW (Danny Machie) | Labor: 1PW (Danny Machie) | Labor: 1PW (Danny Machie) | Labor: 1PW (Danny Machie) | (28.904k)
|  |  | TOTAL = $31.94k | [6 empty] | Total Labor = $63.88k
| October | November | December | January | February | March | April | May | June | July | August
|  |  |  | I&C: valves, viewers | I&C: valves, viewers | I&C: valves, viewers | I&C: valves, viewers | I&C: valves, viewers | I&C: valves, viewers | I&C: valves, viewers
|  |  |  | I&C: BPMs, current monitors | I&C: BPMs, current monitors | I&C: BPMs, current monitors | I&C: BPMs, current monitors | I&C: BPMs, current monitors | I&C: BPMs, current monitors | I&C: BPMs, current monitors
|  |  |  | I&C: vacuum | I&C: timing system | I&C: timing system | I&C: timing system | I&C: vacuum | I&C: vacuum | I&C: vacuum
|  |  |  | I&C:timing system | I&C:timing system | I&C:timing system | I&C:timing system
|  |  |  | Procurement: $100k total | Procurement | Procurement | Procurement | Procurement: $60k total | Procurement | Procurement
|  |  | (12.576k) | Labor: EE 4 PW | Labor: EE | Labor: EE | Labor: EE | Labor: EE 3 PW | Labor: EE | Labor: EE | (9.432K)
|  |  | (31.984k) | Labor: ET 4 PW | Labor: ET 4PW | Labor: ET 4PW | Labor: ET 4PW | Labor: ET 4 PW | Labor: ET 4 PW | Labor: ET 4 PW | (23.988K)
|  |  | (17.248k) | Labor: AC1 2 PW | Labor: AC1 2 PW | Labor: AC1 2 PW | Labor: AC1 2 PW | Labor: AC1 2 PW | Labor: AC1 2 PW | Labor: AC1 2 PW | (12.936K)
|  |  | Total Labor: $61.808k | [7 empty] | Total Labor = $46.356k
|  |  |  | DC Power | DC Power | DC Power | DC Power | DC Power | DC Power | DC Power
|  |  |  | Procurements: 10k$ cable etc., | Procurements | Procurements | Procurements | Procurements: 60k$ trim cards | Procurements: 10k$ cable etc., | Procurements
|  |  | (9.951k) | Labor: EE 1.5 PW (Coleman) | Labor: EE 1.5 PW | Labor: EE | Labor: EE | Labor: EE | Labor: EE | Labor: EE
|  |  | (2.320k) | Labor: ED 1PW | Labor: ED | Labor: ED | Labor: ED | Labor: ED | Labor: ED | Labor: ED
|  |  | (17.397k) | Labor: ET 3 PW (Simon Wood) | Labor: ET 3 PW (Simon Wood) | Labor: ET 3 PW (Simon Wood) | Labor: ET | Labor: ET 3PW (Simon Wood) | Labor: ET 3PW (Simon Wood) | Labor: ET 3PW (Simon Wood) | Total Labor = $17.397k
Total Labor = $29.668k
| Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS | Gun Group: gun at GTS
| Procurement: 160k$ total | Procurement: | Procurement: | Procurement: | Procurement: | Procurement: | Procurement: | Procurement: | Procurement: 60k$ total | Procurement: | Procurement:
|  |  |  | build keV beamline | build keV beamline | build keV beamline | build keV beamline | build keV beamline | build MeV beamline | build MeV beamline | build MeV beamline
|  | Magnet measurement | Magnet measurement |  |  | Magnet measurement | Magnet measurement | Magnet measurement
| 3.495k/WK | Labor: 2 PW (Joe Meyers) | Labor: 2 PW (Joe Meyers) | Total Labor = $27.96k |  | Labor: 2 PW (Joe Meyers) | Labor: 2 PW (Joe Meyers) | Labor: 2 PW (Joe Meyers) | Total Labor = $41.94k
|  | Labor: 2 PW (T. Hiatt) | Labor: 2 PW (T. Hiatt) |  |  | Labor: 2 PW (T. Hiatt) | Labor: 2 PW (T. Hiatt) | Labor: 2 PW (T. Hiatt)
| October | November | December | January | February | March | April | May | June | July | August
|  | Survey and Alignment | Survey and Alignment | Survey and Alignment | Survey and Alignment | Survey and Alignment | Survey and Alignment | Survey and Alignment | Survey and Alignment | Survey and Alignment | Survey and Alignment
|  | Network | Network | Network | SRF | SRF | keV beamline | keV beamline | MeV beamline | MeV beamline | MeV beamline
| (10.094k) | ME3: 2.8 PW | ME3: | ME3: | ME3: 1.6 PW | ME3: | ME3: 7.2 PW | ME3: | ME3: 3.2 PW | ME3: | ME3:
| (2.991k) | MT3: 1.5 PW | MT3: | MT3: | MT3: 0.7 PW | MT3: | MT3: 3.6 PW | MT3: | MT3: 1.6 PW | MT3: | MT3:
| Total Labor = $13.085k |  | they can distribute the weeks across months as warranted…. |  | Total Labor = 5.768 + 1.3958 |  | Total Labor = 25.956 + 7.1784k |  | Total Labor = 11.536 + 3.1904
[5 empty] | $7.1638k |  | $33.1344k |  | $14.7264k
| EHS&Q | EHS&Q | EHS&Q | EHS&Q | EHS&Q | EHS&Q | EHS&Q | EHS&Q | EHS&Q | EHS&Q | EHS&Q
| Safety related | Safety related | Safety related | Safety related | Safety related | Safety related | Safety related | Safety related | Safety related | Safety related | Safety related
| ODH assessment | ODH assessment | ODH assessment
NEPA catagorial exclusion
this color = facilities
this color = cryoinfrastructure
ITFCRY
this color = polarized target beamline
ITFPTB
this color is UITFBL

## total by "fence"
per Fence
FY16 budget request
| TOTALs (not by fence) |  |  | Facilites
| procurements | Labor |  | procurements | Labor | TOTAL cost Procurement + Labor
Facilities | 317 | 34 |  |  | 34 PW
0.77 FTE
Cryo | 118 | 192 |  | $317k | $103.035k | $420.035k
Installation Group | 25 | 21
Ops: network and software | 32.5 | 50 |  | Cryo
High Power RF | 40 | 22 |  | procurements | Labor (PW) | Labor ($) | TOTAL cost Procurement + Labor
|  |  | cryo | 68 | 111 | $224.83k
Low Level RF | 24 | 42 | high power rf | 40 | 22 | $55.35k
|  |  | odh | 2 | 9.5 | $23.2525k
SRF | 10 | 4 | survey | 0 | 2.1 | $7.1638k |  | 420.035
|  |  | srf | 10 | 4 | $17.65k |  | 448.25
SSG: ODH | 2 | 9.5 | TOTAL | 120 | 148.6 | 328.2463 | 448.2463 | 643.5578
[5 empty] | 3.4 FTE |  |  | 1117.6
SSG: PSS | 35 | 63 | [5 empty] | 2629.4428
Mech Design | 0 | 30
Pol Target Beamline
Magnet Measurement | 0 | 20
|  |  |  | procurements | Labor (PW) | Labor ($) | TOTAL cost Procurement + Labor
I&C | 160 | 49 | cryo | 50 | 81 | $162.592k
|  |  | mech design | 0 | 20 | $63.88k
DC Power | 80 | 22 | I&C | 60 | 21 | $46.356k
|  |  | DC power | 70 | 9 | $17.397k
Gun Group | 220 | 0 | mag meas | 0 | 12 | $41.94k
|  |  | gun group | 60 | 0 | 0
Survey and Alignment | 0 | 22 | survey | 0 | 4.8 | $14.7264k
|  |  | TOTAL | 240 | 147.8 | $403.5578k | $643.5578k
| 1063.5 | 580.5 |  |  | 3.4 FTE
13.2 FTEs
UITF
|  |  |  | procurements | Labor (PW) | Labor ($) | TOTAL cost Procurement + Labor
|  |  | install | 25 | 21 | $43.81k |  | 531.75 | what goes into UITFBL
|  |  | ops software | 32.5 | 50 | $145.769k
|  |  | low level rf | 24 | 42 | 102.352
|  |  | pss | 35 | 63 | $241.576k
|  |  | mech design | 0 | 10 | $31.94k
|  |  | I&C | 100 | 28 | $61.808k
|  |  | dc power | 10 | 13 | $29.668k
|  |  | mag meas | 0 | 8 | $27.96k
|  |  | gun group | 160 | 0 | 0
|  |  | survey | 0 | 15.1 | $46.2194k
|  |  | TOTAL | 386.5 | 250.1 | 731.1004 | 1117.6004
5.7 FTE
|  |  |  | 317 | 103
|  |  |  | 120 | 328.2463
|  |  |  | 240 | 403.6
|  |  |  | 386.5 | 731.1004
|  |  |  | 1063.5 | 1565.9467

## delta analysis
| Spent FY14 |  | Spent FY15 |  | Matt's FY16 estimate |  | Totals FY14+15 actuals + FY16 estimate
from "monthly schedule"
[5 empty] | tab#1 | [6 empty] | Matt's previous estimate for FY15 and 16
| Spent FY14 total 350k$ |  | Spent FY15 total 809k$ | [6 empty] | Hari's estimate |  | Numbers directly from service providers
remember to add FY14 for a TOTAL cost (350k$ was spent in FY14 total)
| procurements | Labor (PW) | procurements | Labor (PW) | procurements | Labor (PW) | procurements | Labor (PW) |  | procurement | Labor (PW) | procurement | Labor (PW)
Facilities | 4.2 | 0 | 46.4 | 9.8 | 317 | 34 | 367.6 | 43.8 |  | 298 | 65 | 300 | 28.2
[10 empty] | (+69.6) | (-21.2) | (+67.6) | (+15.6)
Cryo | 0 | 0 | 27.5 | 43.61 | 118 | 192 | 145.5 | 235.6 |  | 40 | 11.5 | 90.5 | 109 |  | My/our first estimate did not include controls or "heat exchanger"
[10 empty] | (+105.5) | (+224.1) | (+55) | (+126.6) |  | We still have not downselected the means to cool HDIce, these estimates include recovery line
Installation Group | 0 | 0.31 | 22.2 | 14.2 | 25 | 21 | 47.2 | 35.5 |  | 15 | 15 | 0 | 0
[10 empty] | (+32.2) | (+20.5) | (+47.2) | (+35.5)
Ops: network and software | 0 | 0 | 24.4 | 0 | 32.5 | 50 | 56.9 | 50 |  | 0 | 21 | 58 | 53.8
[10 empty] | (+56.9) | (+29) | (-1.1) | (+3.8)
High Power RF | 0 | 0 | 67 | 1.18 | 40 | 22 | 107 | 23.2 |  | 100 | 1.5 | 252.5 | 177.6
[10 empty] | (+7) | (+21.7) | (-78.5) | (-107)
Low Level RF | 0 | 1.39 | 43 | 3.96 | 24 | 42 | 67 | 47.4 |  | 25 | 6.5
[10 empty] | (+42) | (+40.9) |  |  |  |  | overbudget
SRF | 0 | 0.31 | 0 | 0.46 | 10 | 4 | 10 | 4.8 |  | 50 | 16 | 0 | 4 |  |  | underbudget
[10 empty] | (-40) | (-11.2) | (+10) | (+0.8)
SSG: ODH | 0 | 0 | 1 | 3.65 | 2 | 9.5 | 3 | 13.2 |  | 59 | 21 | 13 | 10.7
[10 empty] | (+8.1) | (+55.2) | (+2.9) | (+2.5)
SSG: PSS | 0 | 0 | 12.9 | 0 | 35 | 63 | 47.9 | 63 |  |  |  | 35 | 68.2
(+5.2)
Mech Design | 0 | 5.69 | 15.9 | 37.78 | 0 | 30 | 15.9 | 73.5 |  | 0 | 5.5 | 0 | 66
[10 empty] | (+15.9) | (+68) | (+15.9) | (+7.5)
Magnet Measurement | 0 | 0 | 0 | 2.45 | 0 | 20 | 0 | 22.4 |  | 0 | 0 | 0 | 0
[11 empty] | (+22.4) |  | (+22.4)
I&C | 0 | 0 | 15.2 | 1.59 | 160 | 49 | 175.2 | 50.6 |  | 126 | 12 | 219.5 | 96.8
[10 empty] | (+49.2) | (+38.6) | (-44.3) | (-46.2)
DC Power | 0 | 3.85 | 0 | 1.22 | 80 | 22 | 80 | 27.1 |  | 0 | 3 | 144.5 | 14.6
[10 empty] | (+80) | (+24.1) | (-64.5) | (+12.5)
Gun Group | 144.9 | 39.7 | 179.1 | 14.54 | 220 | 0 | 544 | 54.2 |  | 278 | 76 | 381.8 | 68
[10 empty] | (+266) | (-21.8) | (+162.2) | (-13.8)
Survey and Alignment | 0 | 0 | 2 | 1.83 | 0 | 22.2 | 2 | 24 |  | 0 | 13.5 | 0 | 22.2 |  | Matt's estimate = Chris' estimate
[7 empty] | 1669.2 | 768.3 |  | (+2) | (+10.5) | (+2) | (+1.8)
| 189.5 | 52.8 | 482.8 | 136.27 | 1063.5 | 580.5 | 1735.8 | 769.6 | HDIce | 45 | 0
|  | ($160.3k) |  | ($326.7k) |  | 13.2 FTEs | [5 empty] | 189.5 | 52.8 | from FY14
[10 empty] | 738 | 267.5
($1565.9k)
[12 empty] | 1684.3 | 771.9 | Total cost
| FY14 procurements |  | FY15 procurements
| HV insulator | 12.6 | HV insulators | 56.2
| HV power supply | 31.1 | HV cables | 16
| NEG and ion pumps | 20.2 | SF6 tank | 11.8
| and Y chamber |  | steering magnets | 19.4
| machine shop | 40.8 | quad magnets | 69.2
| solid works | 2.2 | girders | 6.8
| gun HV chamber | 7.8 | installation group | 22.2
| photocathode prep | 4.5 | SSG ODH | 1
| assorted | 3.9 | SSG PSS | 12.9
| credit card | 21.8 | cryo controls | 27.5
| ceiling penetrations | 4.2 | bpm parts | 15.2
| subtotal | 149.1 | water skid | 8.8
|  |  | TDK stuff (rf) | 5.5
| leaving 40.4k |  | LLRF boards | 34.2
| I can itemize this…. |  | waveguide stuff | 11.5
|  |  | klystron PS | 50
|  |  | network and video | 24.4
|  |  | Mech designer contractor | 15.9
|  |  | Facilities - | 15.4
|  |  | Facilities - concrete | 31
|  |  | subtotal | 454.9
leaving 27.9k assorted small things
I can itemize this…
Note on G15: Mathew Poelker: penetrations in ceiling
Note on I15: Mathew Poelker: concrete demo plus something for 15.4k from Shoreline Industries
Note on I17: Mathew Poelker: cryo controls
Note on K17: Mathew Poelker: there's some double counting for controls spent FY15, and it also includes some transfer line for HDIce, still somewhat ill defined (there was some pipe found on site)
Note on I21: Mathew Poelker: network switch, assorted other
Note on I23: Mathew Poelker: klystron PS and waveguide things
Note on K23: Mathew Poelker: waveguides and klystron control
Note on R23: Mathew Poelker: sum of ll and high powr rf
Note on I25: Mathew Poelker: water skid, plus parts for LLRF controls
Note on I29: Mathew Poelker: low because I probably included ODH procuments withing PSS category below
Note on J29: Mathew Poelker: all SSG stuff
Note on P29: Mathew Poelker: includes all SSG work, PSS, MPS and ODH
Note on J31: Mathew Poelker: captured in SSG:ODH
Note on I33: Mathew Poelker: Forrest Ellingsworth
Note on I37: Mathew Poelker: bpms stuff
Note on G41: Mathew Poelker: big items from CIS, see below for detail
Note on I41: Mathew Poelker: magnets, insulators, HV power supply, cables, girders
Note on R41: Mathew Poelker: now includes magnets, which I pulled out previously
Note on I43: Mathew Poelker: monuments, although I can't find PR in tally. 2k is my guess
Note on P45: Mathew Poelker: Hari spelled out HDIce as an "item"