## Sheet1
Week # | Week of | Components Due | AIPINJ Jobs | RSR Jobs | Groups | PSS | Sun | Mon | Tue | Wed | Thu | Fri | Sat
-4 | 2020-08-23 |  | BPM mapping #1, #2, #3 Survey Wien electrodes | Run CEBAF / HCO LERF
-3 | 2020-08-30 |  | Start assemble/align 2I components | bar: Mon
-2 | 2020-09-06 |  | Finish assemble/align 2I components | Run CEBAF / Run LERF |  | Mon: Lab Holiday
-1 | 2020-09-13 |  | Prep for Gun/2I jobs (hipot, bake equip)
1 | 2020-09-20 |  | HV test existing tee electrode and Wiens |  | Installation (crane) Ops (lock-ups) | PSS: 4 wks of INJ SEG
2 | 2020-09-27 |  | Replace electrode, rebuild 2I line |  | DC (remove magnets) I&C (remove BPM's) S&A (gun + 2I line)
3 | 2020-10-04 |  | Bake Gun2 and 2I line Assemble Y-chamber NEG | Repair FC1
4 | 2020-10-11 |  | HV test small shed electrode |  | Ops (lock-ups)
5 | 2020-10-18 |  | 1I-0I electronic & vacuum disconnects Laser outrigger table removal |  | DC, I&C, PSS (disconnects) Installation (girder removal) | PSS: 16 wks of no PSS (not counting break!)
6 | 2020-10-25 |  | 1I-0I removing components from tunnel | UHV repair may begin | Installation (girder removal)
7 | 2020-11-01 |  | Assemble Y-chamber in TL Disassemble/modify/clean Wiens Modify pedestals in tunnel ? |  | Machine shop (Wien) S&A/Install (new pedestals)
8 | 2020-11-08 |  | Install Y-chamber in tunnel Test magnetic assembly/map Wiens |  | S&A/Install (crane Y-chamber to tunnel, install, align)
9 | 2020-11-15 |  | Build/align A1/A2 in TL Test magnetic assembly/map Wiens
10 | 2020-11-22 |  | Build/align A1/A2 in TL Test electric assembly/HV Wiens
11 | 2020-11-29 |  | Build/align A1/A2 in TL Test electric assembly/HV Wiens" |  |  | Thu: Lab Holiday; Fri: Lab Holiday
12 | 2020-12-06 |  | Install A1/A2 in tunnel Build up Wien sub-assemblies
13 | 2020-12-13 |  | Bake A1/A2 in tunnel Build up Wien sub-assemblies
14 | 2020-12-20 |  | Float |  |  | Thu: Lab Holiday; Fri: Lab Holiday
15 | 2020-12-27 | [6 empty] | Shutdown Day | Shutdown Day | Shutdown Day | Lab Holiday | Lab Holiday
16 | 2020-01-03 | bar: PSS to Sun
17 | 2020-01-10 |  | Move or build Wiens girder in tunnel
18 | 2020-01-17 |  | Bake Y and Wien girder in tunnel
19 | 2020-01-24 |  | Reconnects of 2I/1I/0I regions
20 | 2020-01-31 |  | HCO of 2I/1I/0I regions | Add new Load chamber
21 | 2020-02-07 |  | HCO of 1I/0I regions
22 | 2020-02-14 |  | Float
23 | 2020-02-21 |  | Float
24 | 2020-02-28 |  | Commission Week #1 - Gun |  |  | PSS: 3 wks of INJ SEG BP Beam to FC#1
25 | 2020-03-07 |  | Commission Week #2 - Setup to chopper
26 | 2020-03-14 |  | Commission Week #3 - Setup to chopper
27 | 2020-03-28 |  | Commission Week #4 - Setup to FC2 |  |  | PSS: 3 wks of INJ/NL BP Beam to FC#2
28 | 2020-04-04 |  | Commission Week #5 - Wien/Spin
29 | 2020-04-11 |  | Commission Week #6 - Float
30 | 2020-04-18 |  | Float |  |  | PSS: 6 wks Float
31 | 2020-04-25 |  | Float
32 | 2020-05-02 |  | Float
33 | 2020-05-09 |  | Float
34 | 2020-05-16 |  | Float
35 | 2020-05-23 |  | Float
36 | 2020-05-30 |  | CEBAF HCO |  |  | PSS: Run CEBAF
37 | 2020-06-06 |  | CEBAF Restore
38 | 2020-06-13 |  | CEBAF Restore
39 | 2020-06-21 |  | CEBAF Physics starts