## Slide 1
Hall | Start | End | Pass | Current | Rep Rate | Polarization
A | Jun 17 | Aug 19 | 1 | 70uA | 499 MHz | Yes
B | Jun 17 | Aug 19 | 5 | “100nA” | 499 MHz | No
C | Jun 24 | July 14 | 3/4/5 | 90/90/50 uA | 499 MHz | No
D | OFF | OFF | OFF | OFF | OFF | OFF
Notables
Helicity Flip Rate – 240Hz or 120Hz (i.e. not usual 30 Hz)
Beam Polarization Reversal - Both Wien filters will be used first time since 2012
Summer 2019 Physics Program

## Slide 2
Week Of… | INJ SEG (FC1) | INJ/NL (FC2…) | Objective | Tasks
May 6 | SAD | SAD | Wrap up SAD | Leave Suitcase but clean up 4-lasers ON Finish Hall D laser work Complete Hot Checkout
May 13 | Yes ? | No | Gun Focus | Turn gun HV back ON Restore beam FC1 Study biased Anode
May 20 | Yes | Yes ? | PQB Focus | Heat/activate SLSP photocathode Rotate puck PQB study, finalize flipper preference?
May 27 | Yes | Yes | Injector Setup | Restore 3-beams to FC2..beyond? Interleave PQB studies
June 3 | Yes | Yes | Injector Finalization | Finalize Injector setup Finalize PQB setup Machine restoration begins
June 10 | Yes | Yes | Machine Restores | Machine restoration ABC
June 17 | Yes | Yes | Physics Starts | Run ABC
SAD to Physics transition

## Slide 3
Vwien=+90
Sol=-90
Sol=+90
Solenoid Flipping
Sol=-90
VWien=+90
VWien=-90
Wien Filter Flipping
Beam Reversal Options