## Slide 1: UITF – Upgrade Injector Test Facility
Deliverables/Milestones
    RF applied to cold ¼ CM by February 2016
    Beam on HDIce by August 2016 (nA current level at ~ 10 MeV)
Staffing
    Critical Skills needed NOW: Facilities, Cryo, Low level and high power RF, Ops Network Communications, Safety System Group for ODH, Installation Group
Update since last meeting
    Monthly meetings with Mont, on-going
    Stairway to top of Cave1: done
    Electronics racks above Cave1, electrical requirements well defined
    Procurement for electricity to Cave1 submitted, awaiting contractor site visit
    Control Room ready for terminals
    Cave2 perimeter under construction now
  ODH source terms more clearly defined, Mat Wright/Will Oren/Hari Areti working on the ODH assessment
  Progress on gun Plan Y, high voltage processing should begin next week
    Finished FY15 with ~ $81k carryover
    Presently “rationing” procurements and labor charges during CR

## Slide 2: UITF – Upgrade Injector Test Facility
To-do list for next 30 days, assuming UITF gets monthly CR allotment
  Select procurements for communications conduit, Cryo controls and transfer lines, odds and ends for Installation Group, RF stuff
  Facilities and Procurement Department: identify vendor for electric work, schedule the work
  Facilities: continue Cave2 structural design
  Cryo: Complete the design of the cryogenic plumbing, connecting ¼ CM to CTF, with a spigot to HDIce in case we need it, remove old transfer lines to facilitate construction of keV beamline
  Installation Group: bolt down racks, shield the penetrations, attach PSS conduit, hang cable trays
  Finish construction of rf control boards, progress on klystron rack
  Complete the ODH assessment (which could impact Cave2 structural design, passive exhaust vents in Cave1 and 2)
  Walter Kellner and company, finish erecting the perimeter of Cave2
  Apply high voltage to gun with shed electrode at LERF Gun Test Stand
  Make some headway on Bob May’s EHS&Q task list

## Slide 3: UITF – Upgrade Injector Test Facility
Issues/Concerns that could affect on-time delivery
  Consider near term milestone: RF applied to cold ¼ CM by February 2016
    Cryo Group and others, very busy, limited CR funding….
    No electricity until end of December, early January 2016
    Work on necessary subsystems delayed by at least one month….
  Consider global milestone: Beam on HDIce August 2016
    CTF 4K cold box work begins August 2016 and lasts through November 2016, CTF commissioning from November 2016 through February 2017
    Physics: limited funds to devote to necessary HDIce work that must precede installation at UITF
    Have we assigned a milestone that can’t be met?
  Total cost of UITF approaching a DOE MIE limit…
Recommended Mitigation
  Looking for guidance on how to push the project along…