## Sheet1
Color Codes for Boxes
| Name exists (I think) | Done, exists, ready to use
| New name | In process, good plan, not missing something
| This box means same location | Still in design phase, missing parts, undecided |  | Type | Element | Before | After | Comment
|  |  |  | Magnets | 15 deg bend dipole | 1 | 1 | New DR (remove old DS)
| Rev 6 |  |  |  | Solenoids | 5 | 5 | FH/FB/FQ => FX; and FGA/FGB remain
[5 empty] | Quads | 6 | 4 | New QW quad (retire old QW, remove QU)
REGION | NAME | STATUS |  |  | Correctors (H + V) | 24 | 26 | Additional pair on 2I line
0 | VIP2I01A | Exists in tunnel | x
| VIP2I01B | Exists in tunnel | x | Wien filters | Vacuum assemblies | 2 | 2 | vacuum chamber, HV feedthru, coils modified
| VIP2I01C | Exists in tunnel | x |  | Wien filter - magnet channels | 2 | 2 | Replace 10A trim with 20A rack mount PS
| ILL2I01DCANO | Ready to install | x |  | Wien filter - high voltage channels | 4 | 4 | Replace existing with Matsusada system
| VIP2I01 | Exists in tunnel | x
|  |  |  | RF | Prebuncher | 1 | 1 | New prebuncher
1 | MBH2I00H | Exists in tunnel | x |  | Brock cavity | 1 | 0 | Remove
| MBH2I00V | Exists in tunnel | x
| IPM2I00 | BPM #1 wire fixed, re-map | x | Current Monitoring | Polarized Source Faraday Cup | 1 | 1 | New location; still interlocked with a viewer
| MBH2I00AH | Exists in tunnel | x |  | A1 | 1 | 1 | Remote motorized aperture, new vac assembly
| MBH2I00AV | Exists in tunnel | x |  | A2 | 1 | 1 | Manual PSS stopper, new vac assembly
| IPM2I00A | BPM #2 mapped OK, re-map larger Y-direction | x
| MFX2I01 | Magnet mapped, pipe NEG coated | x | Diagnostics | Harps | 2 | 1 | Reduce by 1
| MBH2I01H | BH-H on-hand | x |  | BPM | 9 | 10 | 1 additional on 2I beam line
| MBH2I01V | BH-V on-hand | x |  | Viewers | 7 | 8 | 1 additional
| MBH2I01AH | Exists in tunnel | x
| MBH2I01AV | Exists in tunnel | x | Vacuum | Valves | 4 | 3 | Remove Gun3 valve, another viton=>all metal
| IPM2I01A | BPM #3 wire fiixed, re-map | x |  | Gun ion pump | 1 | 1 | No change
| VBV2I01A | Exists in tunnel | x |  | UHV beam line ion pumps | 8 | 10 | gang or add channel
2 | ITV2I01 | Garages tacked welded, Phil needs parts to rebuild | x | Safety | PSS kicker | 1 | 1 | New 200 kV kicker
| VRV1I01 | From tunnel or on-hand | x
| VIP1I01 | Exists in tunnel | x
| VGP1I01 | Build up new NEG's on Y-chamber flange | x
| MDR1I02 | 1st winding not met spec, Milhous re-winding now | x
| ITV1I02 | Garages tacked welded, Phil needs parts to rebuild | x
| VIP1I02 | Exists in tunnel | x
| VGP1I02 | New NEG on pump | x
| MBH1I02H | Exists in tunnel | x
| MBH1I02V | Exists in tunnel | x
| IPM1I02 | Exists in tunnel | x
| MFX1I03 | Mapping completed, ready for alignment | x
3 | MBH1I03H | Exists in tunnel | x
| MBH1I03V | Exists in tunnel | x
| IPM1I03 | Exists in tunnel | x
| MQW1I03 | Initial designs done, ~2 wks to complete/bid | x
| ITV1I03 | replace bellows, determine if we need new tophat/flag | x
| VIP1I03 | Exists in tunnel | x
| VGP1I03 | Add new capaciTorr | x
| MWF1I04 (vertical) | Test tunnel electrodes, design spares | MWF1I04 "Vertical"
| MQW1I04 | Initial designs done, ~2 wks to complete/bid | x
| ITV1I04 | replace bellows, determine if we need new tophat/flag | x
| VIP1I04 | Exists in tunnel | x
| VGP1I04 | Add new capaciTorr | x
| MBH1I04H | Exists in tunnel | x
| MBH1I04V | Exists in tunnel | x
| IPM1I04 | Exists in tunnel | x
| MFG1I04A | Exists in tunnel | x
| MFG1I04B | Exists in tunnel | x
| MBH1I05H | Exists in tunnel | x
| MBH1I05V | Exists in tunnel | x
| IPM1I05 | Exists in tunnel | x
| MQW1I05 | Initial designs done, ~2 wks to complete/bid | x
| ITV1I05 | replace bellows, determine if we need new tophat/flag | x
| VIP1I05 | Exists in tunnel | x
| VGP1I05 | Add new capaciTorr | x
| MWF1I06 (horizontal) | Test tunnel electrodes, design spares | MWF1I06 "Horizontal"
| MQW1I06 | Initial designs done, ~2 wks to complete/bid | x
| ITV1I06 | missing this viewer assembly, ordering chromox screen | x
| VIP1I06 | Exists in tunnel | x
| VRV1I06 | From tunnel or on-hand | x
| VGP1I06 | Add new capaciTorr | x
| RIN1I06 (pre-buncher) | >50% complete, iterating skim cuts, then braze | x
| MBH1I07H | Exists in tunnel | x
| MBH1I07V | Exists in tunnel | x
| IPM1I07 | Exists in tunnel | x
4 | VBV1I07 | Exists in tunnel | x
| VDP0I01 | Leave NEG intact | VDP0I00
| VIP0I01 | the ion pump from VDP1I05 needs to be cleaned | VIP0I00
| VRV0I01 | From tunnel or on-hand | VRV0I00
| MFX0I01 | ETI delivery on schedule, additional vee blocks ordered | x
| MBH0I01H | Exists in tunnel | x
| MBH0I01V | Exists in tunnel | x
| IPM0I01 | Exists in tunnel | x
| ITV0I01 | Garages tacked welded, Phil needs parts to rebuild | x
| IFY0I01 | Exists in tunnel | IFY0I01 "Pcup"
| VIP0I01A | Exists in tunnel | VIP0I01
| VGP0I01A | Add capictorr | VGP0I01
| IFY0IA1 | Cubes to shop for fiducials and tube weld | x
| VIP0I01B | Exists in tunnel | VIP0I01A
| MHD0I01AH | Coils ordered, assembly parts final design/order | MHD0I01AH
| MHD0I01AV | Coils ordered, assembly parts final design/order | MHD0I01AV
| MBH0I01BH | Exists in tunnel | MBH0I01BH
| MBH0I01BV | Exists in tunnel | MBH0I01BV
| IPM0I01B | Exists in tunnel | IPM0I01A
| SBK0I01 | Finish kicker design, bid and fabricate | x
| VBV0I02 | New gate value here | x
| ITV0I02 | Garages tacked welded, Phil needs parts to rebuild | x
| IHA0I02 | Exists in tunnel | x
| IFY0IA2 | Cubes to shop for fiducials and tube weld | x
| VIP0I02 | Exists in tunnel | x
| VRV0I02 | On-hand right angle valve | x
| VGP0I02 | Add NEG | x
| MHD0I02H | Coils ordered, assembly parts final design/order | x
| MHD0I02V | Coils ordered, assembly parts final design/order | x
MFA0I03