## Original Plan
2015-12-10
UITF – FACILITIES PACKAGES AND SCHEDULE, ORIGINAL PLAN (PER AWP)
| CALANDER YEARS |  |  |  |  | 2014 |  |  |  | 2015 | [51 empty] | 2016
| MONTHS |  |  |  |  | DEC |  |  |  | JAN | [5 empty] | FEB |  |  |  | MAR |  |  |  |  | APR |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN | [5 empty] | FEB |  |  |  | MAR |  |  |  |  | APR |  |  | MAY |  |  |  | JUN |  |  | REMARKS
| WEEKS |  |  |  |  | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Sl No. | Activity | Duration in Days | Stat Date | Finish Date | Group or Person Responsible
1 | Selective Demolition in Existing Injector Test Cave | [85 empty] | Package will include selective demolition of existing cave north wall and demolition of knee wall and masonry shielding wall. Demolition must be done during Christmas Holidays to cause low disruption to work in Test Lab.
| Design |  |  |  | Tom | bar: DEC 49 to JAN 5; JUL 30 to SEP 36; DEC 51 to JAN 1
| Procurement |  |  |  | Tom
| Contract Award |  |  |  | Tom
| Construction |  |  |  | Tom
2 | 35% Design
| Structural |  |  |  | Tom | bar: DEC 49 to DEC 52
| Mechanical |  |  |  | FMM | bar: JAN 6 to MAR 13
| Electrical |  |  |  | FME | bar: JAN 6 to MAR 13
| Fire Protection |  |  |  | FMFS | [81 empty] | Detailed Civil Design Depends on completion of this activity (Cave Layout) | bar: JAN 6 to MAR 13
| Cave Layout including Labyrinth |  |  |  | Matt Poelker/Tom | bar: JAN 6 to MAR 15
3 | Civil/Structural Work (Framing only) | [85 empty] | Package will include steel frame on east side, concrete frame on west side, precast beams and roof planks
| Design 100% |  |  |  | Tom | bar: JAN 1 to APR 17
| Procurement |  |  |  | Tom | bar: MAY 22 to JUL 28
| Contract Award |  |  |  | Tom | bar: JUL 29
| Construction |  |  |  | Tom | bar: SEP 39 to DEC 49
4 | Relocation of Existing Utilities | [85 empty] | Package will include relocation of existing electrical distribution panel and mechanical services located along the east side of the cave addition. Procurement and construction to be through existing BOA’s.
| Design |  |  |  | FME/FMM | bar: APR 18 to MAY 22
| Procurement |  |  |  | FME/FMM | bar: MAY 22 to JUN 26
| Contract Award |  |  |  | FME/FMM | bar: JUL 27
| Construction |  |  |  | FME/FMM | bar: JUL 30 to SEP 38
5 | Beam Pit |  |  |  |  | DEC 50: To Start In Christmas Break as
| Design |  |  |  | Tom/Matt Poelker | DEC 50: Total Electrical Shutdown will be | This can be completed only after finalization of the beam design.
| Procurement |  |  |  | Tom | DEC 50: required during cutting of slab
| Contract Award |  |  |  | Tom | [81 empty] | Construction of pit must start before Christmas Holidays as during demolition of floor concrete, the power will need to be shut down for the Test Lab. | bar: SEP 37
| Construction |  |  |  | Tom | bar: DEC 50 to FEB 7
6 | Mechanical, Electrical and Fire Protection Including Roof
| Design 100% |  |  |  | FME/FMM/FMFS | bar: MAY 22 to AUG 34
| Procurement |  |  |  | FME/FMM/FMFS | JAN 1: This can be done only after | This will need to done after installation of experimental equipment.
| Contract Award |  |  |  | FME/FMM/FMFS | JAN 1: Construction of Pit
| Construction |  |  |  | FME/FMM/FMFS | JAN 1: Construction of Pit
7 | Shielding
| Design |  |  |  | Tom | bar: MAY 22 to AUG 34; NOV 48 to MAY 21
| Procurement |  |  |  | Tom
| Contract Award |  |  |  | Tom | JAN 1: This needs to be done after most construction is over
| Construction |  |  |  | Tom
UITF – FACILITIES PACKAGES AND SCHEDULE, ALTERNATE PLAN
| CALANDER YEARS |  |  |  |  | DEC 49: 2014; JAN 1: 2015; JAN 1: 2016
| MONTHS |  |  |  |  | DEC 49: DEC; JAN 1: JAN; FEB 7: FEB; MAR 11: MAR; APR 16: APR; MAY 19: MAY; JUN 23: JUN; JUL 27: JUL; AUG 32: AUG; SEP 36: SEP; OCT 41: OCT; NOV 45: NOV; DEC 49: DEC; JAN 1: JAN; FEB 7: FEB; MAR 11: MAR; APR 16: APR; MAY 19: MAY; JUN 23: JUN | REMARKS
| WEEKS |  |  |  |  | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Sl No. | Activity | Duration in Days | Stat Date | Finish Date | Group or Person Responsible
1 | Selective Demolition in Existing Injector Test Cave | [85 empty] | Package will include selective demolition of existing cave north wall and demolition of knee wall and masonry shielding wall. Demolition must be coordinated with Test Lab operations. May consider delaying and do with Pit Work.
| Design |  |  |  | Tom | bar: JAN 1 to FEB 9
| Procurement |  |  |  | Tom | bar: FEB 10 to MAR 14
| Contract Award |  |  |  | Tom | bar: MAR 15
| Construction |  |  |  | Tom | bar: APR 16 to MAY 21
2 | Test Cave - Structure, Utilities, Roof
| Cave Layout including Labyrinth |  |  |  | Tom/Matt Poelker | bar: JAN 1 to JAN 5
| 35% Design |  |  |  | Facilities | bar: JAN 6 to MAR 11
| Design Review |  |  |  | Facilities | bar: MAR 12 to MAR 13
| 100% Design |  |  |  | Facilities | [81 empty] | Design will need to include method of access for pit work - material and equipment. | bar: MAR 14 to APR 17
| Procurement |  |  |  | Facilities | bar: MAY 20 to JUL 27
| Construction |  |  |  | Facilities | bar: JUL 28 to NOV 45
3 | Beam Pit
| Design |  |  |  | Tom/Matt Poelker | bar: APR 18 to JUL 29; SEP 37 to JAN 3
| Procurement |  |  |  | Tom
| Contract Award |  |  |  | Tom | DEC 50: To Start In Christmas Break as
| Construction |  |  |  | Tom | DEC 50: Total Electrical Shutdown will be
required during cutting of slab
Design
Procurement & Award
Construction