## "GROUP"
Summer SAD '15 Task List | "GROUP"
Task Description | ATLis # | Duration (weeks) | Tunnel Section | Tunnel State | System/Subsystem | Capability | Downtime (HRS) | Downtime (Frequency) | Procurement (part) | Procurement ($) | Groups involved (including home group)
Gun2 - Vacuum Diagnostics + Bakeout (No Venting) | 15144 (Grames) | 3 weeks | INJ SEG | Restricted Access | source/gun | reliability | 0 | 0 | 0 | 0 | CIS
Gun2 - Beam Lifetime Measurement | 15145 (Grames) | 1-2 days | INJ SEG | Beam Permit | source/gun | reliability | 0 | 0 | 0 | 0 | CIS, OPS
Brock Cavity - Tunnel Installation | TBD (Stutzman) | 2 weeks | INJ SEG | Restricted Access | source/diag | improve multi-hall ops | 0 | 0 | 0 | 0 | CIS, S&A, Software
Brock Cavity - Beam Commissioning | TBD (Poelker) | 2-3 shifts | INJ SEG/INJ NL | Beam Permit | source/diag | improve multi-hall ops | 0 | 0 | 0 | 0 | CIS, OPS
3-Laser System - Tunnel Work | TBD (Hansknecht) | May-July | INJ SEG | Restricted Access | source/laser | 250/500 Ops | ? | ? | TBD - ??? | TBD - ??? | CIS, RF-ENG, Software?
3-Laser System - Beam Measurement | TBD (Grames) | 3 shifts | INJ SEG | Beam Permit | source/laser | 250/500 Ops | ? | ? | 0 | 0 | CIS, OPS
Gun2 Photocathode Swap - Tunnel Vacuum Work | TBD (Grames) | 2-3 days | INJ SEG | Restricted Access | source/photocathode | improve polarization | 0 | 0 | 0 | 0 | CIS
Gun2 Photocathode Swap - DBR Mott/Lifetime Test | TBD (Stutzman, Zhang) | 2-3 shifts | INJ/NL | Beam Permit | source/photocathode | improve polarization | 0 | 0 | 0 | 0 | CIS, OPS
Bubble Chamber - Tunnel Installation | TBD (Suleiman) | 3-4 weeks | INJ SEG | Restricted Access | n/a | PAC exp't install | 0 | 0 | TBD - ??? | TBD -??? | CIS, Install, S&A, Software?
Bubble Chamber - Beam Engineering Run | TBD (Suleiman) | 2 weeks (12 hr/day) | INJ/NL | Beam Permit | n/a | PAC exp't eng run | 0 | 0 | 0 | 0 | CIS, Ops
Mott Run 2 | 15065 (Grames) | 1 weeks (24 hr/day) | INJ/NL | Beam Permit | injector/diag | 1% polarimetry | 0 | 0 | 0 | 0 | CIS, Ops
Note on D3: Randy Michaud: PSS Segments: INJ NL SL BSY Hall A Hall B Hall C Hall D Tagger Hall D
Note on E3: Randy Michaud: "Restricted Access" "Power Permit" "Beam Permit"
Note on G3: Randy Michaud: "Energy Reach" ex. He Processing "CEBAF Must" ex. PSS Certification "Reliability" ex. LCW Filter changes, downtime