## Schedule
Inj Commissioning and Restoration after SAD 2024
Prerequisites: HCO to ILD complete, simulated values of solenoids and warm RF ready for download, all lasers operable, on good QE spot, and colinear. Gun HV at 200kV. Reference ATLis: https://tasklists.jlab.org/atlis/tasks/111504
Week 1 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
Shift | Mon 18-Nov | Tues 19-Nov | Wed 20-Nov2 | Thurs 21-Nov2 | Fri 22-Nov | Sat 23-Nov | Sun 24-Nov
Day/Swing Shift | Completing HCO | Completeing HCO | Establish Tune Beam to FC1/1D (16hrs) | Establish Tune Beam to FC1/1D (16hrs) | Tune Beam to 1D (2hrs) | Beam studies to FC1 | Beam Studies to FC1
Set up Chopper (8hrs)
Swing/Owl |  |  |  |  | Possible beam studies to FC1
Week 2 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
Shift | Mon 25-Nov | Tues 26-Nov | Wed 27-Nov | Thurs 28-Nov | Fri 29-Nov | Sat 30-Nov | Sun 01-Dec
Day/Swing Shift | Set up prebuncher (4hrs) | Optimize set up to FC1/1D (8hrs) | Thread beam through Booster and FC2 (6hrs)
|  |  |  | Thanksgiving Holiday | Thanksgiving Holiday | Thanksgiving Holiday | Thanksgiving Holiday
| Set up buncher (4hrs) |  | Phase Booster and set Energy (4hrs)
Swing/Owl | Beam Studies to FC1 | Beam Studies to FC1 | Prep for thanksgiving shut down
hot stand by or complete shut down?
Week 3 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
Shift | Mon 02-Dec | Tues 03-Dec | Wed 04-Dec | Thurs 05-Dec | Fri 06-Dec | Sat 07-Dec | Sun 08-Dec
Day/Swing Shift | Check set up (2hrs) | Set Wien for Physics (8hrs) | Optimization from Gun to FC2 (8Hrs) | Optimization from Gun to FC2 (8Hrs) | Inj Match (8hrs) | Beam Studies to FC2 | Beam Studies to FC2
Calibrate Wien (8hrs) Riad/Max
|  |  | Beam to 4D dump (4hrs) | Beam to 4D dump (4hrs) | Who will perform the match?
Swing/Owl | Beam Studies FC1/FC2 | Beam Studies FC1/FC2 | Beam Studies FC1/FC2 | Beam Studies FC1/FC2 | Beam Studies FC1/FC2
Week 4 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
Shift | Mon 09-Dec | Tues 10-Dec | Wed 11-Dec | Thurs 12-Dec | Fri 13-Dec | Sat 14-Dec | Sun 15-Dec
Day/Swing Shift | High Current to ILD (4hrs) | Commissioning the Degrader (24hrs) | Commissioning the Degrader (24hrs) | Commissioning 5D line/Target irradiation | Commissioning 5D line/Target irradiation | Commissioning 5D line/Target irradiation | Prepare for Physics Beam
Bunch length Measurement (4hrs)
| Beam Studies FC1/FC2 | Beam Studies FC1/FC2 | Beam Studies FC1/FC2 | Beam Studies FC1/FC2 | Beam Studies FC1/FC2
Owl Shift
BSLists SAD 2024:
CASA/ Dennis Turner:
Characterize Wien Filter Optics: https://tasklists.jlab.org/bslist/tasks/107364
Degrader Commissioning with Beam: https://tasklists.jlab.org/bslist/tasks/111105