## Slide 1
What we started with…
UITF as imagined
Upgraded Injector Test Facility - UITF

## Slide 3
Charge Codes!
Facilities
ITFPTB
UITFBL
ITFCRY
  Facilities
Cryo Infrastructure including some RF
Polarized Target Beamline
UITF

## Slide 4
Cave 1 electric and network complete
NEXT: Clean off ledge and move IPC
Status Facilities

## Slide 5
Status Facilities
Precast concrete bids to arrive soon – this package includes bracing and means to secure 2nd layer

## Slide 6
Facilities (T. Renzo)

## Slide 7
Facilities Tasks and Timeline
February 2016
  Cave1 electrical work complete
  Facilities has issued PR for Cave2 concrete and bracing, out for bids
March
  Installation Group willing to secure Cave2 structure, install other utilities
April
  Facilities moves IPC outside Cave2
  Concrete for Cave2 arriving on site, installing it
  Physics installs 2nd layer of concrete, adds bracing
May
  Cave2 including labyrinth complete, roof not yet installed
June
  Facilities focus shifts to utilities inside Cave2: electricity, lights, fire suppression, gate
July
  Facilities continues to work on utilities inside Cave2: electricity, lights, fire suppression, gate
August
  Facilities completes utilities inside Cave2: electricity, lights, fire suppression, gate, entire Cave2 roof installed. All bracing complete
  Facilities provides power to big Bertha from diesel generator (this could happen later, since no Beam to HDIce until Jan 2017)

## Slide 8
Installed transfer line, leak checked OK
Purchased a turbo pump for leaky shield line
Building the heat exchanger
Controls getting worked
Status Cryo Group

## Slide 9
Met with Cryo, SRF, RF, and Kazimi of Ops
Discussing relief valves from ODH point of view
Who does what? e.g. Cryo makes u-tubes and SRF stabs them, Cryo pulls cables, SRF provides connectors
Expect 8 MeV beam with available klystrons
Status New ¼ CM
Test at CMTF June
Install at UITF July

## Slide 10
Cryo, SRF, RF and new 1/4 CM
Recall, we agreed on means to “park” the ¼ CM when not accelerating beam: circulate 80K LN2 through 35K shield line. UITF should not be a burden on CTF 34 wks per year
LN2 temp could fluctuate 80 to 100 K, no problem for parking but….
  How to cool HDIce? I think we are leaning toward CTF connection…
  Nagging ODH assessment is “nagging” because some issues were ill-defined: parking strategy and relief valves
New ¼ CM requires waveguide tuners
Chad Seaton building the high power rf control board
Next biggest issue: designing the waveguide layout

## Slide 11
Gun HV power supply installed inside SF6 tank, very little corona at 60 psi
Gun table and 80/20 keV beamline structure moved into place
NEXT: add gun HV chamber, install big beamline elements, buy stuff….
Status Gun Group
buncher
HV power supply
Barrel polished in 2 days

## Slide 12
Gun and Beamline at GTS

## Slide 13
Notes: Interior Page Design 2

## Slide 14
Yan Wang’s POISSON simulations validated by Fay Hannon using CST 3D field mapper
Status Gun Group
11 MV/m
8 MV/m

## Slide 15
The new gun happy at 325 kV, stopping at this voltage for now. Shifting focus to building the beamline and photocathode deposition chamber (LDRD magnetized beam tests)
Building the electron gun at LERF GTS

## Slide 16
Status Operations
Network switcher hardware installed
Computer terminals installed in control room
6100 IOCs ordered, but we can use older IOCs if needed sooner
Groups are installing hardware in racks, and conversations have started with Software (Scott Higgins our POC)

## Slide 17
Status Engineering
I&C building stripline bpm electronics
DC power prep-ing magnet racks, pulling cables
RF control boards in fab
RF group building second water skid
RF group building the klystron control panel
Safety System Group on track, ODH and PSS
Installation Group done with Cave1, can help with Cave2 when it makes sense

## Slide 18
Status Reviews
UITF Accelerator Review: where beamline design is reviewed by Ops/CASA/SRF, March 18, 2016
  Geoff Krafft, Mike Spata, Reza Kazimi, Arne Freyberger, Todd Satogata, Bob Rimmer
  Need to send out pre-review material soon: beamline design, optics envelope, machine protection
Safety Systems Review, May 2016
  Machine and Personnel, including radiation protection
  SCMB?
UITF Readiness Review, August 2016
  Commissioning and Operations plans
Experimental Readiness Review, December 2016
  Focused on HDIce
Documents: FSAD, mini-AOD, ESAD

## Slide 19
Status HDIce
Lots of scattering at MeV energy. Beam size very large at target. Decided to flip the orientation of the target
Cave2 design seems fine either way, need a Physics designer to be responsible for installation at UITF
Target here
Upstream radiation baffle blows up beam
In this configuration, we can achieve desired small beam size at target
Target here, better
e-beam
e-beam

## Slide 20
Status HDIce
Stripline BPMs see 7nA beam with 1 Hz integration time. But we want to see 1nA beam, or even less at UITF. Don’t want to fly blind

## Slide 21
Status HDIce
x 10 nA = 0.06 nA ; Ibaseline = 0.94nA
Need to work out details with HDIce and T. Allison, J. Musson
Ipeak
Ibaseline
Acceptable duration of high peak current: long enough to see but not long enough to depolarize

## Slide 22: Monthly Meeting with Mont
  Purpose: to inform Lab Leadership of the UITF status
  Action Items (from previous meetings)
Project Update
  Progress Update
  Milestones Update
  Budget Update
  Highlights & Concerns
  Next meeting agenda
Notes: RW=Roy Whitney

## Slide 23: Progress Update
  Major components
  Facilities
  Engineering
    Mech Design
    Installation
    Cryo
    Safety Systems
    I&C
    DC Power
    Low Level RF systems
    High Power RF
    Survey & Alignment
  SRF
    Build new ¼ CM
    Commission with RF
  Operations
    Network and communications
Green means we can see progress

## Slide 24: Progress Update
  Major components
  Source Group
    Reliable 350kV ops
    Beam to cup in front of ¼ CM
    Beam to cup in front of HDIce
  EHSQ
    Shielding approval, ODH assessment
    Global hazard review
    FSAD
    Accel Readiness Review
    Commissioning Plan
  HDIce
    Installation at Cave
    Beam on HDIce
Green means we can see progress