## Sheet1
Area | Job | JAN |  |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
|  | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26
CEBAF | Photocathode activation | bar: JAN 3
Run CEBAF | bar: JAN 3 to FEB 7
Mott BS (photocathode activation) | bar: JAN 10 to FEB 7
Booster BS (4 hours) | bar: JAN 10 to FEB 7
Install and test ML fiber laser | bar: FEB 7 to FEB 14
Characterize gun2 kick (<150 kV) | bar: FEB 7 to FEB 14
No PSS for lock-ups | bar: FEB 21 to APR 18
LLRF 3.0 upgrade (laser amps off) | bar: FEB 21 to APR 18
Harp/YAG/A2 (VBV0I02-VBV0I07) | bar: FEB 21 to APR 18
Mott ladder swap (C to Au) | bar: FEB 21 to APR 18
Install new 15 deg dipole | bar: FEB 21 to APR 18
Mitigate Wien PS noise | bar: FEB 21 to APR 18
Reconfigure Mott IP PS | bar: FEB 21 to APR 18
Investigate NM1830 readback bit | bar: FEB 21 to APR 18
Use harp to evaluate Wien quads | bar: APR 25 to MAY 16
Use harp to evaluate 15 deg dipole | bar: APR 25 to MAY 16
Restore CEBAF | bar: MAY 16 to MAY 30
Run CEBAF | bar: JUN 6 to DEC 19
Winter break | bar: DEC 26
UITF | UITF keV only program | bar: JAN 3 to MAY 30
UITF keV/MeV program | bar: JUN 6 to DEC 26
UITF cave open SAD | bar: JAN 31
200 kV : design/build | bar: JAN 3 to MAY 30
200 kV : install/bake | bar: JUN 6 to JUN 27
200 kV : hv/beam | bar: JUL 4 to DEC 26
Robust : lifetime Sb/Cs/O2 | bar: JAN 3 to JAN 17
Robust : DAQ install | bar: JAN 17 to JAN 31
Robust : U-Wien install | bar: FEB 7 to FEB 28
Robust : keV Mott install | bar: MAR 7 to MAR 28
Robust : keV beam studies | bar: APR 4 to MAY 30
Comtra : design, fab, build magnet | bar: JAN 3 to JUL 25
Comtra : design, fab, build detector | bar: JAN 3 to JUL 25
Comtra : design, fab, build DAQ | bar: JAN 3 to JUL 25
Comtra : design, fab, build radiator | bar: JAN 3 to MAR 28
Comtra : re-design MeV spec | bar: JAN 3 to APR 25
Comtra : fab MeV spec | bar: APR 4 to JUN 27
Comtra : install MeV spec | bar: JUN 6 to AUG 29
Comtra : commission window (1 wk) | bar: SEP 5 to OCT 31
Comtra : calibration window (1 wk) | bar: NOV 7 to DEC 26
KL - laser test develop window | bar: JAN 3 to MAY 30
KL - beam test window | bar: JUN 6 to DEC 26
AIPINJ - 200 kV kicker test window
GTS | GTS - POLMON | bar: JAN 3 to MAR 28
GTS - HVINS | bar: APR 4 to DEC 26