## Slide 1: Status of Upgraded Injector Test Facility (UITF)
Matt Poelker
Status of UITF and dependence on CTF LHe (charge #1, 7, 9)
UITF goals: CEBAF injector, QCM tests, HDIce
Status of RadCon assessment, ARR, ASE, other approvals
Status of beam hardware & software control
Modes/Staff for providing beam
HDIce @ UITF – Experimental Readiness Review
November 19, 2019

## Slide 2: UITF is a 10 MeV spin-polarized electron accelerator
the UITF accelerator is built, ready to use….

## Slide 3: keV beamline commissioned*, RF applied to cold “Booster”, no MeV beam yet
* we are presently restoring operation of the photogun, cathode electrode was moved to CEBAF during SAD

## Slide 4: Test the Booster before installing at CEBAF in 2020
Our new “booster”:
2 cell capture section + 7 cell cavity,
should provide 10 MeV beam and introduce no x/y coupling, allow better matching, more adiabatic damping
Increase gun voltage and Wien filters for 200 kV operation to suppress space-charge effects and improve parity quality beam
Locate Wien filters (energy filters) upstream of pre-buncher cavity and install quadrupoles to better compensate astigmatism
Increase aperture of chopper and beam line solenoids to suppress existing astigmatism and improve parity quality beam
Install new SRF booster that eliminates warm-rf capture cavity, RF deflection and x/y coupling

## Slide 5: Test the spin-polarized target “HDIce”

## Slide 6: Past Reviews of UITF
Review #1: UITF Operations Review, aka “will it work?” March 18, 2016
  https://wiki.jlab.org/ciswiki/index.php/UITF_Meeting_-_March_18,_2016
Review #2: UITF Safety Review, May 10, 2016
  https://wiki.jlab.org/ciswiki/index.php/UITF_Meeting_-_May_10,_2016
Review #2.5: PSS BCM review *, October 21, 2016
  https://wiki.jlab.org/ciswiki/index.php/UITF_Meeting_-_October_21,_2016
Review #3: Conduct of Operations Review, April 24, 2019
  https://wiki.jlab.org/ciswiki/index.php/UITF_Meeting_-_April_24,_2019
Shielding Design Package, June 2019, JLAB-TN-18-020
Accelerator Readiness Review: June 26-28, 2019
  https://www.jlab.org/indico/event/322/timetable/#20190626
* the PSS BCM, once deemed necessary now deemed optional, following detailed shielding assessment

## Slide 7: Official Documentation
https://wiki.jlab.org/ciswiki/index.php/UITF_Official_Documents
https://www.jlab.org/eshq/ProgramDocs
These documents were approved by Lab Leadership and TJSO

## Slide 8: CATS items

## Slide 9: Official Documentation
https://wiki.jlab.org/ciswiki/index.php/UITF_Safety_Documents

## Slide 10: Augmenting Cave2 Shielding
helium vent – used to maintain ODH0, ODH1 status

## Slide 11: Radiation Shielding Assessment and Commissioning Plan
https://wiki.jlab.org/ciswiki/index.php/UITF_Official_Documents
https://wiki.jlab.org/ciswiki/index.php/UITF_Safety_Documents
Shielding is adequate for 100 uA CW beam

## Slide 12
Table 1 of the UITF ARR Plan, presented to ARR Review Committee June 26-28, 2019

## Slide 13
Commissioning process “break points”, verify shielding is adequate
BLM locations (ILMM401, 601 and 701)
Good locations for spill tests:
proximity to control room and labyrinth

## Slide 14: UITF “schedule”
HDIce proposed run schedule
done
waiting for permission
Buncher commissioning December?
Booster commissioning January?
January, February, March, April, May?

## Slide 15: UITF “schedule”
Task | Comment
Restore 200 kV beam operation (photogun bakeout, HV conditioning, activate photocathode) | HV conditioning now
Commission the 200 kV buncher cavity | waiting for amp, Injector Group focused on CEBAF start up
Obtain permission from TJSO to commission the "waist-height" accelerator | EH&S approval, asked Andrei to ask Stuart to ask TJSO
Set a date for commissioning "waist-height" beamline (Run #0) | hard to do without having permission to commission
coordinate with Cryo and SRF, u-tube swap at CTF, booster cool down | 
Engineering gets two weeks notice for HCO | 
HDIce completes work inside enclosure: magnet, dump, halo counter installation | now through…..
administrative tasks: beam authorization, shift plans, coordinate control room staffing approved operators | 
Commission the Booster | estimate one week of beam, no access to the enclosure
Obtain permission to operate UITF accelerator to test HDIce, another round of signatures | Is this time consuming?
Set a date for commissioning the elevated beamline (Run #1) | 
installation work, HDIce specific controls and diagnostics | 
Engineering gets two weeks notice for HCO | 
accelerator checks: beam size, energy spread, stability | 
HDIce specific checks: ragowski coil BPM calibration, raster magnets, fsd functionality, current calibration | 
Remove Booster and install at CEBAF | May-20
Install CEBAF 1/4 CM | 

## Slide 16: CTF Schedule
Dec 2-9/19 ( 8 days = 4 d switch-overs + 4 d UITF OPS)
Jan 31-Feb 16/20 (17 days = 4 d switch-overs + 13 d UITF OPS)
Mar 7-16/20 (10 days = 4 d switch-overs + 6 d UITF OPS)
Apr 11-May 5/20 (25 days = 4 d switch-overs + 21 d UITF OPS)
CTF is broken now, CM20 moved to LERF for testing, no plans for CMTF tests through 2019

## Slide 17: Approved UITF Operators (underlined names)
Gun Group (Center for Injectors and Sources)
Scientists: J. Grames, C. Hernandez-Garcia, M. A. Mamun, M. Poelker, R. Suleiman, M. Stutzman and S. Zhang
Technical staff: P. Adderley, B. Bullard, (plus replacement for John Hansknecht)
Graduate Students: G. Palacios, S. Wijiethunga, J. Yoskovitz
Injector Group
Scientists: R. Kazimi, Y. Wang, A. Hofler

## Slide 18: UITF – Summary (slide presented at JLAAC and P&C Meeting)
Testing the “booster” and HDIce target remain high priority tasks, now with “deadline” May 2020
Project started 2014…..now the Accelerator is built with three MeV beam destinations, waiting for permission to commission
Conduct of Operations Review, Shielding Design Package, and Accelerator Readiness Review
UOD, ASE and updated FSAD
Commissioning Plan and a number of OSPs
While working towards MeV operations, we have been using UITF as a Gun Test Stand:
  Tested a number of cathode electrodes, and two gun designs
  Modified Wien filter to operate at +/-20kV per plate, for 200 keV beam
  Assisted visiting scholar Max Herbert, testing LiCsNF3:GaAs, does lithium prolong operating lifetime?
  Installed the non-invasive resonant polarimeter from sbir-partner Electrodynamic, beam tests soon
When booster leaves UITF for CEBAF May 2020, we will install a traditional ¼ CM, and then we need 350 kV photogun (this is an R&D project for us)
Held Workshop on Uses of UITF
Nb3Sn coated cavities inside ¼ CM, waste water treatment, fast kicking, bubble chamber astrophysics experiment, PEPPo….all these topics represent potential R&D for UITF

## Slide 19: UITF – Summary (~ slide presented at JLAAC and P&C Meeting)
Future challenges:
  The Gun and Injector Groups (nominally, the people we originally imagined operating UITF) need to focus on the CEBAF injector upgrade, scheduled to start May 2020, ~ five months from now
  After Booster commissioning, HDice needs a minimum of three (preferably four) two-week run periods BEFORE the Booster is removed in May of 2020
  Formality of DOE requirements….suggests fulltime Facility Manager and Operations staffing required
  Liquid helium: the CTF refrigerator at building 58 cannot provide sufficient LHe to operate Vertical Test Area, Cryomodule Test Facility and UITF simultaneously

## Slide 20
Back Up Slides