## Phased Approach
Phase A: Initial beam threading w/Wiens and RF elements off, HCO w/beam of elements, centering in elements, Gun@130kV
Phase B: Commissioning RF elements, optics measurements, Gun@130kV; Phase A prereq
Phase C: Element Setup for production, Gun@130kV; Phase A and B prereqs
Phase D: Initial beam threading, Gun@200kV
Phase E: Commissioning beamline elements, optics measurements, Gun@200kV; Phase D prereq

			From Kazimi PowerPoint in ATLis 22060
	Phase	POC	Test Plan / Activity	ATLis	Anticipated Duration	Prerequisite	Deliverable
	A	Kazimi	Initial Beam Threading - Threading	22060	13 shifts	Beam Authorization	tune-beam to PCup, FC1
	(in sequence)		1.1 Beam to PCup
				1.1.1 Correcting for gun Kick
				1.1.2 Setup 15deg bend
				1.1.6 Center on lenses and Wien pipe
			1.2 Beam to FC#1	1.2.1 Thread beam to FC#1
				1.2.3 Check beam on viewers
				1.2.4 Center on lenses, apertures
				1.1.5 + 1.2.4 Aperture check
				1.2.5 Check Transmission

	(in sequence)	Kazimi	Initial Beam Threading - HCO w/Beam	22060	? / 13 shifts	Tune to PCup / FC1	Verification of hardware functionality
			1.1 Beam To PCup
				1.1.3 Check magnets w/beam
				1.1.4 Check wien solenoids w/beam
			1.2 Beam to FC#1
				1.2.2 FOPT correctors checks
				~1.2.3 Check viewers, harps
				~tune-mode BPM Checkout

	(in sequence)	Kowal	PSS Kicker Test	22061	1/2 shift	Tune to FC1	PSS Certification for 130kV

	(before or after Wien checkout?)	Kazimi	RF Element Initial Setup / Checkout	22060	3 shifts	Tune to PCup/FC1	Initial setup at 130kV of RF elements
			2. RF Elements Setup
				2.1 Choppers
				2.3 4-Lasers
				2.2 Prebuncher
				~ Buncher
				~ Capture

	(before or after RF initial setup?)	Grames	130keV E/B Cal for H/V-WIens	22084	1/2 shift	Tune to FC1	polarity/convenction checkout, define operatng values, validate expectations

	(in sequence)	Kazimi	CW to FC#1 Setup	22060	2 shifts	Tune to FC1, w/beam HCO done	CW setup, Wiens On/Off, to FC#1 for 130kV
			5. CW to FC1	check transmission, vacuum
				5.1 Both Wiens Off
				5.2 Both Wiens On
				~ CW BPM checkout

	(in sequence)	Grames	HVPS v PCup Current Calibration	22080	1/8 shift	CW to PCup	Calibration of Gun current

	when makes sense in A	Grames	A1 Aperture Checkout	-	-	Beam to FC1 (tune? CW?)	Checkout remote controls of A1
	when makes sense in A	Grames	Beamline DecaRad Checkout	-	-	Beam to FC1 (tune? CW?)	Verify BL positioning for utility diagnosing loss

	end of Phase A
	Phase	POC	Test Plan / Activity	ATLis	Anticipated Duration	Prerequisite	Deliverable
	B - FC1 limited
	(in sequence)	Poelker	Wien ToF	-		Beam to FC1 (tune? CW?)	Measure ToF vs Wien angle setup, characterization of Wien filters

	(in sequence)	Turner	130keV qsUtility	21923	2 shifts	Tune to FC1, Wien checkout done	Test re/matching capability, model, tool, for various Wien configurations

	(in sequence)	Kazimi	Wien Optics @ 130keV	22060	3 shifts	Tune to FC1	Study effect of Wien on emittance, transmission, and beam phasing
			3. Major Elements Setup
			3.1 V-Wien (H-Wien Off)
				3.1.1 Emittance and transmission measurements, V-wien Off / On
				3.1.2 Check beam phase in choppers, V-wien Off / On
			3.2 H-Wien (V-Wien Off)
				3.2.1 Emittance and transmission measurements, H-wien Off / On
				3.2.2 Check beam phase in choppers, H-wien Off / On
			3.3 H and V Wien On / Off Together
			4.3 Measure Emittance w/ Wiens On/Off
				3.3.1 + 4.3 Emittance and transmission measurements, both off, both on
				3.3.2 Check beam phase in choppers, both off, both on

	when makes sense in B	Kazimi	INJ-I Optics Measurements	22060	4 shifts	Beam to FC1 (CW for bunchlength)
			4. Beam Measurements
				4.1 Bunchlength measurement in choppers, prebuncher On/Off			Prebuncher beam effect characterization
				4.2 Measure focal length of solenoids			Measurement to check/improve model

	when makes sense in B	Turner	MDR1I02 Optics vs Coil Fixture Rotation	22160	1 shift	Tune to FC1	Null optics effect from 15deg dipole
	when makes sense in B	Grames	Lifetime @ 130keV	22082	1 shift	CW To FC1	Quantify photocathode lifetime
	when makes sense in B/C	Palatchi	Cathode 45deg Rotation and Spot Move	22040	1 shift	CW to PCup	Establish birefrengence gradients on laser window
	when makes sense in B/C	Palatchi	130keV Sensitivity Test	22050	1/4 shift	CW to FC1	PQB Checkout, 130v200kV comparison

	B - FC2 limited
	(in sequence)	-	Initial Beam Threading to FC2	-	1 shift?	CW to FC1	Initial beam to FC2
		-	0L02 Setup	-	1 shift?	CW to FC1	Phased and ready for Beam Ops 0L02
		-	Centering in Elements FC1 -> FC2	-	2 shifts?	CW to FC1	Good transmission to FC2
		-	CW to FC2 Setup	-	1 shift?	Tune to FC2, centered	CW setup to FC2

	(in sequence)	Suleiman	Mott HCO w/Beam	22090	1/2 shift	CW to FC2, Mott	Mott polarimeter ready for spin measurements
		Grames	Test MFG Solenoid Hysterisis	22083	1/2 shift	CW to FC2, Mott	Determine appropriate cycling protocol for MFGs
		Suleiman	Spin Dance to Calibrate Spin Rotators	22091	3 shifts	CW to FC2, Mott	Calibrate Wien settings vs spin angle

	(in sequence, LAST in B)	Suleiman	Set 3D Spin Rotator	22092	2 shifts	CW to FC2, Mott	Determine settings for Flip-R/L, Vertical

	when makes sense in B/C	-	CW Setup Reproducibility	-	-	CW to FC2	Quantify ir / reproducibility of setup
	when makes sense in B/C	Moser	5MeV / 0L02 Match	-	1/2 shift	Tune to FC2	Matched beam to FC2
	when makes sense in B/C	Palatchi	Chopper Scan @ 130keV	22120	1/2 shift	CW to FC2	Bunchlength comparison, quantify poss diff from source, informal halo discussion for RTP

	end of Phase B
	Phase	POC	Test Plan / Activity	ATLis	Anticipated Duration	Prerequisite	Deliverable
	Phase C
	when makes sense in B/C	-	CW Setup Reproducibility	-	-	CW to FC2	Quantify ir / reproducibility of setup
	when makes sense in B/C	Palatchi	Cathode 45deg Rotation and Spot Move	22040	1 shift	CW to PCup	Establish birefrengence gradients on laser window
	when makes sense in B/C	Moser	5MeV / 0L02 Match	-	1/2 shift	Tune to FC2	Matched beam to FC2
	when makes sense in B/C	Palatchi	Chopper Scan @ 130keV	22120	1/2 shift	CW to FC2	Bunchlength comparison, quantify poss diff from source, informal halo discussion for RTP
	when makes sense in B/C	Palatchi	130keV Sensitivity Test	22050	1/4 shift	CW to FC1	PQB Checkout, 130v200kV comparison
	when makes sense in C	Turner	Multiwire Emittance Measurement w/Beam	19784	1/4 shift	Tune to ILD	New matching method/tool development

	end of Phase C
	Phase D
	(in sequence)	Kazimi	Initial Beam Threading, 200kV	22060	3 shifts	200kV Gun	tune beam to PCup, FC1 at 200kV
				Correcting for Gun Kick
				Setup 15deg bend
				Thread beam to FC1
				Check beam on viewers
				Aperture check
				Transmission check

	(in sequence)	Kowal	PSS Kicker Test	22061	1/2 shift	Tune to FC1	PSS Certification for 200kV

	(in sequence)	-	200keV Magnet Checkout?	-	-	Tune to FC1	Verification of magnet functionality at 200keV
	(in sequence)	-	200keV Diagnostics Checkout?	-	-	Tune to FC1	Verification of hardware functionality at 200keV

	(before or after RF initial setup?)	Grames	200keV E/B Cal for H/V-WIens	22084	1/2 shift	Tune to FC1	polarity/convenction checkout, define operatng values, validate expectations

	(before or after Wien checkout?)	Kazimi	Initial RF Setup, 200kV	22060	2 shifts	Tune to FC1	initial setup of RF elements @200keV
				Prebuncher
				Choppers
				~ Buncher?
				~ Capture?

	(in sequence)	Kazimi	CW to FC#1 Setup	22060	1 shift	Tune to FC1, w/beam HCO done	CW setup, Wiens On/Off, to FC#1 for 200kV
			5. CW to FC1	check transmission, vacuum
				Both Wiens Off
				Both Wiens On

	(in sequence)	Grames	HVPS v PCup Current Calibration	22080	1/8 shift	CW to PCup	Calibration of Gun current

	when makes sense in D	-	200keV Diagnostics CW Checkout?	-	-	CW to FC1	Verification of hardware functionality at 200keV

	end of Phase D
	Phase	POC	Test Plan / Activity	ATLis	Anticipated Duration	Prerequisite	Deliverable
	Phase E
	(in sequence)	Poelker	Wien ToF	-		Beam to FC1 (tune? CW?)	Measure ToF vs Wien angle setup, characterization of Wien filters

	(in sequence)	Turner	200keV qsUtility	22072	2 shifts	Tune to FC1, Wien checkout done	Test re/matching capability, model, tool, for various Wien configurations

	(in sequence)	Kazimi	Wien Optics @ 200keV	22060	2 shifts	Tune to FC1	Study effect of Wien on emittance, transmission, and beam phasing
			V-Wien (H-Wien Off) ?
				Emittance and transmission measurements, V-wien Off / On
				Check beam phase in choppers, V-wien Off / On
			H-Wien (V-Wien Off) ?
				Emittance and transmission measurements, H-wien Off / On
				Check beam phase in choppers, H-wien Off / On
			H and V Wien On / Off Together ?
				Emittance and transmission measurements, both off, both on
				Check beam phase in choppers, both off, both on

	(in sequence)	-	200keV CW Setup to FC2 ?	-	-	CW to FC1	CW setup to FC2 w/Gun@200kV

	when makes sense in E	-	200keV Bunchlength?	-	-	CW to FC1	Prebuncher beam effect characterization
	when makes sense in E	Grames	Lifetime @ 200keV	22082	1 shift	CW To FC1	Quantify photocathode lifetime
	when makes sense in E	Palatchi	200keV Sensitivity Test	22051	1/4 shift	CW to FC1	PQB Checkout, 130v200kV comparison
	when makes sense in E	Palatchi	Chopper Scan @ 200keV	22121	1/2 shift	CW to FC2 ?	Bunchlength comparison, quantify poss diff from source, informal halo discussion for RTP
	when makes sense in E	Palatchi	RTP pos diff feedback convergence FC2	22053	1 shift	CW to FC2 ?	Injector PQB check for MOLLER
	when makes sense in E	Palatchi	Transmission test gun 200kV	22052	1/4 shift	CW to FC2 ?	MOLLER gun transmission checkout
	when makes sense in E	Poelker	Transmission vs Gun HV	-	-	CW to FC1	Measure gun transmission vs Gun HV setting

## Grouped By Type
Test Plan Type	POC	Test Plan / Activity	ATLis #	Anticipated Duration	Beam Destination	Gun HV	Beam Mode	Phase
Initial Threading	Kazimi	Initial Beam Threading	22060	13 shifts	FC#1	130kV	Tune-Mode	A
	Kazimi	CW to FC#1 Setup	22060	2 shifts	FC#1	130kV	CW	A
	Kazimi	200kV Beam Threading	22060	3 shifts	FC#1	200kV	Tune-Mode	D
	Kazimi	200kV CW Setup	22060	1 shift	FC#1	200kV	CW	D

w/Beam HCO	Kazimi	Initial Beam Threading (checkouts)	22060	? / 13 shifts	FC#1	130kV	Tune-Mode	A
	Kowal	PSS Kicker Test @ 130/200keV	22061	1/2 shift each	FC#1	130/200kV	Tune-Mode	A/D
	Kazimi	RF Element Setup	22060	3 shifts	FC#1	130kV	Tune-Mode	A
	Grames	130/200keV HVPS vs Pcup Current Cal	22080	1/8 shift each	PCup	130/200kV	CW	A/D
	Suleiman	Mott HCO w/Beam	22090	1/2 shift	FC#2 / Mott	130kV	CW	B
	Kazimi	RF Element Setup @200kV	22060	2 shifts	FC#1	200kV	Tune-Mode	D
	Grames	A1 Remote Controls Checkout			FC#1	130kV		A
	Grames	Beamline DecaRAD Checkout			FC#1	130kV		A

Wien/Spin	Grames	130/200keV E/B Cal for H/V-WIens	22084	1/2 shift each	FC#1	130/200kV	Tune-Mode	A/D
	Poelker	Wien ToF @ 130/200keV			FC#1	130/200kV	Tune-Mode	B/E
	Suleiman	Spin Dance to Calibrate Spin Rotators	22091	3 shifts	FC#2 / Mott	130kV	CW	B
	Suleiman	Set 3D Spin Rotators	22092	2 shifts	FC#2 / Mott	130kV	CW	B
	Grames	Test MFG Solenoid Hysterisis	22083	1/2 shift	FC#2 / Mott	130kV	CW	B
	Kazimi	Wien Optics @ 130kV	22060	3 shifts	FC#1	130kV	Tune-Mode	B
	Kazimi	Wien Optics @ 200kV	22060	2 shifts	FC#1	200kV	Tune-Mode	E

Optics/RF	Kazimi	INJ-I Optics Measurements	22060	4 shifts	FC#1	130kV	Tune-Mode	B
	Turner	130/200keV QsUtility	21923/22072	2 shifts each	FC#1	130/200kV	Tune-Mode	B/D
	Turner	MDR1I02 Optics vs Coil Fixture Rotation	22160	1 shift	FC#1	130kV	Tune-Mode	B
	Turner	Multiwire Emittance Measurement w/Beam	19784	1/4 shift	ILD	130kV	Tune-Mode	C

Laser/Gun	Grames	Lifetime @ 130/200keV	22082	1 shift each	FC#1	130/200kV	CW	B/E
	Poelker	Transmission vs Gun Voltage			FC#1	up to 200kV		B/E

Parity	Palatchi	Cathode 45deg Rotation and Spot Moves	22040	1 shift	PCup	130kV	CW	B/C?
	Palatchi	130/200keV Sensitivity Tests	2205{0,1}	1/4 shift each	FC#1	130/200kV	CW	B/E
	Palatchi	Chopper Scan at 130/200keV	2212{0,1}	1/2 shift each	FC#2	130/200kV	CW	B/E
	Palatchi	RTP pos diff feedback convergence FC2 test	22053	1 shift	FC#2	200kV	CW	E
	Palatchi	Transmission test gun 200kV	22052	1/4 shift	FC#2	200kV	CW	E

## March31st ATLiss
Updated 3/31
	POC	Test Plan/Activity	ATLis #	Anticipated Duration	PSS Required	Beam Destination	Gun HV	Prerequisites	Notes
	Injector Locked Up, No Beam
	Hernandez-Garcia	Gun HV Processing	21911	10 shifts	Inj PP	-	200kV +	gun interlocks, Inj PSS	~March/April, not making e-beam
	Injector Only, 130kV Gun
	Kazimi	Initial Beam Threading	22060	13 shifts	Inj BP	FC#1	130kV	Inj PSS, Inj HCO complete
	Kazimi	RF Element Setup	22060	3 shifts	Inj BP	FC#1	130kV	Inj PSS, Inj HCO complete
	Kazimi	Wien Setup	22060	3 shifts	Inj BP	FC#1	130kV	Inj PSS, Inj HCO complete
	Kazimi	INJ-I Optics Measurements	22060	4 shifts	Inj BP	FC#1	130kV	Inj PSS, Inj HCO complete
	Kazimi	CW to FC#1 Setup	22060	2 shifts	Inj BP	FC#1	130kV	Inj PSS, Inj HCO complete
	Grames	130keV HVPS vs Pcup Current Cal	22080	1/8 shift	Inj BP	PCup	130kV	Clean / clear aperture CW setup to PCup	up to 200uA
	Grames	Lifetime @ 130keV	22082	2 shifts	Inj BP	PCup	130kV	High Current and transmission CW Setup to FC#1	1mA CW setup
	Turner	130keV QsUtility	21923	2 shifts	Inj BP	FC#1	130kV	Setup to FC#1 for multiple Wien configs	8 Wien configs in total
	Poelker	Wien ToF @ 130keV	?	1/2 shift	Inj BP	FC#1	130kV
	Palatchi	Cathode 45deg Rotation and Spot Moves	22040	1 shift	Inj BP	PCup	130kV	CW Setup to PCup	15 - 22uA CW
	Palatchi	130keV Sensitivity Test	22050	1/4 shift	Inj BP	FC#1	130kV	CW setup to FC#1	up to 22uA CW
	Grames	130keV E/B Cal for H/V-WIens	22084	1/2 shift	Inj BP	FC#1	130kV	tune-mode up to 10uA to FC#1	Satisfies w/beam HCO of Wiens
	Turner	MDR1I02 Optics vs Coil Fixture Rotation	22160	1 shift	Inj BP	FC#1	130kV	Tune-mode setup to FC#1
	Grames	A1 Aperture Checkout	?	?	Inj BP	FC#1	130kV	Tune-mode setup to FC#1 ?
	Grames	Beamline DecaRad Placement HCO	?	?	Inj BP	FC#1	130kV	Tune or CW? To FC1
	Injector and NL, 130kV Gun
	Suleiman	Mott HCO w/Beam	22090	1/2 shift	Inj + NL BP	FC#2 / Mott	130kV	CW beam setup to FC#2
	Suleiman	Spin Dance to Calibrated Spin Rotators	22091	3 shifts	Inj + NL BP	FC#2 / Mott	130kV	CW beam setup to FC#2
	Suleiman	Set 3D Spin Rotators	22092	2 shifts	Inj + NL BP	FC#2 / Mott	130kV	CW beam setup to FC#2	up to 30uA
	Grames	Test MFG Solenoid Hysterisis	22083	1/2 shift	Inj + NL BP	FC#2 / Mott	130kV	CW beam setup to FC#2
	Palatchi	Chopper Scan 130keV	22120	1/2 shift	Inj + NL BP	FC#2	130kV	CW beam setup to FC#2	up to 75uA CW
	Turner	Multiwire Emittance Measurement w/Beam	19784	1/4 shift	Inj + NL BP	ILD	130kV	Tune mode to ILD, reasonably matched	emittance meas. w mulitple harps
	Injector Only, 200kV Gun
	Grames	Lifetime @ 200keV	22082	2 shifts	Inj BP	FC#1	200kV	High Current and transmission CW Setup to FC#1	1mA CW setup
	Grames	200keV HVPS vs Pcup Current Cal	22080	1/8 shift	Inj BP	PCup	200kV	Clean / clear aperture CW setup to PCup	up to 200uA
	Poelker	Wien ToF @ 200keV	?	1/2 shift	Inj BP	FC#1	200kV
	Grames	200keV E/B Cal for H/V-WIens	22084	1/2 shift	Inj BP	FC#1	200kV	tune-mode up to 10uA to FC#1	Satisfies w/beam HCO of Wiens
	Kazimi	200keV Beam Threading	22060	3 shifts	Inj BP	FC#1	200kV	Inj PSS, Inj HCO complete
	Kazimi	200keV RF Setup	22060	2 shifts	Inj BP	FC#1	200kV	Inj PSS, Inj HCO complete
	Kazimi	200keV Wien Setup	22060	2 shifts	Inj BP	FC#1	200kV	Inj PSS, Inj HCO complete
	Palatchi	200keV Sensitivity Test	22051	1/4 shift	Inj BP	FC#1	200kV	CW setup to FC#1	up to 22uA CW
	Poelker	Transmission vs Gun Voltage	?	?	Inj BP	FC#1	70 - 200kV?	Clean CW setup to FC#1 at various gun voltages	Several different gun voltage setups
	Kowal	PSS Kicker Tests @200kV	22061	1/2 shift	Inj BP	FC#1	200kV	Tune-mode setup to FC#1
	Turner	200keV qsUtility	22072	2 shifts	Inj BP	FC#1	200kV	Setup to FC#1 for multiple Wien configs	8 Wien configs in total
	Injector and NL, 200kV Gun
	Palatchi	RTP Pos Diff Fdbk Convergence FC#2 Test	22053	1 shift	Inj+NL BP	FC#2	200kV	CW setup to FC#2	up to 80uA CW
	Palatchi	Transmission test gun 200keV	22052	1/4 shift	Inj+NL BP	FC#2	200kV	CW setup to FC#2	up to 100uA CW
	Palatchi	Chopper Scan 200keV	22121	1/2 shift	Inj+NL BP	FC#2	200kV	CW setup to FC#2	up to 75uA CW

	POC	Test Plan/Activity	ATLis #	Anticipated Duration
	Injector Locked Up, No Beam
	Hernandez-Garcia	Gun HV Processing	21911	10 shifts
	Injector Only, 130kV Gun
	Kazimi	Initial Beam Threading	22060	13 shifts
	Kazimi	RF Element Setup	22060	3 shifts
	Kazimi	Wien Setup	22060	3 shifts
	Kazimi	INJ-I Optics Measurements	22060	4 shifts
	Kazimi	CW to FC#1 Setup	22060	2 shifts
	Grames	130keV HVPS vs Pcup Current Cal	22080	1/8 shift
	Grames	Lifetime @ 130keV	22082	2 shifts
	Turner	130keV QsUtility	21923	2 shifts
	Poelker	Wien ToF @ 130keV	?	1/2 shift
	Palatchi	Cathode 45deg Rotation and Spot Moves	22040	1 shift
	Palatchi	130keV Sensitivity Test	22050	1/4 shift
	Grames	130keV E/B Cal for H/V-WIens	22084	1/2 shift
	Kowal	PSS Kicker Tests @130kV	22061	1/2 shift
	Turner	MDR1I02 Optics vs Coil Fixture Rotation	22160	1 shift
	Injector and NL, 130kV Gun
	Suleiman	Mott HCO w/Beam	22090	1/2 shift
	Suleiman	Spin Dance to Calibrated Spin Rotators	22091	3 shifts
	Suleiman	Set 3D Spin Rotators	22092	2 shifts
	Grames	Test MFG Solenoid Hysterisis	22083	1/2 shift
	Palatchi	Chopper Scan 130keV	22120	1/2 shift
	Turner	Multiwire Emittance Measurement w/Beam	19784	1/4 shift
	Grames	A1 Aperture Checkout	?	?
	Grames	Beamline DecaRad Placement HCO	?	?

	POC	Test Plan/Activity	ATLis #	Anticipated Duration
	Injector Only, 200kV Gun
	Grames	Lifetime @ 200keV	22082	2 shifts
	Grames	200keV HVPS vs Pcup Current Cal	22080	1/8 shift
	Poelker	Wien ToF @ 200keV	?	1/2 shift
	Grames	200keV E/B Cal for H/V-WIens	22084	1/2 shift
	Kazimi	200keV Beam Threading	22060	3 shifts
	Kazimi	200keV RF Setup	22060	2 shifts
	Kazimi	200keV Wien Setup	22060	2 shifts
	Palatchi	200keV Sensitivity Test	22051	1/4 shift
	Poelker	Transmission vs Gun Voltage	?	?
	Kowal	PSS Kicker Tests @200kV	22061	1/2 shift
	Turner	200keV qsUtility	22072	2 shifts
	Injector and NL, 200kV Gun
	Palatchi	RTP Pos Diff Fdbk Convergence FC#2 Test	22053	1 shift
	Palatchi	Transmission test gun 200keV	22052	1/4 shift
	Palatchi	Chopper Scan 200keV	22121	1/2 shift