## Schedule
Inj Commissioning and Restoration after SAD 2024
Reference ATLis: https://tasklists.jlab.org/atlis/tasks/111504
| Week 1 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 13-Jan | Tues 14-Jan | Wed 15-Jan | Thurs 16-Jan | Fri 17-Jan | Sat 18-Jan | Sun 19-Jan
| Day/Swing Shift | HCO to FC2 | HCO to FC2 | 0L03 He Processing | 0L03 He Processing | 0L03 He Processing | 0L03 He Processing? | 0L03 He Processing?
[7 empty] | Mott DAQ Check | Spin Rotator test at 200keV
Wien angle = -88.2°
[7 empty] | Calibrate Wien (8hrs) Riad/Max | Vwien = 44.1°, flip left
| Swing |  |  | Tune beam to 1D/FC2 | Tune beam to 1D/FC2 | Tune beam to 1D/FC2 |  | Hwien = -44.1°
[5 empty] | Set up Chopper (8hrs) | Phase Booster and set Booster Energy (4hrs)
Set up prebuncher (4hrs)
| Owl |  |  |  | Set up buncher phase | Ops Inj Setup Procedures? | Ops Inj Setup Procedures? | Ops Inj Setup Procedures?
Ops Inj Setup Procedures?
| Week 2 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 20-Jan | Tues 21-Jan | Wed 22-Jan | Thurs 23-Jan | Fri 24-Jan | Sat 25-Jan | Sun 26-Jan
| Day/Swing | HCO to ILD | HCO to ILD | HCO to ILD | HCO to ILD | Complete HCO to ILD?
|  | 0L03 He Processing | 0L03 He Processing | 0L03 He Processing | 0L03 He Processing? | 0L03 He Processing? | Optimize beam to ILD | Optimize beam to ILD
| Swing/Owl | Optimize beam to FC2 | Optimize beam to FC2 | Optimize beam to FC2 | Optimize beam to FC2 | Beam to ILD? | Beam Studies to FC1/FC2/ILD | Beam Studies to FC1/FC2/ILD
|  |  | Set Wien for Physics | Set Wien for Physics
| Owl | Beam Studies to FC1/FC2 | Beam Studies to FC1/FC2 | Beam Studies to FC1/FC2 | Beam Studies to FC1/FC2 | Beam Studies to FC1/FC2 | Beam Studies to FC1/FC2/ILD | Beam Studies to FC1/FC2/ILD
| Week 3 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 27-Jan | Tues 28-Jan | Wed 29-Jan | Thurs 30-Jan | Fri 31-Jan | Sat 01-Feb | Sun 02-Feb
| Day | Optimize beam to ILD | Optimize beam to ILD | Optimize beam to ILD | Optimize beam to ILD | Optimize beam to ILD | PQB Studies? | PQB Studies?
|  | Steer to 4D | Steer to 4D | Steer to 4D | Inj Match/CASA
|  | Phase 0L03/0L04 | Phase 0L03/0L04
|  | Set Inj Energy | Set Inj Energy | Inj Match/CASA | Check Transmission for high current | Check Transmission for high current
| Swing | Beam Studies to FC1/FC2/ILD | Beam Studies to FC1/FC2/ILD | Beam Studies to FC1/FC2/ILD | Beam Studies to FC1/FC2/ILD | Beam studies up to ILD | Beam studies up to ILD | Beam studies up to ILD
| Owl | Beam Studies to FC1/FC2/ILD | Beam Studies to FC1/FC2/ILD | Beam Studies to FC1/FC2/ILD | Beam studies up to ILD | Beam studies up to ILD | Beam studies up to ILD | Beam studies up to ILD
Note: Spin Rotator test at 200keV: Yan and Max: https://tasklists.jlab.org/bslist/tasks/114355
Max: Mott DAQ Checkout with Beam: https://tasklists.jlab.org/bslist/tasks/114409
| Week 4 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 03-Feb | Tues 04-Feb | Wed 05-Feb | Thurs 06-Feb | Fri 07-Feb | Sat 08-Feb | Sun 09-Feb
| Day/Swing Shift |  | Hand over to ops?
Turn over to Ops?
Else continue Beam studies
PQB Studies?
| Swing | Beam studies up to ILD
Owl
| Week 5 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 10-Feb | Tues 11-Feb | Wed 12-Feb | Thurs 13-Feb | Fri 14-Feb | Sat 15-Feb | Sun 16-Feb
| Day/Swing Shift |  | Beam studies up to ILD | Beam studies up to ILD | Beam studies up to ILD | Beam studies up to ILD
| Swing |  | Beam studies up to ILD | Beam studies up to ILD
| Owl |  | Beam studies up to ILD | Beam studies up to ILD | Beam studies up to ILD | Beam studies up to ILD
| Week 6 | DATE | DATE | DATE | DATE | DATE | WEEKEND | WEEKEND
| Shift | Mon 17-Feb | Tues 18-Feb | Wed 19-Feb | Thurs 20-Feb | Fri 21-Feb | Sat 22-Feb | Sun 23-Feb
Day
Swing
Owl