## Slide 1: GTS updates week of October 21, 2024
High Voltage chamber ready for ops
High voltage processing using Xe for the first time.
  No clear evidence Xe did much for processing field emitter.
Gun electrode conditioned to 230 kV with polished stainless steel puck.
Field emission free to 230 kV.
Conditioning resistor shorted out
Gun ready for beam ops at 200 kV
Photocathode in HV chamber being evaluated for QE
Cs3Sb photocathode reinstalled in gun electrode
Photocathode ready for testing photocurrent measurement using eye-safe class 3R laser, and battery box with new cable borrowed from LERF gun. This will tell us if the cathode has QE left, and if the system can read photocurrent.
Still to resolve: QE scanning mirrors electronics.
Keithely 6487 with voltage source is now in GTS. Interlock and connector box ready. Carlos will coordinate getting Keithely readback in EPICS for QE scans using QE Tool.

## Slide 2: GTS plans week of October 28, 2024
Prep chamber vacuum work
Prep the Cs feed, remove effusion cells, pucks, top heater, blank off the chamber, pull vacuum, leak check, assist Shukui if laser work is performed
HVPS SF6 tank: Relief valve must be replaced to address CATS item.
Pressure system design authority has been assigned
Developing job scope and schedule for decommissioning in-house SF6 recovery system
New relief valve will be installed directly to the HVPS SF6 tank
Preparations for beam
DC power expect to turn on magnet rack and HCO on Nov 1st.
Shukui will tell us an estimate on when the drive laser can be functional and aligned
Max will tell us his plans for beam between now and Nov. 30th.
GTS beam/HV ops stop Nov 30th for Accelerator Readiness Review