## Calendar
| SUN | MON | TUE | WED | THU | FRI | SAT
AUG | 9 | 10 | 11 | 12 | 13 | 14 | 15 | SCHEDULED
OWL
DAY |  | RA/Bubble | RA/Bubble | RA/Bubble |  |  |  | AVAILABLE
SWI |  | IN/Bubble | IN/Bubble | IN/Bubble | IN/Bubble | IN/Mott 5756-4 | IN/Bubble
AUG | 16 | 17 | 18 | 19 | 20 | 21 | 22 | UNAVAILABLE
OWL
DAY
SWI |  | IN/GPT | IN/GPT | IN/GPT | IN/GPT | IN/GPT
AUG | 23 | 24 | 25 | 26 | 27 | 28 | 29
OWL
DAY
SWI |  | IN/GPT | IN/GPT | IN/GPT | IN/GPT | IN/GPT
AUG-SEP | 30 | 31 | 1 | 2 | 3 | 4 | 5
OWL
DAY
SWI
SEP | 6 | 7 | 8 | 9 | 10 | 11 | 12
OWL |  | Holiday
DAY |  | Holiday
SWI |  | Holiday
SEP | 13 | 14 | 15 | 16 | 17 | 18 | 19
OWL
DAY |  | IN/Bubble | IN/Bubble | IN/Bubble | IN/Bubble | IN/Bubble
SWI |  | IN/Bubble | IN/Bubble | IN/Bubble | IN/Bubble | IN/Bubble
SEP | 20 | 21 | 22 | 23 | 24 | 25 | 26
OWL
DAY |  | CRYO | CRYO | CRYO | CRYO | CRYO | CRYO
SWI |  | PSS | PSS | PSS | PSS | PSS | PSS
SEP-OCT | 27 | 28 | 29 | 30 | 1 | 2 | 3
OWL
DAY | CRYO | CRYO | CRYO | CRYO | CRYO | CRYO | CRYO
SWI | PSS | PSS | PSS | PSS | PSS | PSS
OCT | 4 | 5 | 6 | 7 | 8 | 9 | 10
OWL
DAY |  | HCO/CRYO | … | … | … | …
SWI
OCT | 11 | 12 | 13 | 14 | 15 | 16 | 17
OWL
DAY |  | HCO/CRYO | … | … | … | …
SWI
OCT | 18 | 19 | 20 | 21 | 22 | 23 | 24
OWL
DAY |  | HCO/CRYO | … | … | … | …
SWI
OCT-NOV | 25 | 26 | 27 | 28 | 29 | 30 | 1
OWL
DAY |  | RESTORE | RESTORE | RESTORE | RESTORE | RESTORE
SWI

## Tasks
ATLIS | Task | Contact | RA | INJSEG | INJ/NL | Term | Energy | Current | # shifts | Shift | Accesses | When?
| Bubble commissioning | Riad |  |  | x | FC2 | Up to max | 10 uA cw | 5 | SWING | maybe | 8/10-8/15
| Test SLSP-5756-4 | Joe/Riad |  |  | x | FC2 | 5 MeV | 2 uA cw | 1 | SWING | no | 8/14
| Radiate tungsten/gallium | George/Pavel |  |  | x | FC2 | Max E | 10 uA cw | 1 | SWING | maybe | August?
15425 | GPT RF benchmarking | Injector group |  |  | x | FC2 | standard | Pulsed | 2 week | SWING | no | 8/17-8/28
15326 | Test 250MHz phase shifter | Joe/Tomasz/John |  | x | x | FC1/FC2 | standard | 10 uA cw | 0.5 | DAY | no | August?
| Test Brock deconvolution | Wes |  | x |  | FC1 | 130 keV | 10 uA cw | 0.5 | DAY | yes | August?
| Compare Brock and model | Brock team |  | x |  | FC1 | 130 keV | 100 uA cw | 1 | DAY | no | August?
| Bubble Commissioning | Riad |  |  | x | FC2 | 10 MeV | 100 uA | 1 week | SWING | maybe | 9/14-9/19
CRYO RECONFIGURATION AND PSS CERTIFICATION FROM SEP 21 - OCT 3
| Gun2 suitcase swap | Marcy/Joe | x | [5 empty] | 6 | DAY | yes | Week 9/21
| Laser#4 @ 31 MHz | Hansknecht | x | [5 empty] | 1 day | DAY | no | mid-Sept
| 250/499 laser/RF commissioning | EGG |  | x | x | FC1 | standard | 10 uA CW | 3 shift | DAY | maybe | October
| Commission new BCM0L02 receiver | Joe/Musson/Riad |  |  | x | FC2 | standard | 100 uA | 0.5 | DAY | yes | October
| Bubble Commissioning | Riad |  |  | x | FC2 | 10 MeV | 100 uA | 1 week | DAY/SWING | limited ? | October
15065 | Mott Run II | Mott team |  |  | x | FC2 | 3-8 MeV | 10 uA | 3-4 days | 24/7 | no | October
| Test DBR | EGG | x | x | x | FC1/FC2 | standard | 1 mA /10 uA | 3 days | 24/7 | yes | October
| Test Sb | EGG | x | x | x | FC1/FC2 | standard | 1 mA /10 uA | 3 days | 24/7 | yes | October
| Test Brock as phase monitor | Joe/Curt |  | x |  | FC1 | 130 keV | 50 uA | 0.5 | DAY | yes | October
| Activate photocathode for physics | EGG | x | [5 empty] | 1 | DAY | yes | Week 10/19
| 3 beam injector restoration | EGG/INJ |  |  | x | FC2 | standard | 100 uA cw | 2 days | 24/7 | no | Week 10/26