## Sheet1
TASK | April |  |  |  | May |  |  |  | June |  |  |  |  | July
| 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2-May | 9-May | 16-May | 23-May | 30-May | 6-June | 13-June | 2022-06-20 | 2022-06-27 | 2022-07-05
Wrap-up HV chamber vacuum eval
Measure HV chamber (S&A)
Shaun makes HV chamber model per Lesker prints
Define HV chamber layout for install at CEBAF using Inj Phase I anode flange
Anode bore shield tubes and Macor spsacer prints signed off
Anode bore shield tubes and Macor spacers fab
Anode tube length defined and prints signed off (one tube ground, other isolated)
Anode tubes fab (one 12 slot short (isolated) one 12 slot long (grounded)
Anode parts vacuum degas along with NEG screen 900 C
Anode assembly installation in HV chamber and fiducial
Define NEG screen
Neg screen frame prints ready for sign off
Neg screen fab (CIS? Shop?)
Neg screen UHV cleean and vacuum degas 900 C
Neg screen instal in HV chamber
Anode flange per print 0101 Inj Phase I version with two ports print for review
Anode flange per print 0101 Inj Phase I version with two ports fab
Anode flange with two ports vaacuum degas 400 C
Anode flange install to HV chaamber
Cathode aassembly and fiducial
Cathode install in HV chamber and fiducial
HV chamber install in UITF beam line
Establish vacuum and prep for bake
Bake
Remove bake and eval vacuum
High voltage conditioning