## Sheet1
UITF Wien filter rebuild using 13 mm electrode gap
September 21 2021
Item | Description | Qty | Status | Estimated cost
1 | MACOR electrode insulator | 10 | Req submitted to machine shop | 2275
2 | Single piece SS electrodes made by Xometry | 2 | 2 in final polishing sate. 4 unpolihsed spares
3 | 13 mm gap Teflon spacers | 2 | Material on hand, Carlos to submit request | 500
4 | Ceramic washers and scews | 16 | On hand
5 | SS spring washers | 16 | On hand
6 | Inconel electrode spacer springs 13 mm gap | 2 | On hand, 2 more spare sets
7 | HV spring guides | 2 | On hand, polished and ready
8 | HV conenctor non-magnetic springs | 2 | On hand
9 | HV spring pin retainer | 2 | Ordered, Carlos to find out where they are
10 | 40 kV CeramTec feedthroughs | 2 | On hand, 2 more spares
11 | Vacuum chamber | 1 | On hand, ready for magnet
12 | Ni end plates, 15 mm aperture | 2 | On hand, ready for mounting to chamber
13 | Steel yoke | 2 | On hand, ready for mounting to chamber
14 | Magnet coil | 2 | On hand, ready for mounting to magnet & chamber
15 | Magnet coild retainer plates | 2 | On hand, ready for mounting to magnet
16 | HV cables | 2 | Installed in UITF
17 | HV Matsusada power supply | 2 | Neg and Pos, installed in UITF
18 | HV switcher chassis | 1 | Installed in UITF, needs integration for EPICS control. Is a like, nothing more. | Waiting to hear back frm K. Cole on estimated cost