**PSS lock-ups in RED**

**Possible work within 6’ in BLUE**

**Week 0 (Sep 14-20)**

* Complete SAF300, MED13/N95 training
* Prep ISB w/ items for tunnel (DILO, PIG, HV cables, turbo cart, particle counter, etc…)

**Week 1 (Sep 21-27)**

Mon/21

* Day
	+ **Neil (AM)** – crane our stuff to tunnel.
	+ **CIS (AM) - pre-SAD gun checks**
		- (Joe) QE + Spiricon scans w/ ABCD lasers (wraps up biased anode tests)
		- (Shukui) Add irises to reckon laser launch + lock-out laser room shutter
		- (Joe) Move bulk GaAs to HV chamber, rest to Prep (later Suitcase)
	+ **S&A (PM)** – as found of y-chamber, gun, HV chamber, anything else

Tue/22

* DAY
	+ **Carlos/Bubba – setup for HV conditioning**
		- Lock-out gun HVPS
		- Install resistor for HV conditioning
		- Setup camera to remotely monitor Kr pressure
		- Relocate beam line decarads around Wien filters
	+ **Marcy/Phil – setup for HV conditioning**
		- Remove in-line NEG filters
		- Add turbo to exhaust line
		- Move Gun2 valve controls to Gun3 (to bypass HV interlock)
* SWING
	+ **Joe/Riad – test Wien filters vs. high voltage**
		- Evaluate performance to HVPS limit (15 kV)

Wed/23 to Sun/27

* DAY
	+ 8:30am Toolbox (https://bluejeans.com/7572697097)
	+ **Power Permit - SSO/CIS – Evaluate and condition Tee electrode**
* SWING
	+ 3:30pm Toolbox (https://bluejeans.com/7572697097)
	+ **Power Permit - SSO/CIS – Evaluate and condition Tee electrode**

**Daniel is organizing SSO support.**

**Carlos is organizing CIS support (workers + training)**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **CIS** | **Wed/23** | **Thu/24** | **Fri/25** | **Sat/26** | **Sun/27** |
| DAY | Carlos/Marcy | Bubba/Marcy | Joe/Carlos | Riad | Riad |
| SWING | Joe | Carlos | Eric | Eric | Eric |