## JMG 01 25 21
Themes | AIPINJ - Activity (detailed) | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7 | 6/14 | 6/21 | 6/28 | 7/5 | 7/12 | 7/19 | 7/26
PSS avail | INJ SEG PSS Availability (J. Kowal) or HV conditioning start of SAD | bar: 9/21; 10/12; 3/1
Test gun @ 200 kV | Gun - 200 kV w/o FE | bar: 9/21
Gun - HV condition tee, test Wien to 15 kV | bar: 9/21
Gun - Vent Gun, swap cathodes, bake
Gun - HV condition tee+shed cathode
Demolition injector | Instrument disconnects | bar: 9/28
Laser box disconnects | bar: 9/28
Vac - Vent/remove 2I, 1I, 0I beam line | bar: 10/5
Crane girders to 1137 | bar: 10/5
Drop penetrations | bar: 10/5 to 10/12
Build Y TL | S&A Y-chamber fiducial on girder | bar: 10/5 to 10/12
Laser window stress tests Y-chamber | bar: 10/12
Add Y-viewers | bar: 10/19
Add NEG's | bar: 10/26; 11/16
Add windows, valve, pumps | bar: 11/2; 11/23
Y-chamber leak testing (pre-install) | bar: 11/9
Install Gun to Y Tunnel | Move gun table | bar: 10/26
S&A set points | bar: 11/2
Receive pedestals | bar: 11/9
Install anchors, pedestals, grout | bar: 11/9 to 11/16
Fire pipe demo window | bar: 11/2; 11/16
Map new 15 deg dipoles DR#1, DR#2 | bar: 11/16; 1/11
Move gun table, install Y and beam line | bar: 11/30
Build 200 kV prebuncher | Prebuncher - complete machining all pars | bar: 9/21 to 10/12
Prebucher - braze end plates | bar: 10/19
Prebuncher - weld flanges, final leak check | bar: 10/26; 11/23
Prebuncher - RF testing/tuning | bar: 11/2 to 11/9; 11/23
Wien HV System | HV disconencts | bar: 9/28
Install and commission Wien High Voltage System, ready for connects | bar: 2/1
Wien Pre-Build Steps | Coordinate shop jobs/welding with vince | bar: 10/5
Remove Wien girder from tunnel and place them in TL1137 clean room | bar: 10/5
Remove Wiens from girder and remove steel & coil | bar: 10/5
Dissasemble keeping track of electrode positions & vacuum chambers | bar: 10/5 to 10/12
Take vacuum chambers to machine shop | bar: 10/12
Machine shop modfies vacuum chambers | bar: 10/19
Assemble Wien fixtrures | bar: 10/19 to 10/26
Take modified vacuum chambers & fixtures to Magnet Test | bar: 10/19 to 10/26
Test fit steel & coils on modified vacuum chambers | bar: 10/26
Install SCE PS for Wien maping | bar: 11/2
V-Wien Rebuild | V-Wien : magnetic assembly test & field mapping | bar: 11/2 to 11/16
V-Wien : vacuum chamber to cleaning | bar: 11/16
V-Wien : upgrade chamber w/ 40 kV feedthroughs & ceramic screws | bar: 11/16
V-Wien : initial add electrodes/align | bar: 11/23
V-Wien : initial bake and HV tests | bar: 11/30 to 12/7
V-Wien : final alignment | bar: 1/4
V-Wien : final bake and HV test (TBD) | bar: 1/11 to 1/18
V-Wien : ready for assembly to girder | bar: 1/11; 1/25
H-Wien Rebuild | H-Wien : initial magnetic assembly test & field mapping | bar: 11/23 to 11/30
H-Wien : remake end plates, clean and anneal | bar: 1/4
H-Wien : remap H-Wien field, decide on end-plates | bar: 1/11 to 1/18
H-Wien : vacuum chamber to cleaning | bar: 1/18
H-Wien : upgrade chamber w/ 40 kV feedthroughs & ceramic screws | bar: 1/18
H-Wien : align steel/electrodes | bar: 1/18
H-Wien : bake and HV tests | bar: 2/1
H-Wien : ready for assembly to girder | bar: 2/8
Build Wien girder TL | Wien quads crosses arrives | bar: 11/9 to 11/16
Wien quads hardware arrives | bar: 11/16; 12/7
Wien quads arrives | bar: 11/16; 12/7
Wien quad fit up tests | bar: 11/30; 12/14
Wien quad magnetic tests | bar: 12/7; 1/11
Wien quads weld flanges | bar: 1/18
Wien quads build new viewers | bar: 1/18
Wien quads - add viewers finaly assembly | bar: 1/25
Replace spool in FG solenoids | bar: 11/16; 1/11
Region 2 girder arrives | bar: 11/9 to 11/16
WIEN - (REGION 2) girder assembly/align in S&A lab | bar: 2/15
Build A1A2 girder TL | A1/A2 - weld aperture tube to cubes | bar: 10/12; 10/26
A1/A2 - MHD coils arrives | bar: 10/26
A1/A2 - MHD QC | bar: 11/2
A1/A2 - MHD weld up DOWN support fixutres | bar: 11/9
A1/A2 - collect TOP/LEFT/RIGHT flanges + tabs | bar: 11/9
A1/A2 - make up A1/A2 cubes, leak check | bar: 11/16
A1/A2 - cube fixtures arrive | bar: 11/16
A1/A2 - make up spare cube for magnet test | bar: 11/16
A1/A2 - magnetic mapping/tests with spare cube | bar: 11/23 to 11/30
A1/A2 - A1/A2 cubes gets magnets | bar: 11/30
A1/A2 - A1/A2 cubes get apertures for S&A | bar: 12/7
A1/A2 - A1/A2 final assembly of each cube is done | bar: 12/14; 1/4
A1/A2 - rebuild viewers | bar: 1/18
A1/A2 - girder arrives | bar: 11/9 to 11/16
A1/A2 (REGION 3) girder component assembly/align in S&A lab | bar: 1/25
Build 200 kV PSS kicker | PSS kicker design done | bar: 11/2 to 11/9; 12/7
PSS kicker ordered | bar: 11/16; 12/14
PSS kicker due | bar: 2/15
PSS kicker assembly parts done | bar: 2/15
PSS kicker bench tested, ready | bar: 3/1
Install bake girders tunnel | Preliminary injector songsheet available | bar: 1/4
Region 2 girder install/align | bar: 2/22 to 3/1
Region 2 girder bake | bar: 3/8 to 3/15
Region 2 girder reconnects | bar: 3/22 to 3/29
Region 3 girder install/align | bar: 2/1 to 2/8
Region 3 girder bake | bar: 2/15 to 2/22
Region 3 reconnects | bar: 3/1 to 3/8
Themes | AIPINJ - Activity (detailed) | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7 | 6/14 | 6/21 | 6/28 | 7/5 | 7/12 | 7/19 | 7/26 | AIPINJ - Activity (detailed)
PSS | PSS INJ CERT | [45 empty] | PSS INJ CERT | bar: 2/8 to 2/22
| PSS NL CERT | [45 empty] | PSS NL CERT | bar: X 5/3 to X 5/17
| STEVE NL AVAIL | [45 empty] | STEVE NL AVAIL | bar: X 6/7 to X 7/26
| PSS MACHINE CERT | [45 empty] | PSS MACHINE CERT | bar: X 5/24 to X 6/7
CRYO | QCM @ 4K | [45 empty] | QCM @ 4K | bar: X 4/19 to X 5/10
| QCM @ 2K | [45 empty] | QCM @ 2K | bar: X 5/17 to X 7/26
AIPINJ Commissioning | Complete Installation | [45 empty] | Complete Installation | bar: 1/25 to X 3/29
| HCO and System Readiness | [45 empty] | HCO and System Readiness | bar: X 4/5 to X 4/26
| Commission INJ setup @ 130/200 | [45 empty] | Commission INJ setup @ 130/200 | bar: X 5/3 to X 5/31
| LLRF 3.0 Window (prebuncher + buncher + choppers) | [45 empty] | LLRF 3.0 Window (prebuncher + buncher + choppers) | bar: X 5/31 to X 7/12
| Commission INJ/NL @ 130 + Wiens | [45 empty] | Commission INJ/NL @ 130 + Wiens | bar: X 6/7 to X 6/28
CEBAF Restore | CEBAF Restoration | [45 empty] | CEBAF Restoration | bar: X 7/5 to X 7/19
| Physics Begins | [45 empty] | Physics Begins | bar: X 7/26
LERF | LERF HV CHECK (do we need processing?) | [45 empty] | LERF HV CHECK (do we need processing?) | bar: 11/9
| CIS Ready for LERF Run 1 - 5 kW test | [45 empty] | CIS Ready for LERF Run 1 - 5 kW test | bar: 1/4 to 1/11
| CIS LERF Run 2 - ISOTOPE RUN | X 5/17: TBD; X 5/24: TBD; X 5/31: TBD; X 6/7: TBD; X 6/14: TBD; X 6/21: TBD; X 6/28: TBD; X 7/5: TBD; X 7/12: TBD; X 7/19: TBD; X 7/26: TBD | CIS LERF Run 2 - ISOTOPE RUN

## JMG 01 11 21
Themes | AIPINJ - Activity (detailed) | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7
PSS avail | INJ SEG PSS Availability (J. Kowal) | bar: 9/21; 10/12; 3/1
Test gun @ 200 kV | Gun - 200 kV w/o FE | bar: 9/21
Gun - HV condition tee, test Wien to 15 kV | bar: 9/21
Gun - Vent Gun, swap cathodes, bake
Gun - HV condition tee+shed cathode
Demolition injector | Instrument disconnects | bar: 9/28
Laser box disconnects | bar: 9/28
Vac - Vent/remove 2I, 1I, 0I beam line | bar: 10/5
Crane girders to 1137 | bar: 10/5
Drop penetrations | bar: 10/5 to 10/12
Build Y TL | S&A Y-chamber fiducial on girder | bar: 10/5 to 10/12
Laser window stress tests Y-chamber | bar: 10/12
Add Y-viewers | bar: 10/19
Add NEG's | bar: 10/26; 11/16
Add windows, valve, pumps | bar: 11/2; 11/23
Y-chamber leak testing (pre-install) | bar: 11/9
Install Gun to Y Tunnel | Move gun table | bar: 10/26
S&A set points | bar: 11/2
Receive pedestals | bar: 11/9
Install anchors, pedestals, grout | bar: 11/9 to 11/16
Fire pipe demo window | bar: 11/2; 11/16
Map new 15 deg dipoles DR#1, DR#2 | bar: 11/16; 1/11
Move gun table, install Y and beam line | bar: 11/30
Build 200 kV prebuncher | Prebuncher - complete machining all pars | bar: 9/21 to 10/12
Prebucher - braze end plates | bar: 10/19
Prebuncher - weld flanges, final leak check | bar: 10/26; 11/23
Prebuncher - RF testing/tuning | bar: 11/2 to 11/9; 11/23
Wien HV System | HV disconencts | bar: 9/28
Install and commission Wien High Voltage System, ready for connects | bar: 1/18
Wien Pre-Build Steps | Coordinate shop jobs/welding with vince | bar: 10/5
Remove Wien girder from tunnel and place them in TL1137 clean room | bar: 10/5
Remove Wiens from girder and remove steel & coil | bar: 10/5
Dissasemble keeping track of electrode positions & vacuum chambers | bar: 10/5 to 10/12
Take vacuum chambers to machine shop | bar: 10/12
Machine shop modfies vacuum chambers | bar: 10/19
Assemble Wien fixtrures | bar: 10/19 to 10/26
Take modified vacuum chambers & fixtures to Magnet Test | bar: 10/19 to 10/26
Test fit steel & coils on modified vacuum chambers | bar: 10/26
Install SCE PS for Wien maping | bar: 11/2
V-Wien Rebuild | V-Wien : magnetic assembly test & field mapping | bar: 11/2 to 11/16
V-Wien : vacuum chamber to cleaning | bar: 11/16
V-Wien : upgrade chamber w/ 40 kV feedthroughs & ceramic screws | bar: 11/16
V-Wien : initial add electrodes/align | bar: 11/23
V-Wien : initial bake and HV tests | bar: 11/30 to 12/7
V-Wien : final alignment | bar: 1/4
V-Wien : final bake and HV test (TBD) | bar: 1/11 to 1/18
V-Wien : ready for assembly to girder | bar: 1/11; 1/25
H-Wien Rebuild | H-Wien : initial magnetic assembly test & field mapping | bar: 11/23 to 11/30
H-Wien : remake end plates, clean and anneal | bar: 1/4
H-Wien : remap H-Wien field, decide on end-plates | bar: 1/11
H-Wien : vacuum chamber to cleaning | bar: 1/18
H-Wien : upgrade chamber w/ 40 kV feedthroughs & ceramic screws | bar: 1/18
H-Wien : align steel/electrodes | bar: 1/18
H-Wien : bake and HV tests | bar: 2/1
H-Wien : ready for assembly to girder | bar: 2/8
Build Wien girder TL | Wien quads crosses arrives | bar: 11/9 to 11/16
Wien quads hardware arrives | bar: 11/16; 12/7
Wien quads arrives | bar: 11/16; 12/7
Wien quad fit up tests | bar: 11/30; 12/14
Wien quad magnetic tests | bar: 12/7; 1/11
Wien quads weld flanges | bar: 1/18
Wien quads build new viewers | bar: 1/18
Wien quads - add viewers finaly assembly | bar: 1/25
Replace spool in FG solenoids | bar: 11/16; 1/11
Region 2 girder arrives | bar: 11/9 to 11/16
WIEN - (REGION 2) girder assembly/align in S&A lab | bar: 2/15
Build A1A2 girder TL | A1/A2 - weld aperture tube to cubes | bar: 10/12; 10/26
A1/A2 - MHD coils arrives | bar: 10/26
A1/A2 - MHD QC | bar: 11/2
A1/A2 - MHD weld up DOWN support fixutres | bar: 11/9
A1/A2 - collect TOP/LEFT/RIGHT flanges + tabs | bar: 11/9
A1/A2 - make up A1/A2 cubes, leak check | bar: 11/16
A1/A2 - cube fixtures arrive | bar: 11/16
A1/A2 - make up spare cube for magnet test | bar: 11/16
A1/A2 - magnetic mapping/tests with spare cube | bar: 11/23 to 11/30
A1/A2 - A1/A2 cubes gets magnets | bar: 11/30
A1/A2 - A1/A2 cubes get apertures for S&A | bar: 12/7
A1/A2 - A1/A2 final assembly of each cube is done | bar: 12/14; 1/4
A1/A2 - rebuild viewers | bar: 1/18
A1/A2 - girder arrives | bar: 11/9 to 11/16
A1/A2 (REGION 3) girder component assembly/align in S&A lab | bar: 1/25
Build 200 kV PSS kicker | PSS kicker design done | bar: 11/2 to 11/9; 12/7
PSS kicker ordered | bar: 11/16; 12/14
PSS kicker due | bar: 2/15
PSS kicker assembly parts done | bar: 2/15
PSS kicker bench tested, ready | bar: 3/1
Install bake girders tunnel | Preliminary injector songsheet available | bar: 1/4
Region 2 girder install/align | bar: 2/22 to 3/1
Region 2 girder bake | bar: 3/8 to 3/15
Region 2 girder reconnects | bar: 3/22 to 4/5
Region 3 girder install/align | bar: 2/1 to 2/8
Region 3 girder bake | bar: 2/15 to 2/22
Region 3 reconnects | bar: 3/1 to 3/8
Floats | Pre-Post Floats | bar: 3/1 to 3/29; 5/17
AIPINJ HCO/Commission | HCO w/o beam | bar: 4/5
Commission Week #1 - Gun | bar: 4/12
Commission Week #2 - Setup to chopper | bar: 4/19
Commission Week #3 - Setup to chopper | bar: 4/26
Commission Week #4 - Setup to FC2 | bar: 5/3
Commission Week #5 - Wien/Spin | bar: 5/10
CEBAF HCO/Restore | CEBAF HCO (S. Suhring) | bar: 5/24 to 5/31
CEBAF Restore (S. Suhring) | bar: 6/7
LERF | LERF HV CHECK (do we need processing?) | bar: 11/9
LERF Run 1 - 5 kW test | bar: 1/4 to 1/11
LERF Run 2 - ISOTOPE RUN | bar: 4/5 to 5/3

## JMG 12 18 20
Themes | AIPINJ - Activity (detailed) | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7
PSS avail | INJ SEG PSS Availability (J. Kowal) | bar: 9/21; 10/12; 3/1
Test gun @ 200 kV | Gun - 200 kV w/o FE | bar: 9/21
Gun - HV condition tee, test Wien to 15 kV | bar: 9/21
Gun - Vent Gun, swap cathodes, bake
Gun - HV condition tee+shed cathode
Demolition injector | Instrument disconnects | bar: 9/28
Laser box disconnects | bar: 9/28
Vac - Vent/remove 2I, 1I, 0I beam line | bar: 10/5
Crane girders to 1137 | bar: 10/5
Drop penetrations | bar: 10/5 to 10/12
Build Y TL | S&A Y-chamber fiducial on girder | bar: 10/5 to 10/12
Laser window stress tests Y-chamber | bar: 10/12
Add Y-viewers | bar: 10/19
Add NEG's | bar: 10/26; 11/16
Add windows, valve, pumps | bar: 11/2; 11/23
Y-chamber leak testing (pre-install) | bar: 11/9
Install Gun to Y Tunnel | Move gun table | bar: 10/26
S&A set points | bar: 11/2
Receive pedestals | bar: 11/9
Install anchors, pedestals, grout | bar: 11/9 to 11/16
Fire pipe demo window | bar: 11/2; 11/16
Move gun table, install Y and beam line | bar: 11/30
Build 200 kV prebuncher | Prebuncher - complete machining all pars | bar: 9/21 to 10/12
Prebucher - braze end plates | bar: 10/19
Prebuncher - weld flanges, final leak check | bar: 10/26; 11/23
Prebuncher - RF testing/tuning | bar: 11/2 to 11/9; 11/23
Wien HV System | HV disconencts | bar: 9/28
Install and commission Wien High Voltage System, ready for connects | bar: 1/18
Wien Pre-Build Steps | Coordinate shop jobs/welding with vince | bar: 10/5
Remove Wien girder from tunnel and place them in TL1137 clean room | bar: 10/5
Remove Wiens from girder and remove steel & coil | bar: 10/5
Dissasemble keeping track of electrode positions & vacuum chambers | bar: 10/5 to 10/12
Take vacuum chambers to machine shop | bar: 10/12
Machine shop modfies vacuum chambers | bar: 10/19
Assemble Wien fixtrures | bar: 10/19 to 10/26
Take modified vacuum chambers & fixtures to Magnet Test | bar: 10/19 to 10/26
Test fit steel & coils on modified vacuum chambers | bar: 10/26
Install SCE PS for Wien maping | bar: 11/2
V-Wien Rebuild | V-Wien : magnetic assembly test & field mapping | bar: 11/2 to 11/16
V-Wien : vacuum chamber to cleaning | bar: 11/16
V-Wien : upgrade chamber w/ 40 kV feedthroughs & ceramic screws | bar: 11/16
V-Wien : initial add electrodes/align | bar: 11/23
V-Wien : initial bake and HV tests | bar: 11/30 to 12/7
V-Wien : final alignment | bar: 1/4
V-Wien : final bake and HV test (TBD) | bar: 1/18
V-Wien : ready for assembly to girder | bar: 1/25
H-Wien Rebuild | H-Wien : initial magnetic assembly test & field mapping | bar: 11/23 to 11/30
H-Wien : remake end plates, clean and anneal | bar: 1/4
H-Wien : remap H-Wien field, decide on end-plates | bar: 1/11
H-Wien : vacuum chamber to cleaning | bar: 1/18
H-Wien : upgrade chamber w/ 40 kV feedthroughs & ceramic screws | bar: 1/18
H-Wien : align steel/electrodes | bar: 1/18
H-Wien : bake and HV tests | bar: 2/1
H-Wien : ready for assembly to girder | bar: 2/8
Build Wien girder TL | Wien quads crosses arrives | bar: 11/9 to 11/16
Wien quads hardware arrives | bar: 11/16; 12/7
Wien quads arrives | bar: 11/16; 12/7
Wien quad fit up tests | bar: 11/30; 12/14
Wien quad magnetic tests | bar: 12/7; 1/11
Wien quads weld flanges | bar: 1/18
Wien quads build new viewers | bar: 1/18
Wien quads - add viewers finaly assembly | bar: 1/25
Replace spool in FG solenoids | bar: 11/16; 1/11
Region 2 girder arrives | bar: 11/9 to 11/16
WIEN - (REGION 2) girder assembly/align in S&A lab | bar: 2/15
Build A1A2 girder TL | A1/A2 - weld aperture tube to cubes | bar: 10/12; 10/26
A1/A2 - MHD coils arrives | bar: 10/26
A1/A2 - MHD QC | bar: 11/2
A1/A2 - MHD weld up DOWN support fixutres | bar: 11/9
A1/A2 - collect TOP/LEFT/RIGHT flanges + tabs | bar: 11/9
A1/A2 - make up A1/A2 cubes, leak check | bar: 11/16
A1/A2 - cube fixtures arrive | bar: 11/16
A1/A2 - make up spare cube for magnet test | bar: 11/16
A1/A2 - magnetic mapping/tests with spare cube | bar: 11/23 to 11/30
A1/A2 - A1/A2 cubes gets magnets | bar: 11/30
A1/A2 - A1/A2 cubes get apertures for S&A | bar: 12/7
A1/A2 - A1/A2 final assembly of each cube is done | bar: 12/14; 1/4
A1/A2 - rebuild viewers | bar: 1/18
A1/A2 - girder arrives | bar: 11/9 to 11/16
A1/A2 (REGION 3) girder component assembly/align in S&A lab | bar: 1/25
Build 200 kV PSS kicker | PSS kicker design done | bar: 11/2 to 11/9; 12/7
PSS kicker ordered | bar: 11/16; 12/14
PSS kicker due | bar: 2/15
PSS kicker assembly parts done | bar: 2/15
PSS kicker bench tested, ready | bar: 3/1
Install bake girders tunnel | Preliminary injector songsheet available | bar: 1/4
Region 2 girder install/align | bar: 2/22 to 3/1
Region 2 girder bake | bar: 3/8 to 3/15
Region 2 girder reconnects | bar: 3/22 to 4/5
Region 3 girder install/align | bar: 2/1 to 2/8
Region 3 girder bake | bar: 2/15 to 2/22
Region 3 reconnects | bar: 3/1 to 3/8
Floats | Pre-Post Floats | bar: 3/1 to 3/29; 5/17
AIPINJ HCO/Commission | HCO w/o beam | bar: 4/5
Commission Week #1 - Gun | bar: 4/12
Commission Week #2 - Setup to chopper | bar: 4/19
Commission Week #3 - Setup to chopper | bar: 4/26
Commission Week #4 - Setup to FC2 | bar: 5/3
Commission Week #5 - Wien/Spin | bar: 5/10
CEBAF HCO/Restore | CEBAF HCO (S. Suhring) | bar: 5/24 to 5/31
CEBAF Restore (S. Suhring) | bar: 6/7
LERF | LERF HV CHECK (do we need processing?) | bar: 11/9
LERF Run 1 - 5 kW test | bar: 1/4 to 1/11
LERF Run 2 - ISOTOPE RUN | bar: 4/5 to 5/3

## JMG 12 08 20
Themes | AIPINJ - Activity (detailed) | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7
PSS avail | INJ SEG PSS Availability (J. Kowal) | bar: 9/21; 3/1
Test gun @ 200 kV | Gun - 200 kV w/o FE | bar: 9/21
Gun - HV condition tee, test Wien to 15 kV | bar: 9/21
Gun - Vent Gun, swap cathodes, bake
Gun - HV condition tee+shed cathode
Demolition injector | Instrument disconnects | bar: 9/28
Laser box disconnects | bar: 9/28
Vac - Vent/remove 2I, 1I, 0I beam line | bar: 10/5
Crane girders to 1137 | bar: 10/5; 11/2
Drop penetrations | bar: 10/5 to 10/12
Build Y TL | S&A Y-chamber fiducial on girder | bar: 10/5 to 10/12
Laser window stress tests Y-chamber | bar: 10/12
Add Y-viewers | bar: 10/19
Add NEG's | bar: 10/26; 11/16
Add windows, valve, pumps | bar: 11/2; 11/23
Y-chamber leak testing (pre-install) | bar: 11/9
Install Gun to Y Tunnel | Move gun table | bar: 10/26
S&A set points | bar: 11/2
Receive pedestals | bar: 11/9
Install anchors, pedestals, grout | bar: 11/9 to 11/16
Fire pipe demo window | bar: 11/2 to 11/23
Move gun table, install Y and beam line | bar: 11/30
Build 200 kV prebuncher | Prebuncher - complete machining all pars | bar: 9/21 to 10/12
Prebucher - braze end plates | bar: 10/19
Prebuncher - weld flanges, final leak check | bar: 10/26 to 11/23
Prebuncher - RF testing/tuning | bar: 11/2 to 11/23
Prebuncher - on girder | bar: 1/11
Rebuild Wiens 200 kV | HV disconencts | bar: 9/28
Install and commission Wien High Voltage System, ready for connects | bar: 9/28 to 11/23
Coordinate shop jobs/welding with vince | bar: 10/5
Remove Wien girder from tunnel and place them in TL1137 clean room | bar: 10/5
Remove Wiens from girder and remove steel & coil | bar: 10/5
Dissasemble keeping track of electrode positions & vacuum chambers | bar: 10/5 to 10/12
Take vacuum chambers to machine shop | bar: 10/12
Machine shop modfies vacuum chambers | bar: 10/19
Assemble Wien fixtrures | bar: 10/19 to 10/26
Take modified vacuum chambers & fixtures to Magnet Test | bar: 10/19 to 10/26
Test fit steel & coils on modified vacuum chambers | bar: 10/26
Install SCE PS for Wien maping | bar: 11/2
V-Wien : magnetic assembly test & field mapping | bar: 11/2 to 11/16
V-Wien : vacuum chamber to cleaning | bar: 11/16
V-Wien : upgrade chamber w/ 40 kV feedthroughs & ceramic screws | bar: 11/16
V-Wien : add electrodes/align | bar: 11/16 to 11/23
V-Wien : bake and HV tests | bar: 11/16 to 12/7
V-Wien : ready for assembly to girder | bar: 12/14
H-Wien : magnetic assembly test & field mapping | bar: 11/16 to 11/23
H-Wien : vacuum chamber to cleaning | bar: 11/30
H-Wien : upgrade chamber w/ 40 kV feedthroughs & ceramic screws | bar: 11/30
H-Wien : add electrodes/align | bar: 12/7
H-Wien : bake and HV tests | bar: 12/14; 1/4
H-Wien : ready for assembly to girder | bar: 1/11
Build Wien girder TL | Wien quads crosses arrives | bar: 11/9 to 11/16
Wien quads hardware arrives | bar: 11/16; 12/7
Wien quads arrives | bar: 11/16; 12/7
Wien quad fit up tests | bar: 11/23 to 11/30
Wien quad magnetic tests | bar: 11/30 to 12/7
Wien quads weld flanges | bar: 12/7 to 12/14; 1/4
Wien quads build new viewers | bar: 12/7 to 12/14; 1/4
Wien quads - add viewers finaly assembly | bar: 1/4 to 1/11
Replace spool in FG solenoids | bar: 1/4 to 1/11
Region 2 girder arrives | bar: 11/9 to 11/16
WIEN - (REGION 2) girder assembly/align in S&A lab | bar: 1/18 to 1/25
Build A1A2 girder TL | A1/A2 - weld aperture tube to cubes | bar: 10/12 to 10/26
A1/A2 - MHD coils arrives | bar: 10/26 to 11/2
A1/A2 - MHD QC | bar: 11/2
A1/A2 - MHD weld up DOWN support fixutres | bar: 11/9
A1/A2 - collect TOP/LEFT/RIGHT flanges + tabs | bar: 11/9
A1/A2 - make up A1/A2 cubes, leak check | bar: 11/16
A1/A2 - cube fixtures arrive | bar: 11/16
A1/A2 - make up spare cube for magnet test | bar: 11/16
A1/A2 - magnetic mapping/tests with spare cube | bar: 11/23 to 11/30
A1/A2 - A1/A2 cubes gets magnets | bar: 11/30
A1/A2 - A1/A2 cubes get apertures for S&A | bar: 12/7
A1/A2 - A1/A2 final assembly of each cube is done | bar: 12/14; 1/4
A1/A2 - rebuild viewers | bar: 12/7 to 12/14; 1/4
A1/A2 - girder arrives | bar: 11/9 to 11/16; 1/11 to 1/18
A1/A2 (REGION 3) girder component assembly/align in S&A lab | bar: 1/25 to 2/1
Build 200 kV PSS kicker | PSS kicker design done | bar: 11/2 to 11/9; 11/23; 12/7
PSS kicker ordered | bar: 11/16
PSS kicker fab | bar: 11/16 to 12/14; 1/4 to 3/1
PSS kicker arrives | bar: 3/1
PSS kicker bench tested, ready | bar: 3/1 to 3/15
Install bake girders tunnel | Preliminary injector songsheet available | bar: 1/4
Region 2 girder install/align | bar: 2/1 to 2/8
Region 2 girder bake | bar: 2/15 to 2/22
Region 2 girder reconnects | bar: 3/1 to 3/15
Region 3 girder install/align | bar: 2/8 to 2/15
Region 3 girder bake | bar: 2/22 to 3/1
Region 3 reconnects | bar: 3/8 to 3/15
Floats | Pre-Post Floats | bar: 3/1 to 3/29; 5/17
AIPINJ HCO/Commission | HCO w/o beam | bar: 4/5
Commission Week #1 - Gun | bar: 4/12
Commission Week #2 - Setup to chopper | bar: 4/19
Commission Week #3 - Setup to chopper | bar: 4/26
Commission Week #4 - Setup to FC2 | bar: 5/3
Commission Week #5 - Wien/Spin | bar: 5/10
CEBAF HCO/Restore | CEBAF HCO (S. Suhring) | bar: 5/24 to 5/31
CEBAF Restore (S. Suhring) | bar: 6/7
LERF | LERF HV CHECK (do we need processing?) | bar: 11/9
LERF Run 1 - 5 kW test | bar: 1/4 to 1/11
LERF Run 2 - ISOTOPE RUN | bar: 4/5 to 5/3

## JMG 11 17 20
Themes | AIPINJ - Activity (detailed) | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7
PSS avail | INJ SEG PSS Availability (J. Kowal) | bar: 9/21; 3/1
Test gun @ 200 kV | Gun - 200 kV w/o FE | bar: 9/21
Gun - HV condition tee, test Wien to 15 kV | bar: 9/21
Gun - Vent Gun, swap cathodes, bake
Gun - HV condition tee+shed cathode
Demolition injector | Instrument disconnects | bar: 9/28
Laser box disconnects | bar: 9/28
Vac - Vent/remove 2I, 1I, 0I beam line | bar: 10/5
Crane girders to 1137 | bar: 10/5; 11/2
Drop penetrations | bar: 10/5 to 10/12
Build Y TL | S&A Y-chamber fiducial on girder | bar: 10/5 to 10/12
Laser window stress tests Y-chamber | bar: 10/12
Add Y-viewers | bar: 10/19
Add NEG's | bar: 10/26; 11/16
Add windows, valve, pumps | bar: 11/2; 11/23
Y-chamber leak testing (pre-install) | bar: 11/9
Install Gun to Y Tunnel | Move gun table | bar: 10/26
S&A set points | bar: 11/2
Receive pedestals | bar: 11/9
Install anchors, pedestals, grout | bar: 11/9 to 11/16
Fire pipe demo window | bar: 11/2 to 11/23
Move gun table, install Y and beam line | bar: 11/30
Build 200 kV prebuncher | Prebuncher - complete machining all pars | bar: 9/21 to 10/12
Prebucher - braze end plates | bar: 10/19
Prebuncher - weld flanges, final leak check | bar: 10/26 to 11/23
Prebuncher - RF testing/tuning | bar: 11/2 to 11/23
Prebuncher - float | bar: 11/16 to 11/23
Prebuncher - on girder | bar: 11/30 to 12/7
Rebuild Wiens 200 kV | HV disconencts | bar: 9/28
Install and commission Wien High Voltage System, ready for connects | bar: 9/28 to 11/23
Coordinate shop jobs/welding with vince | bar: 10/5
Remove Wien girder from tunnel and place them in TL1137 clean room | bar: 10/5
Remove Wiens from girder and remove steel & coil | bar: 10/5
Dissasemble keeping track of electrode positions & vacuum chambers | bar: 10/5 to 10/12
Take vacuum chambers to machine shop | bar: 10/12
Machine shop modfies vacuum chambers | bar: 10/19
Assemble Wien fixtrures | bar: 10/19 to 10/26
Take modified vacuum chambers & fixtures to Magnet Test | bar: 10/19 to 10/26
Test fit steel & coils on modified vacuum chambers | bar: 10/26
Install SCE PS for Wien maping | bar: 11/2
V-Wien : magnetic assembly test & field mapping | bar: 11/2 to 11/16
V-Wien : vacuum chamber to cleaning | bar: 11/16
V-Wien : upgrade chamber w/ 40 kV feedthroughs & ceramic screws | bar: 11/16
V-Wien : add electrodes/align | bar: 11/16 to 11/23
V-Wien : bake and HV tests | bar: 11/16 to 12/7
V-Wien : ready for assembly to girder | bar: 12/14
H-Wien : magnetic assembly test & field mapping | bar: 11/16 to 11/23
H-Wien : vacuum chamber to cleaning | bar: 11/30
H-Wien : upgrade chamber w/ 40 kV feedthroughs & ceramic screws | bar: 11/30
H-Wien : add electrodes/align | bar: 12/7
H-Wien : bake and HV tests | bar: 12/14; 1/4
H-Wien : ready for assembly to girder | bar: 1/11
Build Wien girder TL | Wien quads crosses arrives | bar: 11/9 to 11/16
Wien quads hardware arrives | bar: 11/16
Wien quads arrives | bar: 11/16
Wien quad fit up tests | bar: 11/23 to 11/30
Wien quad magnetic tests | bar: 11/30 to 12/7
Wien quads weld flanges | bar: 12/7 to 12/14; 1/4
Wien quads build new viewers | bar: 12/7 to 12/14; 1/4
Wien quads - add viewers finaly assembly | bar: 1/4 to 1/11
Replace spool in FG solenoids | bar: 1/4 to 1/11
Region 2 girder arrives | bar: 11/9 to 11/16
WIEN - (REGION 2) girder assembly/align in S&A lab | bar: 1/18 to 1/25
Build A1A2 girder TL | A1/A2 - weld aperture tube to cubes | bar: 10/12 to 10/26
A1/A2 - MHD coils arrives | bar: 10/26 to 11/2
A1/A2 - MHD QC | bar: 11/2
A1/A2 - MHD weld up DOWN support fixutres | bar: 11/9
A1/A2 - collect TOP/LEFT/RIGHT flanges + tabs | bar: 11/9
A1/A2 - make up A1/A2 cubes, leak check | bar: 11/16
A1/A2 - cube fixtures arrive | bar: 11/16
A1/A2 - make up spare cube for magnet test | bar: 11/16
A1/A2 - magnetic mapping/tests with spare cube | bar: 11/23
A1/A2 - A1/A2 cubes gets magnets | bar: 11/30
A1/A2 - A1/A2 cubes get apertures for S&A | bar: 12/7
A1/A2 - A1/A2 final assembly of each cube is done | bar: 12/14; 1/4
A1/A2 - rebuild viewers | bar: 12/7 to 12/14; 1/4
A1/A2 - girder arrives | bar: 11/9 to 11/16; 1/11 to 1/18
A1/A2 (REGION 3) girder component assembly/align in S&A lab | bar: 1/25 to 2/1
Build 200 kV PSS kicker | PSS kicker design done | bar: 11/2 to 11/9; 11/23
PSS kicker ordered | bar: 11/16
PSS kicker fab | bar: 11/16 to 12/14; 1/4 to 3/1
PSS kicker arrives | bar: 3/1
PSS kicker bench tested, ready | bar: 3/1 to 3/15
Install bake girders tunnel | Preliminary injector songsheet available | bar: 1/4
Region 2 girder install/align | bar: 2/1 to 2/8
Region 2 girder bake | bar: 2/15 to 2/22
Region 2 girder reconnects | bar: 3/1 to 3/15
Region 3 girder install/align | bar: 2/8 to 2/15
Region 3 girder bake | bar: 2/22 to 3/1
Region 3 reconnects | bar: 3/8 to 3/15
Floats | Pre-Post Floats | bar: 3/1 to 3/29; 5/17
AIPINJ HCO/Commission | HCO w/o beam | bar: 4/5
Commission Week #1 - Gun | bar: 4/12
Commission Week #2 - Setup to chopper | bar: 4/19
Commission Week #3 - Setup to chopper | bar: 4/26
Commission Week #4 - Setup to FC2 | bar: 5/3
Commission Week #5 - Wien/Spin | bar: 5/10
CEBAF HCO/Restore | CEBAF HCO (S. Suhring) | bar: 5/24 to 5/31
CEBAF Restore (S. Suhring) | bar: 6/7
LERF | LERF HV CHECK (do we need processing?) | bar: 11/9
LERF Run 1 - 5 kW test | bar: 1/4 to 1/11
LERF Run 2 - ISOTOPE RUN | bar: 4/5 to 5/3

## CHG 11 13 20
Week of
Task | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21
UITF 3 shifts ops no access for Wien HV test
HV disconencts
Install and commission Wien High Voltage System, ready for connects
Coordinate shop jobs/welding with vince
Remove Wien girder from tunnel and place them in TL1137 clean room
Remove Wiens from girder and remove steel & coil
Dissasemble keeping track of electrode positions & vacuum chambers
Take vacuum chambers to machine shop
Machine shop modfies vacuum chambers
Assemble Wien fixtrures
Clean modified vacuum chambers
Take modified vacuum chambers & fixtures to Magnet Test
Test fit steel & coils on modified vacuum chambers
V-Wien magnetic assembly test & field mapping
Remove steel & coil from Vertical Wien, bring mounting fixtures to TL1137
Take Vertical Wien vacuum chamber to chem room for UHV cleaning
Assemble V-Wien upgrade with 40 kV feedthroughs & ceramic screws
Mount V-Wien in 80/20 testbed & bake in TL1137
V-Wien HV test in UITF-Checked w/Matt
Dismount V-Wien from HV testbed and move to TL1137 for girder install
H-Wien magnetic assembly test & field mapping
Remove steel & coil from Horizontal Wien, bring mounting fixtures to TL1137
Take Vertical Wien vacuum chamber to chem room for UHV cleaning
Assemble H-Wien upgrade with 40 kV feedthroughs & ceramic screws
Mount H-Wien in 80/20 testbed & bake in TL1137
H-Wien HV test in UITF CONFLICT WITH UITF OPS
Dismount H-Wien from HV testbed and move to TL1137 for girder install
Don't necessarily need to happen, we could wait until Wiens are installed & baked in beamline

## JMG 11 10 20
Themes | AIPINJ - Activity (detailed) | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7
PSS avail | INJ SEG PSS Availability (J. Kowal) | bar: 9/21; 2/22 to 6/7
Test gun @ 200 kV | Gun - 200 kV w/o FE | bar: 9/21
Gun - HV condition tee, test Wien to 15 kV | bar: 9/21
Gun - Vent Gun, swap cathodes, bake
Gun - HV condition tee+shed cathode
Demolition injector | Instrument disconnects | bar: 9/28
Laser box disconnects | bar: 9/28
Vac - Vent/remove 2I, 1I, 0I beam line | bar: 10/5
Crane girders to 1137 | bar: 10/5
Drop penetrations | bar: 10/5 to 10/12
Build Y TL | S&A Y-chamber fiducial on girder | bar: 10/5 to 10/12
Laser window stress tests Y-chamber | bar: 10/12
Add Y-viewers | bar: 10/19
Add NEG's | bar: 10/26
Add windows, valve, pumps | bar: 11/2
Final Y-chamber vacuum testing (pre-install) | bar: 11/9
Install Gun to Y Tunnel | Move gun table | bar: 10/26
S&A set points | bar: 11/2
Receive pedestals | bar: 11/9
Install anchors, pedestals, grout | bar: 11/9
Fire pipe demo window | bar: 11/2 to 11/23
Move gun table, install Y and beam line | bar: 11/30
Build 200 kV prebuncher | Prebuncher - complete machining all pars | bar: 9/21 to 10/12
Prebucher - braze end plates | bar: 10/19
Prebuncher - weld flanges, final leak check | bar: 10/26
Prebuncher - RF testing/tuning | bar: 11/2 to 11/9
Prebuncher - float | bar: 11/16 to 11/23
Prebuncher - on girder | bar: 11/30 to 12/7
Rebuild Wiens 200 kV | HV disconencts | bar: 9/28
Install and commission Wien High Voltage System, ready for connects | bar: 9/28 to 11/23
Coordinate shop jobs/welding with vince | bar: 10/5
Remove Wien girder from tunnel and place them in TL1137 clean room | bar: 10/5
Remove Wiens from girder and remove steel & coil | bar: 10/5
Dissasemble keeping track of electrode positions & vacuum chambers | bar: 10/5 to 10/12
Take vacuum chambers to machine shop | bar: 10/12
Machine shop modfies vacuum chambers | bar: 10/19
Assemble Wien fixtrures | bar: 10/19 to 10/26
Take modified vacuum chambers & fixtures to Magnet Test | bar: 10/19 to 10/26
Test fit steel & coils on modified vacuum chambers | bar: 10/26
Install SCE PS for Wien maping | bar: 11/2
V-Wien magnetic assembly test & field mapping | bar: 11/2 to 11/16
H-Wien magnetic assembly test & field mapping | bar: 11/9 to 11/23
Remove steel & coil from both Wiens, bring mounting fixtures to TL1137 | bar: 11/23
Take vacuum chambers to chem room for UHV cleaning | bar: 11/23
Assemble V-Wien upgrade with 40 kV feedthroughs & ceramic screws | bar: 11/30
Assemble H-Wien upgrade with 40 kV feedthroughs & ceramic screws | bar: 12/7
Mount V-Wien in 80/20 testbed & bake in ISB? Tunnel? | bar: 11/30
V-Wien HV test in ISB.? Tunnel.? | bar: 12/7
Dismount V-Wien from HV testbed and move to TL1137 for girder install | bar: 12/14
Mount H-Wien in 80/20 testbed & bake in ISB? Tunnel? | bar: 12/14
H-Wien HV test in ISB.? Tunnel.? | bar: 1/4
Dismount H-Wien from HV testbed and move to TL1137 for girder install | bar: 1/11
Build Wien girder TL | Wien quads crosses arrives | bar: 11/9
Wien quads hardware arrives | bar: 11/16
Wien quads arrives | bar: 11/16
Wien quad fit up tests | bar: 11/23 to 11/30
Wien quad magnetic tests | bar: 11/30 to 12/7
Wien quads weld flanges | bar: 12/7 to 12/14; 1/4
Wien quads build new viewers | bar: 12/7 to 12/14; 1/4
Wien quads - add viewers finaly assembly | bar: 1/4 to 1/11
Replace spool in FG solenoids | bar: 1/4 to 1/11
Region 2 girder arrives | bar: 11/16
WIEN - (REGION 2) girder component assembly occurs | bar: 11/16 to 12/14; 1/4 to 1/25
Build A1A2 girder TL | A1/A2 - weld aperture tube to cubes | bar: 10/12 to 10/26
A1/A2 - MHD coils arrives | bar: 10/26 to 11/2
A1/A2 - MHD QC | bar: 11/2
A1/A2 - MHD weld up DOWN support fixutres | bar: 11/9
A1/A2 - collect TOP/LEFT/RIGHT flanges + tabs | bar: 11/9
A1/A2 - make up A1/A2 cubes, leak check | bar: 11/16
A1/A2 - make up spare cube for magnet test | bar: 11/16
A1/A2 - magnetic mapping/tests with spare cube | bar: 11/23
A1/A2 - A1/A2 cubes gets magnets | bar: 11/30
A1/A2 - A1/A2 cubes get apertures for S&A | bar: 12/7
A1/A2 - A1/A2 final assembly of each cube is done | bar: 12/14; 1/4
A1/A2 - girder arrives | bar: 11/16; 1/11 to 1/18
A1/A2 (REGION 3) girder component assembly occurs | bar: 11/16 to 12/14; 1/4 to 2/1
Build 200 kV PSS kicker | PSS kicker design done | bar: 11/2 to 11/9
PSS kicker ordered | bar: 11/16
PSS kicker fab | bar: 11/16 to 12/14; 1/4 to 3/1
PSS kicker arrives | bar: 3/1
PSS kicker bench tested, ready | bar: 3/1 to 3/15
Install bake girders tunnel | Preliminary injector songsheet available | bar: 1/4; 2/1 to 3/15
Region 2 girder install/align | bar: 2/1 to 3/15
Region 2 girder bake | bar: 2/1 to 3/15
Region 2 girder reconnects | bar: 2/1 to 3/15
Region 3 girder install/align | bar: 2/1 to 3/15
Region 3 girder bake | bar: 2/1 to 3/15
Region 3 reconnects | bar: 2/1 to 3/15
Floats | Pre-Post Floats | bar: 3/1 to 3/29; 5/17
AIPINJ HCO/Commission | HCO w/o beam | bar: 4/5
Commission Week #1 - Gun | bar: 4/12
Commission Week #2 - Setup to chopper | bar: 4/19
Commission Week #3 - Setup to chopper | bar: 4/26
Commission Week #4 - Setup to FC2 | bar: 5/3
Commission Week #5 - Wien/Spin | bar: 5/10
CEBAF HCO/Restore | CEBAF HCO (S. Suhring) | bar: 5/24 to 5/31
CEBAF Restore (S. Suhring) | bar: 6/7
LERF | LERF HV CHECK (do we need processing?) | bar: 11/9
LERF Run 1 - 5 kW test | bar: 1/4 to 1/11
LERF Run 2 - ISOTOPE RUN | bar: 4/5 to 5/3

## JMG 11 06 20
AIPINJ - Activity (detailed) | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7
INJ SEG PSS Availability (J. Kowal) | bar: 9/21; 2/22 to 6/7
Gun - 200 kV w/o FE | bar: 9/21
Gun - HV condition tee, test Wien to 15 kV | bar: 9/21
Gun - Vent Gun, swap cathodes, bake
Gun - HV condition tee+shed cathode
Instrument disconnects | bar: 9/28
Laser box disconnects | bar: 9/28
Vac - Vent/remove 2I, 1I, 0I beam line | bar: 10/5
Crane girders to 1137 | bar: 10/5
Drop penetrations | bar: 10/5 to 10/12
S&A Y-chamber fiducial on girder | bar: 10/5 to 10/12
Laser window stress tests Y-chamber | bar: 10/12
Add Y-viewer | bar: 10/19
Add laser-viewer | bar: 10/26
Add NEG's | bar: 11/2
Final Y-chamber vacuum testing (pre-install) | bar: 11/9
Move gun table | bar: 10/26
S&A set points | bar: 11/2
Install anchors, pedestals, grout | bar: 11/9
Fire pipe demo window | bar: 11/2 to 11/23
Move gun table, install Y and beam line | bar: 11/30
Prebuncher - complete machining all pars | bar: 9/21 to 10/12
Prebucher - braze end plates | bar: 10/19
Prebuncher - weld flanges, final leak check | bar: 10/26
Prebuncher - RF testing/tuning | bar: 11/2 to 11/9
Prebuncher - float | bar: 11/16 to 11/23
Prebuncher - on girder | bar: 11/30 to 12/7
HV disconencts | bar: 9/28
Install and commission Wien High Voltage System, ready for connects | bar: 9/28 to 11/23
Coordinate shop jobs/welding with vince | bar: 10/5
Remove Wien girder from tunnel and place them in TL1137 clean room | bar: 10/5
Remove Wiens from girder and remove steel & coil | bar: 10/5
Dissasemble keeping track of electrode positions & vacuum chambers | bar: 10/5 to 10/12
Take vacuum chambers to machine shop | bar: 10/12
Machine shop modfies vacuum chambers | bar: 10/19
Assemble Wien fixtrures | bar: 10/19 to 10/26
Take modified vacuum chambers & fixtures to Magnet Test | bar: 10/19 to 10/26
Test fit steel & coils on modified vacuum chambers | bar: 10/26
Install SCE PS for Wien maping | bar: 11/2
V-Wien magnetic assembly test & field mapping | bar: 11/2 to 11/16
H-Wien magnetic assembly test & field mapping | bar: 11/9 to 11/23
Remove steel & coil from both Wiens, bring mounting fixtures to TL1137 | bar: 11/23
Take vacuum chambers to chem room for UHV cleaning | bar: 11/23
Assemble V-Wien upgrade with 40 kV feedthroughs & ceramic screws | bar: 11/30
Assemble H-Wien upgrade with 40 kV feedthroughs & ceramic screws | bar: 12/7
Mount V-Wien in 80/20 testbed & bake in ISB? Tunnel? | bar: 11/30
V-Wien HV test in ISB.? Tunnel.? | bar: 12/7
Dismount V-Wien from HV testbed and move to TL1137 for girder install | bar: 12/14
Mount H-Wien in 80/20 testbed & bake in ISB? Tunnel? | bar: 12/14
H-Wien HV test in ISB.? Tunnel.? | bar: 12/21
Dismount H-Wien from HV testbed and move to TL1137 for girder install | bar: 12/28
Wien crosses arrives | bar: 11/9
Wien hardware arrives | bar: 11/16
Wien quads arrives | bar: 11/16
Wien fit up tests | bar: 11/23 to 12/7
Wien magnetic tests | bar: 12/14 to 12/28
Wien quads weld flanges | bar: 12/28
Wien quads build new viewers | bar: 12/28
Wien quads - add viewers finaly assembly | bar: 1/4 to 1/11
Replace spool in FG solenoids | bar: 12/7
Region 2 girder arrives | bar: 11/16
Region 2 girder component assembly | bar: 11/16 to 1/11
Region 2 girder install/align | bar: 1/18 to 1/25
Region 2 girder bake | bar: 2/1 to 2/8
Region 2 reconnects | bar: 2/15 to 2/22
A1/A2 - weld aperture tube to cubes | bar: 10/12 to 10/26
A1/A2 - MHD coils arrives | bar: 10/26 to 11/2
A1/A2 - MHD QC | bar: 11/2
A1/A2 - MHD weld up DOWN support fixutres | bar: 11/9
A1/A2 - collect TOP/LEFT/RIGHT flanges + tabs | bar: 11/9
A1/A2 - make up A1/A2 cubes, leak check | bar: 11/16
A1/A2 - make up spare cube for magnet test | bar: 11/16
A1/A2 - magnetic mapping/tests with spare cube | bar: 11/23
A1/A2 - A1/A2 cubes gets magnets | bar: 11/30
A1/A2 - A1/A2 cubes get apertures for S&A | bar: 12/7
A1/A2 - A1/A2 final assembly of each cube is done | bar: 12/14 to 12/21
A1/A2 - on girder | bar: 12/28 to 1/4
A1/A2 - remaining girder assembly | bar: 1/11 to 1/18
PSS kicker design done | bar: 11/2 to 11/9
PSS kicker ordered | bar: 11/16
PSS kicker fab | bar: 11/16 to 2/15
PSS kicker arrives | bar: 2/15
PSS kicker bench tested, ready | bar: 2/15 to 3/1
Region 3 girder arrives | bar: 11/16
Region 3 girder beam line assembly | bar: 11/16 to 1/18
Region 3 girder - install to tunnel | bar: 1/25 to 2/1
Region 3 girder - bake | bar: 2/8 to 2/15
Region 3 reconnects | bar: 2/22 to 3/1
Pre-Post Floats | bar: 3/1 to 3/29; 5/17
HCO w/o beam | bar: 4/5
Commission Week #1 - Gun | bar: 4/12
Commission Week #2 - Setup to chopper | bar: 4/19
Commission Week #3 - Setup to chopper | bar: 4/26
Commission Week #4 - Setup to FC2 | bar: 5/3
Commission Week #5 - Wien/Spin | bar: 5/10
CEBAF HCO (S. Suhring) | bar: 5/24 to 5/31
CEBAF Restore (S. Suhring) | bar: 6/7
LERF HV CHECK (do we need processing?) | bar: 11/9
LERF Run 1 - 5 kW test | bar: 1/4 to 1/11
LERF Run 2 - ISOTOPE RUN | bar: 4/5 to 5/3

## JMG 10 29 20
AIPINJ - Activity (detailed) | Done | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7
INJ SEG PSS Availability (J. Kowal) | 2020-09-28
Gun - 200 kV w/o FE | 2020-09-23 | X
Gun - HV condition tee, test Wien to 15 kV | 2020-09-24 | X
Gun - Vent Gun, swap cathodes, bake | cancel
Gun - HV condition tee+shed cathode | cancel
Instrument disconnects |  |  | X
Laser box disconnects |  |  | X
Vac - Vent/remove 2I, 1I, 0I beam line |  |  |  | X
Crane girders to 1137 |  |  |  | X
Drop penetrations |  |  |  |  | X
S&A Y-chamber fiducial on girder |  |  |  | X
Laser window stress tests Y-chamber |  |  |  |  | X
Add Y-viewer | [5 empty] | X
Add laser-viewer | [6 empty] | X
Add NEG's | [7 empty] | X
Final Y-chamber vacuum testing (pre-install) | [8 empty] | X
Move gun table | [6 empty] | X
S&A set points | [7 empty] | X
Install anchors, pedestals, grout | [8 empty] | X
Fire pipe install window | [7 empty] | X | X | X | X
Move gun table, install Y and beam line | [11 empty] | X
Prebuncher - fab |  | X | X | X | X | X | X
Prebuncher - testing | [7 empty] | X | X | X | X
Prebuncher - on girder | [11 empty] | X | X
FG solenoids on girder w/ new spool ??? | [11 empty] | X | X
HV disconencts |  |  | X
Install and commission Wien High Voltage System, ready for connects |  |  | X | X | X | X | X | X | X | X | X
Coordinate shop jobs/welding with vince |  |  |  | X
Remove Wien girder from tunnel and place them in TL1137 clean room |  |  |  | X
Remove Wiens from girder and remove steel & coil |  |  |  | X
Dissasemble keeping track of electrode positions & vacuum chambers |  |  |  |  | X
Take vacuum chambers to machine shop |  |  |  |  | X
Machine shop modfies vacuum chambers | [5 empty] | X
Assemble Wien fixtrures | [5 empty] | X
Take modified vacuum chambers & fixtures to Magnet Test | [6 empty] | X
Test fit steel & coils on modified vacuum chambers | [6 empty] | X
Install SCE PS for Wien maping | [7 empty] | X
V-Wien magnetic assembly test & field mapping | [5 empty] | X | X | X
H-Wien magnetic assembly test & field mapping | [6 empty] | X | X | X
Remove steel & coil from both Wiens, bring mounting fixtures to TL1137 | [9 empty] | X
Take vacuum chambers to chem room for UHV cleaning | [9 empty] | X
Assemble V-Wien upgrade with 40 kV feedthroughs & ceramic screws | [10 empty] | X
Assemble H-Wien upgrade with 40 kV feedthroughs & ceramic screws | [11 empty] | X
Mount V-Wien in 80/20 testbed & bake in ISB? Tunnel? | [10 empty] | X
V-Wien HV test in ISB.? Tunnel.? | [11 empty] | X
Dismount V-Wien from HV testbed and move to TL1137 for girder install | [12 empty] | X
Mount H-Wien in 80/20 testbed & bake in ISB? Tunnel? | [12 empty] | X
H-Wien HV test in ISB.? Tunnel.? | [13 empty] | X
Dismount H-Wien from HV testbed and move to TL1137 for girder install | [14 empty] | X
Wien cross - build new viewers | [8 empty] | X | X | X | X
Wien cross - quads arrive, QA | [11 empty] | X
Wien cross - add quads, weld flanges | [12 empty] | X | X
Wien cross - map quads | [14 empty] | X | X
Wien cross - final assembly | [16 empty] | X | X
Region 2 girder install/align | [18 empty] | X | X
Region 2 girder bake | [20 empty] | X | X
Region 2 reconnects | [22 empty] | X | X
A1/A2 - welded cubes ready/clean | [5 empty] | X | X
A1/A2 - MHD coils arrives | [6 empty] | X | X
A1/A2 - MHD assembly/mapping | [8 empty] | X
A1/A2 - vacuum aperture assembly & alignment | [9 empty] | X | X
A1/A2 - on girder | [11 empty] | X | X
A1/A2 - remaining girder assembly | [13 empty] | X | X | X
PSS kicker design done | [7 empty] | X | X
PSS kicker ordered | [9 empty] | X
PSS kicker fab | [9 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X
PSS kicker arrives | [22 empty] | X
PSS kicker bench tested, ready | [22 empty] | X | X | X
Region 3 girder - install to tunnel | [16 empty] | X | X
Region 3 girder - bake | [18 empty] | X | X
Region 3 reconnects | [20 empty] | X | X
Pre-Post Floats
HCO w/o beam | [29 empty] | X
Commission Week #1 - Gun | [30 empty] | X
Commission Week #2 - Setup to chopper | [31 empty] | X
Commission Week #3 - Setup to chopper | [32 empty] | X
Commission Week #4 - Setup to FC2 | [33 empty] | X
Commission Week #5 - Wien/Spin | [34 empty] | X
CEBAF HCO (S. Suhring) | [36 empty] | X | X
CEBAF Restore (S. Suhring) | [38 empty] | X
LERF HV CHECK (do we need processing?) | [8 empty] | X
LERF Run 1 - 5 kW test | [16 empty] | X | X
LERF Run 2 - ISOTOPE RUN | [29 empty] | X | X | X | X | X

## JMG 10 08 20
AIPINJ - Activity (detailed) | Done | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7
INJ SEG PSS Availability (J. Kowal) | 2020-09-28
Gun - 200 kV w/o FE | 2020-09-23 | X
Gun - HV condition tee, test Wien to 15 kV | 2020-09-24 | X
Gun - Vent Gun, swap cathodes, bake | cancel
Gun - HV condition tee+shed cathode | cancel
Instrument disconnects |  |  | X
Laser box disconnects |  |  | X
Vac - Vent/remove 2I, 1I, 0I beam line |  |  |  | X
Crane girders to 1137 |  |  |  | X
Drop penetrations |  |  |  |  | X
S&A Y-chamber fiducial on girder |  |  |  | X
Laser window stress tests Y-chamber |  |  |  |  | X
Add NEG's and viewers to Ychamber | [5 empty] | X
Final Y-chamber vacuum testing (pre-install) | [6 empty] | X
Move gun table, install Y and beam line | [7 empty] | X
Prebuncher - fab |  | X | X | X | X | X | X
Prebuncher - testing | [7 empty] | X | X | X | X
Prebuncher - on girder | [11 empty] | X | X
FG solenoids on girder w/ new spool ??? | [11 empty] | X | X
HV disconencts |  |  | X
Install and commission Wien High Voltage System, ready for connects |  |  | X | X | X | X | X | X | X | X | X
Coordinate shop jobs/welding with vince |  |  |  | X
Remove Wien girder from tunnel and place them in TL1137 clean room |  |  |  | X
Remove Wiens from girder and remove steel & coil |  |  |  | X
Dissasemble keeping track of electrode positions & vacuum chambers |  |  |  |  | X
Take vacuum chambers to machine shop |  |  |  |  | X
Machine shop modfies vacuum chambers | [5 empty] | X
Assemble Wien fixtrures | [5 empty] | X
Clean modified vacuum chambers | [6 empty] | X
Take modified vacuum chambers & fixtures to Magnet Test | [6 empty] | X
Test fit steel & coils on modified vacuum chambers | [6 empty] | X
V-Wien magnetic assembly test & field mapping | [7 empty] | X
H-Wien magnetic assembly test & field mapping | [8 empty] | X
Remove steel & coil from both Wiens, bring mounting fixtures to TL1137 | [9 empty] | X
Take vacuum chambers to chem room for UHV cleaning | [9 empty] | X
Assemble V-Wien upgrade with 40 kV feedthroughs & ceramic screws | [10 empty] | X
Assemble H-Wien upgrade with 40 kV feedthroughs & ceramic screws | [11 empty] | X
Mount V-Wien in 80/20 testbed & bake in ISB? Tunnel? | [10 empty] | X
V-Wien HV test in ISB.? Tunnel.? | [11 empty] | X
Dismount V-Wien from HV testbed and move to TL1137 for girder install | [12 empty] | X
Mount H-Wien in 80/20 testbed & bake in ISB? Tunnel? | [12 empty] | X
H-Wien HV test in ISB.? Tunnel.? | [13 empty] | X
Dismount H-Wien from HV testbed and move to TL1137 for girder install | [14 empty] | X
Wien cross - build new viewers | [8 empty] | X | X | X | X
Wien cross - quads arrive, QA | [11 empty] | X
Wien cross - add quads, weld flanges | [12 empty] | X | X
Wien cross - map quads | [14 empty] | X | X
Wien cross - final assembly | [16 empty] | X | X
Region 2 girder install/align | [18 empty] | X | X
Region 2 girder bake | [20 empty] | X | X
Region 2 reconnects | [22 empty] | X | X
A1/A2 - welded cubes ready/clean | [5 empty] | X | X
A1/A2 - MHD coils arrives | [6 empty] | X | X
A1/A2 - MHD assembly/mapping | [8 empty] | X
A1/A2 - vacuum aperture assembly & alignment | [9 empty] | X | X
A1/A2 - on girder | [11 empty] | X | X
A1/A2 - remaining girder assembly | [13 empty] | X | X | X
Region 3 girder - install to tunnel | [16 empty] | X | X
Region 3 girder - bake | [18 empty] | X | X
Region 3 reconnects | [20 empty] | X | X
Pre-Post Floats
HCO w/o beam | [29 empty] | X
Commission Week #1 - Gun | [30 empty] | X
Commission Week #2 - Setup to chopper | [31 empty] | X
Commission Week #3 - Setup to chopper | [32 empty] | X
Commission Week #4 - Setup to FC2 | [33 empty] | X
Commission Week #5 - Wien/Spin | [34 empty] | X
CEBAF HCO (S. Suhring) | [36 empty] | X | X
CEBAF Restore (S. Suhring) | [38 empty] | X
LERF Run 1 - mid November run (HCO, then run) | [9 empty] | X |  | X
LERF Run 2 - mid January run (HCO, then run) | [16 empty] | X | X

## CHG 10 01 20
Week of
Task | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21
HV disconencts
Install and commission Wien High Voltage System, ready for connects
Coordinate shop jobs/welding with vince
Remove Wien girder from tunnel and place them in TL1137 clean room
Remove Wiens from girder and remove steel & coil
Dissasemble keeping track of electrode positions & vacuum chambers
Take vacuum chambers to machine shop
Machine shop modfies vacuum chambers
Assemble Wien fixtrures
Clean modified vacuum chambers
Take modified vacuum chambers & fixtures to Magnet Test
Test fit steel & coils on modified vacuum chambers
V-Wien magnetic assembly test & field mapping
H-Wien magnetic assembly test & field mapping
Remove steel & coil from both Wiens, bring mounting fixtures to TL1137
Take vacuum chambers to chem room for UHV cleaning
Assemble V-Wien upgrade with 40 kV feedthroughs & ceramic screws
Assemble H-Wien upgrade with 40 kV feedthroughs & ceramic screws
Mount V-Wien in 80/20 testbed & bake in ISB? Tunnel?
V-Wien HV test in ISB.? Tunnel.?
Dismount V-Wien from HV testbed and move to TL1137 for girder install
Mount H-Wien in 80/20 testbed & bake in ISB? Tunnel?
H-Wien HV test in ISB.? Tunnel.?
Dismount H-Wien from HV testbed and move to TL1137 for girder install
Don't necessarily need to happen, we could wait until Wiens are installed & baked in beamline

## JMG 10 01 20
AIPINJ - Activity (detailed) | Done | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22 | 3/1 | 3/8 | 3/15 | 3/22 | 3/29 | 4/5 | 4/12 | 4/19 | 4/26 | 5/3 | 5/10 | 5/17 | 5/24 | 5/31 | 6/7
INJ SEG PSS Availability (J. Kowal) | 2020-09-28
Gun - 200 kV w/o FE | 2020-09-23 | X
Gun - HV condition tee, test Wien to 15 kV | 2020-09-24 | X
Gun - Vent Gun, swap cathodes, bake | cancel
Gun - HV condition tee+shed cathode | cancel
Instrument disconnects |  |  | X
Laser box disconnects |  |  | X
Vac - Vent/remove 2I, 1I, 0I beam line |  |  |  | X
Crane girders to 1137 |  |  |  | X
Drop penetrations |  |  |  |  | X
S&A Y-chamber fiducial on girder |  |  |  | X
Laser window stress tests Y-chamber |  |  |  |  | X
Add NEG's and viewers to Ychamber | [5 empty] | X
Final Y-chamber vacuum testing (pre-install) | [6 empty] | X
Move gun table, install Y and beam line | [7 empty] | X
Prebuncher - fab
Prebuncher - testing
Prebuncher - on girder
FG solenoids on girder w/ new spool ???
Install and commission Wien High Voltage System, ready for connects |  |  |  | ? | ? | ? | ? | ? | ?
Coordinate shop jobs/welding with vince
Remove Wiens from tunnel and place them in TL1137 clean room
Remove Steel & coil
Dissasemble keeping track of electrode positions & vacuum chambers
Take vacuum chambers to machine shop
Machine shop modfies vacuum chambers
Take modified vacuum chambers to Magnet Test
Assemble steel & mount coils
V-Wien magnetic assembly test
V-Wien magnetic field mapping
Remove steel & coil from V-Wien
Take V-Wien vacuum chamber to chem room for UHV cleaning
Assemble V-Wien upgrade with 40 kV feedthroughs & ceramic screws
Install V-Wien in test fixture & bake
H-Wien magnetic assembly test
H-Wien magnetiic field mapping
Remove steel & coil from H-Wien
Take H-Wien vacuum chamber to chem room for UHV cleaning
Assemble H-Wien upgrade with 40 kV feedthroughs & ceramic screws
V-Wien filter HV test in UITF?
Remove V-Wien from text fixture and have it ready for girder install
Install H-Wien in test fixture & bake
H-Wien HV test in UITF?
Remove H-Wien from text fixture and have it ready for girder install
Wien cross - build new viewers
Wien cross - quads arrive, QA
Wien cross - add quads, weld flanges
Wien cross - map quads
Wien cross - final assembly
Region 2 girder install/align
Region 2 girder bake
Region 2 reconnects
A1/A2 - welded cubes ready/clean
A1/A2 - MHD coils arrives
A1/A2 - MHD assembly/mapping
A1/A2 - vacuum aperture assembly & alignment
A1/A2 - on girder
A1/A2 - remaining girder assembly
Region 3 girder - install to tunnel
Region 3 girder - bake
Region 3 reconnects
Pre-Post Floats
HCO w/o beam
Commission Week #1 - Gun
Commission Week #2 - Setup to chopper
Commission Week #3 - Setup to chopper
Commission Week #4 - Setup to FC2
Commission Week #5 - Wien/Spin
CEBAF HCO (S. Suhring) | [36 empty] | X | X
CEBAF Restore (S. Suhring) | [38 empty] | X
LERF Run 1 - mid November run
LERF Run 2 - mid January run

## MS 09 30 20
When | Marcy's e-mail | Joe's comments
Next Mon/Tue | (a) vent VBV2Ixx to VBV1I07 through y chamber rough valve monitor vacuum in gun and 3I stub disconnect beamline at y chamber, upstream of 1I07 and blank off remove harp cross - it hangs off the end of the girder and won't be supported well disconnect beamline segments that are attached to laser table, blank off pump down blank & y chamber to rough vacuum through the y chamber rough pump. (b) vent between 1I07 and 0I02 through rough pump port (0I01, I think) disconnect, blank to transport under nitrogen If desired, put pinch valve on 0I02 valve and pump the back side of that valve. | Both of your steps "a" and "b" in either order Grab laser window + Gun3 valve + anything else, blank off and pump down Remove suitcase w/ 2 "bad" pucks Final prep for Neil removal Give one harp to Matt for UITF
Next Wed/Thu? |  | Neil lifts laser table + stand out of way (if we haven't already) Neil moves both girders + suitcase to 1137, on your sawhorses Neil delivers oil tank to Brett Lewis
Next Fri |  | Float, in case it rains or something
Intervening weeks… |  | Finish Y-chamber... (a) Swap green solenoid direction (b) S&A finish 1A (c ) I have conf call w/ Caryn early next week (d) Add viewers + NEG's
Late October i.e. S&A | vent remove 2I line remove and replace 10" flange, mini feedthrough blank 4.5" flange remove old suitcase with appropriate pucks rough down, get ion pumps on move to proper location install new puck loader, bake that install 2I line, attach to gun, bake | -remove old Y and 2I line -C5 moves gun table, relocates feet, put gun table down -Neil cranes OUT old Y and cranes IN new Y, position on pedestals -S&A 2A on Y & table, pedestal -Gun work, install new 2I -Pump down Gun, 2I, Y -Add new suitcase when convenient, can come later...

## CHG 09 30 20
Week of
Task | 2020-11-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21
HV disconencts
Let Vince know Wien vacuum chmbers are coming to the shop approx Friday Oct-9
Remove Wiens from tunnel and place them in TL1137 clean room
Remove Steel & coil
Dissasemble keeping track of electrode positions & vacuum chambers
Take vacuum chambers to machine shop
Machine shop modfies vacuum chambers
Take modified vacuum chambers to Magnet Test
Assemble steel & mount coils
V-Wien magnetic assembly test
V-Wien magnetic field mapping
Remove steel & coil from V-Wien
Take V-Wien vacuum chamber to chem room for UHV cleaning
Assemble V-Wien upgrade with 40 kV feedthroughs & ceramic screws
Install V-Wien in test fixture & bake
H-Wien magnetic assembly test
H-Wien magnetiic field mapping
Remove steel & coil from H-Wien
Take H-Wien vacuum chamber to chem room for UHV cleaning
Assemble H-Wien upgrade with 40 kV feedthroughs & ceramic screws
V-Wien filter HV test in UITF?
Remove V-Wien from text fixture and have it ready for girder install
Install H-Wien in test fixture & bake
H-Wien HV test in UITF?
Remove H-Wien from text fixture and have it ready for girder install

## JMG 09 14 20
AIPINJ - Activity (overview) | Start | End | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
INJ SEG PSS Availability (J. Kowal) | 2020-09-01 | 2020-10-15 | bar: SEP 1 to OCT 2; MAR 1 to JUN 4
200 kV Gun and Wien tests | 2020-09-21 | 2020-10-14 | bar: SEP 3 to OCT 2
Beamline removal | 2020-10-01 | 2020-10-31 | bar: OCT 1 to OCT 4
Region 1 installation | 2020-11-01 | 2020-12-14 | bar: NOV 1 to DEC 2
Region 2 installation | 2020-06-01 | 2020-04-15 | bar: SEP 1 to APR 2
Region 3 installation | 2020-10-08 | 2020-02-21 | bar: OCT 3 to FEB 3
HCO and commissioning | 2020-04-15 | 2020-05-30 | bar: APR 3 to MAY 4
CEBAF HCO & Restore (S. Suhring) | 2020-05-24 | 2020-10-01 | bar: MAY 4 to JUN 4
LERF Run 1 - mid November run | 2020-11-07 | 2020-11-21 | bar: NOV 2 to NOV 3
LERF Run 2 - mid January run | 2020-01-07 | 2020-01-21 | bar: JAN 2 to JAN 3
AIPINJ - Activity (detailed) | Start | End | SEP 1: SEP; OCT 1: OCT; NOV 1: NOV; DEC 1: DEC; JAN 1: JAN; FEB 1: FEB; MAR 1: MAR; APR 1: APR; MAY 1: MAY; JUN 1: JUN
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
INJ SEG PSS Availability (J. Kowal) | 2020-09-01 | 2020-10-15 | bar: SEP 1 to OCT 2; MAR 1 to JUN 4
200 kV Gun and Wien tests | 2020-09-21 | 2020-10-14 | bar: SEP 3 to OCT 2
Gun - HV condition tee, test Wien to 15 kV | 2020-09-21 | 2020-09-30 | bar: SEP 3
Gun - Vent Gun, swap cathodes, bake | 2020-10-01 | 2020-10-07 | bar: SEP 4 to OCT 1
Gun - HV condition tee+shed cathode | 2020-10-08 | 2020-10-14 | bar: OCT 2
Beamline removal | 2020-10-01 | 2020-10-31 | bar: OCT 1 to OCT 4
Vac - Early 1I (Y) vacuum removal | 2020-10-01 | 2020-10-14 | bar: OCT 1 to OCT 2
Vac - 2I, 1I, 0I laser box disconnects | 2020-10-15 | 2020-10-21 | bar: OCT 3
Vac - Vent/remove 2I, 1I, 0I beam line | 2020-10-22 | 2020-10-31 | bar: OCT 4
Region 1 installation | 2020-11-01 | 2020-12-14 | bar: NOV 1 to DEC 2
Vac - Complete rebuild of Y | 2020-11-01 | 2020-11-07 | bar: NOV 1
Vac - Install/align beamline Gun, 2I, Y | 2020-11-01 | 2020-11-14 | bar: NOV 1 to NOV 2
Region 1 (Gun, 2I) bake | 2020-11-15 | 2020-11-30 | bar: NOV 3 to NOV 4
Region 1 reconnects | 2020-12-01 | 2020-12-14 | bar: DEC 1 to DEC 2
Region 2 installation | 2020-06-01 | 2020-04-15 | bar: SEP 1 to APR 2
Prebuncher - fab | 2020-06-01 | 2020-10-30 | bar: SEP 1 to OCT 4
Prebuncher - testing | 2020-11-01 | 2020-11-30 | bar: NOV 1 to NOV 4
Prebuncher - on girder | 2020-12-01 | 2020-12-15 | bar: DEC 1 to DEC 2
FG solenoids on girder | 2020-12-01 | 2020-12-15 | bar: DEC 1 to DEC 2
Wiens - Modify/clean Wien vacuum chamber | 2020-10-21 | 2020-11-14 | bar: OCT 4 to NOV 2
Wiens - Assemble/map Wien magnet | 2020-11-15 | 2020-11-30 | bar: NOV 3 to NOV 4
Wiens - Finalize electrodes | 2020-12-01 | 2020-12-14 | bar: DEC 1 to DEC 2
Wiens - Complete S&A assembly | 2020-12-14 | 2020-01-07 | bar: DEC 3 to JAN 1
Wiens - Test HV | 2020-01-08 | 2020-01-21 | bar: JAN 2 to JAN 3
Wiens - On girder | 2020-01-22 | 2020-02-07 | bar: JAN 4 to FEB 1
Wien cross - build new viewers | 2020-11-21 | 2020-12-21 | bar: NOV 4 to DEC 3
Wien cross - quads arrive, QA | 2020-12-22 | 2020-01-14 | bar: DEC 4 to JAN 2
Wien cross - add quads, weld flanges | 2020-01-15 | 2020-01-31 | bar: JAN 3 to JAN 4
Wien cross - map quads | 2020-02-01 | 2020-02-14 | bar: FEB 1 to FEB 2
Wien cross - final assembly | 2020-02-15 | 2020-02-28 | bar: FEB 3 to FEB 4
Region 2 girder install/align | 2020-03-01 | 2020-03-14 | bar: MAR 1 to MAR 2
Region 2 girder bake | 2020-03-15 | 2020-03-31 | bar: MAR 3 to MAR 4
Region 2 reconnects | 2020-04-01 | 2020-04-15 | bar: APR 1 to APR 2
Region 3 installation | 2020-10-08 | 2020-02-21 | bar: OCT 3 to FEB 3
A1/A2 - welded cubes ready/clean | 2020-10-08 | 2020-10-14 | bar: OCT 3 to OCT 4
A1/A2 - MHD coils arrives | 2020-10-23 | 2020-11-07 | bar: OCT 4 to NOV 1
A1/A2 - MHD assembly/mapping | 2020-11-08 | 2020-11-14 | bar: NOV 2
A1/A2 - vacuum aperture assembly & alignment | 2020-11-15 | 2020-11-30 | bar: NOV 3 to NOV 4
A1/A2 - on girder | 2020-12-01 | 2020-12-14 | bar: DEC 1 to DEC 2
A1/A2 - remaining girder assembly | 2020-12-15 | 2020-01-07 | bar: DEC 3 to JAN 1
Region 3 girder - install to tunnel | 2020-01-08 | 2020-01-21 | bar: JAN 2 to JAN 3
Region 3 girder - bake | 2020-01-22 | 2020-02-07 | bar: JAN 4 to FEB 1
Region 3 reconnects | 2020-02-08 | 2020-02-21 | bar: FEB 2 to FEB 3
HCO and commissioning | 2020-04-15 | 2020-05-30 | bar: APR 3 to MAY 4
HCO w/o beam | 2020-04-15 | 2020-04-21 | bar: APR 3
Commission Week #1 - Gun | 2020-04-22 | 2020-04-30 | bar: APR 4
Commission Week #2 - Setup to chopper | 2020-05-01 | 2020-05-07 | bar: MAY 1
Commission Week #3 - Setup to chopper | 2020-05-08 | 2020-05-14 | bar: MAY 2
Commission Week #4 - Setup to FC2 | 2020-05-15 | 2020-05-21 | bar: MAY 3
Commission Week #5 - Wien/Spin | 2020-05-22 | 2020-05-30 | bar: MAY 4
CEBAF HCO & Restore (S. Suhring) | 2020-05-24 | 2020-10-01 | bar: MAY 4 to JUN 4
CEBAF HCO (S. Suhring) | 2020-05-24 | 2020-06-07 | bar: MAY 4 to JUN 1
CEBAF Restore (S. Suhring) | 2020-06-07 | 2020-06-21 | bar: JUN 2 to JUN 3
Start Physics (S. Suhring) | 2020-06-21 | 2020-10-01 | bar: JUN 4
LERF Run 1 - mid November run | 2020-11-07 | 2020-11-21 | bar: NOV 2 to NOV 3
LERF Run 2 - mid January run | 2020-01-07 | 2020-01-21 | bar: JAN 2 to JAN 3

## JMG 09 01 20
AIPINJ - Activity (overview) | Start | End | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | Comments
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
INJ SEG PSS Availability (J. Kowal) | 2020-09-01 | 2020-10-15 | [40 empty] | PSS Dependency - per J. Kowal | bar: SEP 1 to OCT 2; MAR 1 to JUN 4
200 kV Gun and Wien tests | 2020-09-21 | 2020-10-14 | [40 empty] | Gun HV tests required before PSS upgrade begins | bar: SEP 3 to OCT 2
Beamline removal | 2020-10-01 | 2020-10-31 | [40 empty] | On track | bar: OCT 1 to OCT 4
Region 1 installation | 2020-11-01 | 2020-12-14 | [40 empty] | Ahead of plan (~50% built pre-SAD) | bar: NOV 1 to DEC 2
Region 2 installation | 2020-06-01 | 2020-04-15 | [40 empty] | Longest job, limited by a magnet delivery, trying to reduce ~4 wks | bar: SEP 1 to APR 2
Region 3 installation | 2020-10-08 | 2020-02-21 | [40 empty] | On track | bar: OCT 3 to FEB 3
HCO and commissioning | 2020-04-15 | 2020-05-30 | [40 empty] | 6 wks for HCO and beamline commissioning should be OK | bar: APR 3 to MAY 4
CEBAF HCO & Restore (S. Suhring) | 2020-05-24 | 2020-10-01 | [40 empty] | CEBAF Dependency - per S. Suhring | bar: MAY 4 to JUN 4
AIPINJ - Activity (detailed) | Start | End | SEP 1: SEP; OCT 1: OCT; NOV 1: NOV; DEC 1: DEC; JAN 1: JAN; FEB 1: FEB; MAR 1: MAR; APR 1: APR; MAY 1: MAY; JUN 1: JUN
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
INJ SEG PSS Availability (J. Kowal) | 2020-09-01 | 2020-10-15 | bar: SEP 1 to OCT 2; MAR 1 to JUN 4
200 kV Gun and Wien tests | 2020-09-21 | 2020-10-14 | bar: SEP 3 to OCT 2
Gun - HV condition tee, test Wien to 15 kV | 2020-09-21 | 2020-09-30 | bar: SEP 3
Gun - Vent Gun, swap cathodes, bake | 2020-10-01 | 2020-10-07 | bar: SEP 4 to OCT 1
Gun - HV condition tee+shed cathode | 2020-10-08 | 2020-10-14 | bar: OCT 2
Beamline removal | 2020-10-01 | 2020-10-31 | bar: OCT 1 to OCT 4
Vac - Early 1I (Y) vacuum removal | 2020-10-01 | 2020-10-14 | bar: OCT 1 to OCT 2
Vac - 2I, 1I, 0I laser box disconnects | 2020-10-15 | 2020-10-21 | bar: OCT 3
Vac - Vent/remove 2I, 1I, 0I beam line | 2020-10-22 | 2020-10-31 | bar: OCT 4
Region 1 installation | 2020-11-01 | 2020-12-14 | bar: NOV 1 to DEC 2
Vac - Complete rebuild of Y | 2020-11-01 | 2020-11-07 | bar: NOV 1
Vac - Install/align beamline Gun, 2I, Y | 2020-11-01 | 2020-11-14 | bar: NOV 1 to NOV 2
Region 1 (Gun, 2I) bake | 2020-11-15 | 2020-11-30 | bar: NOV 3 to NOV 4
Region 1 reconnects | 2020-12-01 | 2020-12-14 | bar: DEC 1 to DEC 2
Region 2 installation | 2020-06-01 | 2020-04-15 | bar: SEP 1 to APR 2
Prebuncher - fab | 2020-06-01 | 2020-10-30 | bar: SEP 1 to OCT 4
Prebuncher - testing | 2020-11-01 | 2020-11-30 | bar: NOV 1 to NOV 4
Prebuncher - on girder | 2020-12-01 | 2020-12-15 | bar: DEC 1 to DEC 2
FG solenoids on girder | 2020-12-01 | 2020-12-15 | bar: DEC 1 to DEC 2
Wiens - Modify/clean Wien vacuum chamber | 2020-10-21 | 2020-11-14 | bar: OCT 4 to NOV 2
Wiens - Assemble/map Wien magnet | 2020-11-15 | 2020-11-30 | bar: NOV 3 to NOV 4
Wiens - Finalize electrodes | 2020-12-01 | 2020-12-14 | bar: DEC 1 to DEC 2
Wiens - Complete S&A assembly | 2020-12-14 | 2020-01-07 | bar: DEC 3 to JAN 1
Wiens - Test HV | 2020-01-08 | 2020-01-21 | bar: JAN 2 to JAN 3
Wiens - On girder | 2020-01-22 | 2020-02-07 | bar: JAN 4 to FEB 1
Wien cross - build new viewers | 2020-11-21 | 2020-12-21 | bar: NOV 4 to DEC 3
Wien cross - quads arrive, QA | 2020-12-22 | 2020-01-14 | bar: DEC 4 to JAN 2
Wien cross - add quads, weld flanges | 2020-01-15 | 2020-01-31 | bar: JAN 3 to JAN 4
Wien cross - map quads | 2020-02-01 | 2020-02-14 | bar: FEB 1 to FEB 2
Wien cross - final assembly | 2020-02-15 | 2020-02-28 | bar: FEB 3 to FEB 4
Region 2 girder install/align | 2020-03-01 | 2020-03-14 | bar: MAR 1 to MAR 2
Region 2 girder bake | 2020-03-15 | 2020-03-31 | bar: MAR 3 to MAR 4
Region 2 reconnects | 2020-04-01 | 2020-04-15 | bar: APR 1 to APR 2
Region 3 installation | 2020-10-08 | 2020-02-21 | bar: OCT 3 to FEB 3
A1/A2 - welded cubes ready/clean | 2020-10-08 | 2020-10-14 | bar: OCT 3 to OCT 4
A1/A2 - MHD coils arrives | 2020-10-23 | 2020-11-07 | bar: OCT 4 to NOV 1
A1/A2 - MHD assembly/mapping | 2020-11-08 | 2020-11-14 | bar: NOV 2
A1/A2 - vacuum aperture assembly & alignment | 2020-11-15 | 2020-11-30 | bar: NOV 3 to NOV 4
A1/A2 - on girder | 2020-12-01 | 2020-12-14 | bar: DEC 1 to DEC 2
A1/A2 - remaining girder assembly | 2020-12-15 | 2020-01-07 | bar: DEC 3 to JAN 1
Region 3 girder - install to tunnel | 2020-01-08 | 2020-01-21 | bar: JAN 2 to JAN 3
Region 3 girder - bake | 2020-01-22 | 2020-02-07 | bar: JAN 4 to FEB 1
Region 3 reconnects | 2020-02-08 | 2020-02-21 | bar: FEB 2 to FEB 3
HCO and commissioning | 2020-04-15 | 2020-05-30 | bar: APR 3 to MAY 4
HCO w/o beam | 2020-04-15 | 2020-04-21 | bar: APR 3
Commission Week #1 - Gun | 2020-04-22 | 2020-04-30 | bar: APR 4
Commission Week #2 - Setup to chopper | 2020-05-01 | 2020-05-07 | bar: MAY 1
Commission Week #3 - Setup to chopper | 2020-05-08 | 2020-05-14 | bar: MAY 2
Commission Week #4 - Setup to FC2 | 2020-05-15 | 2020-05-21 | bar: MAY 3
Commission Week #5 - Wien/Spin | 2020-05-22 | 2020-05-30 | bar: MAY 4
CEBAF HCO & Restore (S. Suhring) | 2020-05-24 | 2020-10-01 | bar: MAY 4 to JUN 4
CEBAF HCO (S. Suhring) | 2020-05-24 | 2020-06-07 | bar: MAY 4 to JUN 1
CEBAF Restore (S. Suhring) | 2020-06-07 | 2020-06-21 | bar: JUN 2 to JUN 3
Start Physics (S. Suhring) | 2020-06-21 | 2020-10-01 | bar: JUN 4