## Slide 1: UITF Project Status Meeting
Matt Poelker
August 31, 2015

## Slide 2: Outline
  Purpose: to inform Lab Leadership of the UITF status
  Action Items (from previous meetings)
Project Update
  Progress Update
  Milestones Update
  Budget Update
  Highlights & Concerns
  Next meeting agenda
Notes: RW=Roy Whitney

## Slide 3
To refresh your memory…
What we started with…
UITF as imagined

## Slide 4
Action Items – From July 31, 2015 Minutes
Discussion Notes:
Emphasis was made to ensure the UITF area ODH analysis includes a Cryo assessment. Dick Owen, EHS&Q, will contact Mat Wright, Cryo to go over the layout and address ventilation concerns. Worst case scenario of ~1,500 liters from HDIce plus 400 liters from ¼ CM. But Will O. points out that the cryo lines will drive the capacity for defining a worst case scenario (i.e., the CTF represents a bigger helium supply).
Milestones Update slide. Mont would like Andy to schedule out what Physics needs to complete prior to going into the UITF. Andy mentioned 1 of 3 sets of targets would be ready. He needs about 3 months of work in the cave before the August 2016 beam to HDice. Matt describes their group’s plan to operate the ITF at ~33% in support of HDIce in the early days, but then hopes that Accel Ops would take over. Andy indicates that further discussion is needed on the ops plans.
Schedule Ramifications slide: Plan work towards the Jan 2016 milestone of ¼ CM commissioning (no beam).
Notes: RW=Roy Whitney

## Slide 5
Action Items – From July 31, 2015 Minutes
Issues & Concerns:
CTF capacity to run 3 LHe Users: meetings being held to evaluate path forward. J. Preble has the lead and action item from the P&C meeting.
Andrew wondered if the UITF should get all the new parts. Perhaps the new parts could be installed in the machine and the older parts be used in the UITF.
New Action Items:
M. Poelker/W. Akers: create a detailed schedule with milestones that can be updated during each meeting. Work in progress. Goal is to show progress during each update meeting. A simple gantt chart would work.
M. Poelker: Add an Estimate to Complete (ETC) slide to the monthly briefing. Develop a “Spend Profile”, particularly for procurements, to understand when funds are needed.
A. Sandorfi/W. Akers: prepare a schedule of activities for HDIce to complete before the Aug 2016 beam to HDIce.
Notes: RW=Roy Whitney

## Slide 6: Highlights
  Major components
  Facilities
  Engineering
    Mech Design
    Cryo
    Safety Systems
    I&C
    DC Power
    Low Level RF systems
    High Power RF
    Survey & Alignment
  SRF
    Commission with RF
  Operations
    Network and communications
Green means we can see progress

## Slide 7: Highlights
  Major components
  Source Group
    Reliable 350kV ops
    Beam to cup in front of ¼ cm
    Beam to cup in front of HDIce
  EHSQ
    Shielding approval
    Global hazard review
    FSAD
    Accel Readiness Review
    Commissioning Plan
  HDIce
    Installation at Cave
    Beam on HDIce
Green means we can see progress

## Slide 8
Cave 1 cleared out

## Slide 9
…and then filled back up
Unistrut added to walls for utilities, LCW piping being installed
keV beamline girders in house
S&A checked monuments, identified gun and girder locations

## Slide 10: Rack layout now more clearly defined
Consensus on layout
Working with system owners to finalize electrical requirements
Build it, populate the racks

## Slide 11
Move these racks here
Top of cave cleared out
Installed LCW lines
Building rack platform

## Slide 12
Jib crane removal was completed on 8/25/15.
Access Stair purchase order issued 8/18/15. Preconstruction meeting held 8/20/15. Shop drawings due 9/4/15, with installation scheduled for completion by 9/25/15.
Control Room carpet, Dennis met with Tuskegee Contracting on 8/26/15 to review job. They will provide the labor, we provide materials. Will have labor quote by 8/28/15. Estimate completion date of 9/9/15.
Leo Meire working with installation Group, LCW piping complete 9/15/15.
For Cave 1 electrical work, schedule as follows: Electrical drawings in progress and should be complete 9/4/15. Complete technical and ESH reviews, send purchase req to procurement 9/18/15. Contractor site visit 9/25/15 with bids due 10/2/15. Award first week of October, completion date will depend on panel lead time, but tentative date is 11/6/15.
Facilities updated cost estimates: $307k direct procurement, plus 43 PW labor. Original estimate $300k total, procurement + labor.
Status Facilities Tasks

## Slide 13
Status Cryo
Related to ¼ Cryomodule
Drawings complete within 6 weeks (October 8, 2015)
Plumbing installed by Feb 1, 2016
They prefer we provide a keep-out space during installation, but we would like to start building beamline…
Cryo didn’t considered computer controls…resources are available, but added cost
Related to HDIce
Must get to know HDIce, to design warm return
Related to ODH assessment
LERF building 18 vault assigned OHD0 because of two 12” diameter vent pipes to outside. UITF is more “holy”

## Slide 14
Simple ODH solution? vent pipes
Large entry/exit with chain-link gate
Install elbow-shaped vent pipes inside pre-cast concrete
Can Cryo/EHS&Q specify vent dimensions? How many?
Radcon must approve from shielding perspective
Two 30” vent pipes in Cave1
Six 10” dia. cable penetrations

## Slide 15: Shaun Gregory has started the MeV beamline design
Contractor Forrest Ellingsworth wrapping up details of keV beamline

## Slide 16
Enough Space?
Enough Space?
The chicane dictates 11 quads to provide a tight and round beam at HDIce, does this leave enough space for HDIce? Consider raster and beam dump requirements
Physics Division should provide accurate HDIce model, Shaun needs a Physics Designer POC

## Slide 17
The chicane dictates 10 quads to provide a tight round beam at HDIce, does this leave enough space for HDIce? raster and beam dump
Physics Division to provide accurate HDIce model, Shaun needs a Physics Designer POC
87”
Need to agree on height soon, as this affects many things

## Slide 18
Notes: Interior Page Design 2

## Slide 19
Combine the two features that provided incremental success: shed and doped insulator
Next test late September

## Slide 20
“Shed” triple-point protection
Doped insulator
SF6
R350 epoxy receptacle
Combination of doped insulator and shed, SF6 and epoxy receptacle, plus added length
Yan Wang has modeled the shed, a good design…
…then in October

## Slide 21: Milestones Update
WBS | Item | Milestone Description | Start Date | Projected Finish | % Complete | Days Float? | Change (%) | Change (Days)
1.04.xxx | Facilities | Civil work complete | 6-4-15 | Feb 2016 | 10% |  |  | 
 | Gun | Demonstrate gun ok at 350 kW at FEL GTS |  | Dec 2015 | 80% |  |  | 
 | CM | Commission cold ¼ CM, no beam |  | Jan 2016 | 10% |  |  | 
 |  | Beam from Gun to Cup in front of ¼ CM |  | Mar 2016 | 10% |  |  | 
 |  | Beam thru ¼ @ MeV energy delivered to cup in front of HDIce |  | Jun 2016 | 0 |  |  | 
 |  | Beam to HDIce |  | Aug 2016 | 0 |  |  | 

## Slide 22: Schedule Ramifications
  Current status:
    Utility work is key focus now, particularly electricity to racks
    Source group starting to put keV beamline together
    ODH assessment must be completed soon, for Tom Renzo to make progress on Cave2 structural design
  Next month activities (September)
    LCW complete
    Compressed air and GN2 complete
    Electrical requirements delivered to Jason/Facilities
    Stairway to top of Cave1 installed
    ODH assessment complete, ideally with ODH0 assignment
    Voltage applied to gun at GTS, plan Y
    MeV beamline design complete to 80%, done with contractor

## Slide 23: Schedule Ramifications
  In two months (October):
    Facilities working on electricity to racks
    Klystron rack finished, Seidman building control panel
    Apply high voltage to new gun design at GTS, plan Z
    Renzo working on Cave2, precast and bracing
    Move more shield blocks into place. Build as much of Cave2 perimeter as possible
  Recall, next big milestone…commission ¼ CM (no beam), scheduled for Jan. 2016 (cryo, ODH, LL and HP RF, software, adequate shielding, EHS&Q approvals)

## Slide 24: Schedule Ramifications
  Commission ¼ CM (no beam), scheduled for Jan 2016
    Facilities – electricity to racks by Nov 2015
    Control room – complete by Nov 2015, with computer terminals
    SRF checkout of ¼ CM present condition – complete Nov 2015
    Low Level RF – Hovater and Seidman have provided MO and LL RF control boards by Dec 2015
    High Power RF – klystron chassis and controls complete by Dec 2015
    Network controls (IOCs) – complete by Dec 2015
    Software control of RF – complete by Jan 2016
    Facilities - adequate shielding (Cave2 with a roof) – Feb 2016
    Cryo - plumbing to ¼ CM and controls complete Feb 2016
    ODH - SSG installed permanent system by Feb 2016, or we are using portable system from CEBAF
    EHS&Q approvals…

## Slide 25: Schedule Ramifications
  Commission ¼ CM (no beam), scheduled for Feb 2016
    Electric/FM – 150 k$
    Control room – -
    SRF checkout of ¼ CM present condition – -
    Low Level RF – 25 k$
    High Power RF – 56 k$
    Network controls – -
    Software control of RF – -
    adequate shielding (Cave2 with a roof) – 95 k$
    Cryo – 90 k$
    ODH - SSG 6 k$
    EHS&Q approvals…
    Total 422 k$

## Slide 27: FY16 Procurements?
 | ~ required | spent in FY14 FY15 | To purchase in FY16 | 
Facilities: | 300 | 56.2 | 245 | 
Cryo | 90.8 | 0 | 90.8 | waiting for update
RF | 252.5 | 121.4 | 131.1 | 
Gun | 451.2 | 265.5 | 130 | includes beamline components + contract designer
I&C | 219.5 | 7.6 | 211.9 | Hope to reduce this number using PLC technology
SSG | 45.7 | 1 | 44.7 | 
DC power | 144.5 | 100 | 8 | Trim cards…
Magnets | 120 | 119.3 | 0 | shop to make quads, assumed 100k but could be less Still need three dipoles
Network | 58 | 58 | 0 | 
Total | 1682 | 671 | 862 | Of course, hope the number comes in lower: 750 k$

## Slide 28: Issues & Concerns
Schedule slip one month…
If it slips more, perhaps consider installing the new ¼ CM first (ready June, 2016). Commission HDIce and the new ¼ CM at same time (kill two birds with one stone)
CTF is not big enough to support three LHe Users. How to “park” the ¼ cryomodule?
  UITF (4 to 6 wks, 3 times per year)
  CMTF and LCLS II
  VTA
Groups are busy but I continue to be optimistic that work can get done opportunistically within project timeline. Facilities, Mech Design, Cryo, SSG, and Ops software have expressed most reservations

## Slide 29: Summary
Progress now becoming more obvious. By October, expect to see some beamline, with ¼ CM inside the cave, electronics racks above the cave….
Hope the Lab can continue funding at ~ FY15 level
We are being responsible with money and we are respectful of other JLab work priorities…

## Slide 30: Backup Slides
Backup slides from past meetings, P&C meetings

## Slide 31: Original vs Current Cost Estimate
Presented at UITF meeting May 13, 2015:
Total cost estimate. The specific allocations for FY15 and 16 are not correct
Original Est. by Hari Areti |  | FTEs | Labor | Proc | Total |  | Labor | Proc | Total | 
on 2-7-2014 | FY14 | 3.7 | 462.54 | 478.95 | 941.49 |  | 682.70 | 671.23 | 1,353.94 | 
 | FY15 | 2.5 | 312.08 | 557.10 | 869.18 |  | 465.00 | 830.07 | 1,295.07 | 
 | FY16 | 0 | - | - | - |  | - | - | - | 
 | Total | 6.2 | 774.62 | 1,036.05 | 1,810.66 |  | 1,333.458 | 1,501.306 | 2,649.011 | 
Revised Est. |  | FTEs | Labor | Proc | Total |  | Labor | Proc | Total | 
by Matt Poelker | FY14 | 1.2 | 160.32 | 189.48 | 349.80 |  | 233.08 | 274.29 | 507.37 | 47.6%
on 5-13-2015 | FY15 | 8.6 | 937.36 | 611.17 | 1,548.53 |  | 1,396.67 | 907.95 | 2,304.62 | 49.0%
 | FY16 | 7.9 | 940.39 | 881.33 | 1,821.72 |  | 1,422.80 | 1,333.46 | 2,756.26 | 51.3%
 | Total | 17.7 | 2,038.07 | 1,681.98 | 3,720.05 |  | 3,052.56 | 2,515.70 | 5,568.26 | 
Dfference from original estimate |  | (11.5) | (1,263.46) | (645.93) | (1,909.39) |  | (1,719.10) | (1,014.40) | (2,919.25) | 
Loaded $
Direct $

## Slide 32: Revised Estimates Breakdown
Original request to DOE: $2.6M (loaded)
Current estimate for completion: $5.6 M (loaded)
Delta increase of $2.9M (loaded)
Labor estimates
  Underestimated effort by 11.5 FTEs
  Increased labor by $1.7M (loaded)
Procurements
  Underestimated by ~$1M (loaded)
  Several sub-system components were not included in the original estimate and later determined were necessary to complete the scope

## Slide 33: Comparison Procurement Estimates (Direct $)
System | Prev | Now | Delta | Comment
Facilities | 305 | 300 | -5 | (numbers are Proc and Labor)
Safety System | 59 | 46 | -13 | 
RF Systems | 125 | 253 | +128 | rf control boards, klystron PS
Cryogenics | 40 | 91 | +51 | Pipe, heat exchanger
Polarized Source | 255 | 262 | +7 | Gun insulators, beamline parts
I&C | 131 | 220 | +89 | BPMs, viewers, picoammeters
DC Power | 0 | 145 | +145 | Trim cards and parts
Magnets | 58 | 120 | +62 | Addl. quads, correctors, dipoles
SRF | 50 | 0 | -50 | 
HDIce | 5 | 0 | -5 | 
Network, IOCs | 0 | 58 | +58 | 
CIS FY14 Actuals | 0 | 189 | +189 | FY14 actuals
Total | 1,028 | 1,684 | +656 | 

## Slide 34: FY14 and FY15 UITF Procurements
FY14 |  |  |  | FY15 |  |  | Addl. expected FY15 procurements | 
Solid Works CAD |  | 2.2 |  | Insulator flange | 1 |  | Contract Mech Designer | ~ 30
450kV HV power supply |  | 31.1 |  | bpm components | 7.6 |  | stairs | ~ 20
semiconducting R30 insulators |  | 52.6 |  | semiconducting R30 insulators_v2 | 22.3 |  | trim cards | ~100
gun HV chamber |  | 7.8 |  | Klystron HV power supply | 55.5 |  | quad magnets (machine shop) | 70 to 130
ion pumps |  | 15.1 |  | concrete wall removal | 32 |  | Chopper rf amplifiers (x2) | 44
beamline Y chamber |  | 5 |  | LLRF parts | 15.1 |  | water skid for chopper | 3
photocathode prep chamber |  | 4.5 |  | steering magnets | 19.3 |  | keV beamline support structure | 6.5
drill penetrations in concrete |  | 4.2 |  | SF6 tank | 11.3 |  | Addl. FY15 procurement total | 303.5
assorted |  | 3.9 |  | waveguide | 3.8 |  |  | 
Credit card |  | 21.8 |  | SSG sensor | 1 |  |  | 
Machine shop |  | 40.8 |  | assorted | 9.4 |  |  | 
total | 189 |  |  | total | 178.3 |  |  | 
FY14 + FY15 Procurements: 670.8
UITF Total Procurements 1682

## Slide 35: UITF – Upgrade Injector Test Facility
Deliverables/Milestones
    Beam on HDIce by August 2016 (nA current level at ~ 10 MeV)
Staffing
    Critical Skills needed NOW: Facilities, Cryo including ODH assessment, Mechanical Design, Safety System Group for ODH, Ops Software
Update since last meeting
    Monthly meetings with Mont, on-going
    Cave1 north concrete wall demolition complete
    Accelerator design sufficiently complete to start building the keV beamline
    Shaun Gregory has started the MeV beamline design
    Cave1 cleared out, ready for Survey and Alignment
  Consensus achieved on entry/exit labyrinth from shielding point of view
  We realized we might have unwanted ODH2 conditions. Mat Wright now performing formal ODH assessment, which will include recommendations (?). Suspect we must revisit Cave2 ceiling design, to provide a passive escape path for helium gas
  Stairway to top of Cave1 – PR has been awarded
  Carlos and Don Bullard are back – they can focus on 350kV gun
  Continued progress on “stretch goals”: RF control modules, trim cards, quad magnets, BPMs (and staying within FY15 budget)

## Slide 36: UITF – Upgrade Injector Test Facility
To-do list for next 30 days
  Setup the electronics racks above Cave1
    Agree on layout, RadCon to approve it
    Installation Group (Neal Wilson and company) to build it
    Need a temporary stairway to access the top of Cave
    Provide electrical requirements to Facilities/Jason Willoughby
  Obtain the formal ODH assessment, use it to provide Tom Renzo information relevant to Cave2 ceiling design. Modifications to Cave1 ceiling required?
  Facilities should remove utilities on Control Room exterior wall (window air conditioner, fire, electric), so that Walter Kehlner can move more concrete block into position to erect the perimeter of Cave2
  Installation Group to install unistrut along east wall, for attaching utilities. Installation Group and Facilities to begin attaching utilities to this wall: LCW, GN2, compressed air, electric, lighting, fire suppression
  Move the ¼ CM into Cave1 or Cave2
  Apply high voltage to gun with shed electrode at FEL Gun Test Stand
  Need to make some headway on Bob May’s EHS&Q task list

## Slide 37: UITF – Upgrade Injector Test Facility
Issues/Concerns that could affect on-time delivery
  Can Cryo provide plumbing soon? Begin work on He recovery system for HDIce? Want to leave space for them to do their work but also want to start “filling up the cave” now
  Designers in short supply
  Can SSG provide the ODH and PSS systems on schedule?
  Facilities end-date February 2016 could delay ¼ CM commissioning, gun HV conditioning, and intentional beam generation
  Impact on CTF, a new LHe User
Recommended Mitigation
  Purchase contract designer
  We can use portable ODH monitoring system for ¼ CM commissioning
  Temporary shield wall and OSP could provide a means to commission ¼ CM, condition gun and perhaps make 350kV beam without a completed UITF concrete enclosure and PSS?
  Preble, K. Davis, Cryo Group have started conversation related to oversubscribed CTF. However, near term solution is likely a scheduling solution.
  Timing is good for Ops Software, provided we (mostly) duplicate existing CEBAF software controls

## Slide 38: EHS&Q related tasks (from Bob May)
Global hazard review (can be documented in FSAD)
  Radiation source term, shielding design, assessment, approval, installation
  Final ODH assessment, with Cryo?
  Standard industrial hazards (electrical, fall protection, emergency egress, magnetic and RF field exposure, etc.)
FSAD update (Rev 8) incorporating hazards assessment and mitigations
ASE development and submittal (Rev 8) for TJSO approval
Commissioning Plan Development
(Internal or External?) Review of Commissioning Plan (CP)
Operations plan/procedure development (related to Accelerator Operations Directives? Borrow from and scale down LERF procedures?)
  Decision about type of ARR and who participates – external/internal/combo
Accelerator Readiness Review Plan Review (can be done with CP Review)
Work with SSG to implement PSS, RCD to implement CARMS
Conduct Hot Checkout (test all installed systems – ready for safe/effective ops)
Conduct ARR
Obtain TJSO permission to commission UITF (must include shileding effectiveness check, verification of safety device performance
Commissioning results report
Obtain TJSO permission to operate UITF
Hari has agreed to work on this

## Slide 39: Building the 350 kV Gun
Start with “dummy” electrodes and test different insulators and cathode screening electrode
Notes: Interior Page Design 2

## Slide 41
Approved Labyrinth and a plan for 100uA
Plus: augment ceiling shielding, maybe some restricted areas, and be generous with local shielding of dumps

## Slide 42
Today’s layout, ready to cut metal…..
Cryo lines hug the wall, waveguides on same side as cryo lines
Heat exchanger added to the mix, Rao says this will make things more efficient and stable
Design by Shaun Gregory

## Slide 43
Cryo lines compatible with old and new ¼ CM…
Looks similar to our “upgrade injector” front end