## Overview
ITFU Phase 1 Cost Overview
[5 empty] | Procurements (K$) | Labor
System | FY14 Procurements | FY14 Labor | Fy15 Procurements | Fy15 Labor | FY14+FY15 | FY14+Fy15
| k$ | Person-weeks | k$ | person-weeks
Infrastructure | 305 | 61 | 221 | 16 | 526 | 77
Beamline Layout | - | 4 | - |  |  | 4
Infrastructure | 305 | 53 | 150 | 5 | 455 | 58
Safety Systems |  |  | 36 | 8 | 36 | 8
Radiation Controls |  | 4 | 20 | 1 | 20 | 5
Fire Safety |  |  | 15 | 2 | 15 | 2
Section 1: High Voltage Gun to Aperture A2
Section 1 Total | 15 | 82.5 |  |  | 15 | 82.5
Beamline Elements | 15 | 68.5 |  |  | 15 | 68.5
Control Software | - | 14 |  |  |  | 14
Section 2: Warm RF acceleration - Aperture A2 to Capture
Capture Cavity | 40 | 37.5 | 114 |  | 154 | 37.5
Section 3: SRF Acceleration - End of Capture to End of 1/4 cryomodule
Quarter Cryomodule |  | 7.5 | 50 | 9.5 | 50 | 17
Section 4: End of 1/4 cryomodule to HDIce
Section 4 Total |  |  | 94 | 63.5 | 94 | 63.5
HDIce |  |  | 94 | 29.5 | 94 | 29.5
Shielding | - |  | - | 24 |  | 24
Infrastructure | - |  |  | 10 |  | 10
Total Beam to HDIce | 360 | 188.5 | 479 | 89
Labor Breakdown in Person-weeks for the entire project construction
Accelerator | Engineering | Facilities management | RadCon | Physics
108.5 | 90 | 22 | 5 | 52

## Labor
Phase I - Section 1, High Voltage Gun to Aperture A2
Task Type | Task | Person Weeks | [5 empty] | PIC
1. Infrastructure |  | Sci. | Eng. | Tech. | Comp. Sci | Other | Total
Beamline layout
| Component Layout | 2 |  |  |  | 2 | 4 | R. Kazimi
Infrastructure
| AC Power to the Area |  | 5 |  |  |  | 5 | P.Powers
| HVAC |  | 5 |  |  |  | 5 | R. Yasky
| Distribution of AC power to Instrumentation Racks |  |  | 20 |  |  | 20 | B. Shinault
| LCW to Chopper, capture, HPAs |  |  | 10 |  |  | 10 | P. Adderley
| Instrumentation Air along the beamline |  |  | 2 |  |  | 2 | P. Adderley
| Cryolines to 1/4 Cryo and to Hdice |  | 2 | 8 |  |  | 10 | D. Arenius
| Racks for High Power RF, LLRF and Control systems |  |  | 3 |  |  | 3 | O. Garza | other = designer
| Trim Racks |  |  | 3 |  |  | 3 | O. Garza
62
2. Safety Systems
PSS & MPS | Personnel Safety System Evaluation |  | 1 |  |  |  | 1 | K.Mahoney
| Personnel Safety System Design, includes ODH |  | 1 |  |  |  | 1 | K.Mahoney
| Personnels Safety System Installation |  |  | 2 |  |  | 2 | K.Mahoney
| Machine Protection System Design |  | 1 |  |  |  | 1 | K.Mahoney
| Machine Protection System Installation |  | 1 | 2 |  |  | 3 | K.Mahoney
Radiation Controls | Radiation Assessment |  | 4 |  |  |  | 4 | V. Vylet
| CARM Installation |  |  | 1 |  |  | 1 | D. Hamlet
Fire Safety | Fire Protection Evaluation |  | 1 |  |  |  | 1 | D. Kausch
| Fire Protection Installation |  | 1 |  |  |  | 1 | D. Kausch
[7 empty] | 15 |  | 77
Phase I - Section 1: High Voltage Gun to Aperture A2
1. Beamline Elements | HV Gun |  | 2 |  |  |  | 2 | J. Hansknecht
| Laser System |  | 22 |  |  |  | 22 | J. Hansknecht
| Diagnostics (BPMs, Viewers, Harps, Faraday Cup, BCMs) | [5 empty] | 4 | O. Garza
| CAMAC/VME crates and wiring |  |  | 7 |  |  | 7 | O. Garza
| Vacuum |  |  | 4 |  |  | 4 | P. Adderley
| Magnets |  |  | 4 |  |  | 4 | O. Garza
| Wien Filters |  |  | 3 |  |  | 3 | P. Adderley
| Polarimeter |  |  | 3 |  |  | 3 | P. Adderley
| Girder Design for chopper |  | 0.5 | 1 |  |  | 1.5 | M. Bevins
| Chopper |  |  | 6 |  |  | 6 | P. Adderley
| RF for Chopper |  | 1 | 4 |  |  | 5 | C. Hovater
| Beam Dump |  |  | 1 |  |  | 1 | P. Adderley
| Survey and Alignment |  | 2 | 4 |  |  | 6 | C. Curtis
2. Control Software | Design |  |  |  | 4 |  | 4 | P.Kjeldsen
| Installation |  |  | 10 |  |  | 10 | P.Kjeldsen
[7 empty] | 82.5 |  | 82.5
Phase I - Section 2: Warm RF acceleration - Aperture A2 to Capture
1. Beamline | Girder design for capture |  | 1 | 4 |  |  | 5 | M. Bevins
Capture Cavity
| Design | 4 | 2 |  |  | 4 | 10 | R. Rimmer
| Fabrication | 2 | 2 | 4 |  |  | 8 | R. Rimmer
| Testing | 1 | 1 | 4 |  |  | 6 | R. Rimmer
| RF for Capture |  | 0.5 | 1 |  |  | 1.5 | C. Hovater
| Beam Dump |  |  | 1 |  |  | 1 | P. Adderley
| Survey and Alignment |  | 2 | 4 |  |  | 6 | C. Curtis
[7 empty] | 32.5 |  | 37.5
Phase I - Section 3: SRF Acceleration - End of Capture to End of 1/4 cryomodule
1. 1/4 cryomodule | 1/4 Cryo |  | 2 | 4 |  |  | 6 | J. Preble
| RF for 1/4 Cryo |  | 0.5 | 1 |  |  | 1.5 | C. Hovater
| LLRF Controls |  | 0.5 | 1 |  |  | 1.5 | C. Hovater
| Cryoline hook up |  | 0.5 | 1 |  |  | 1.5 | J. Preble
| Commissioning |  | 2 | 2 |  |  | 4 | J. Preble
| Survey and Alignment |  | 0.5 | 1 |  |  | 1.5 | C. Curtis
| Beam Dump |  |  | 1 |  |  | 1 | P. Adderley
[7 empty] | 17 |  | 17
Phase I - Section 4: End of 1/4 cryomodule to HDIce
Hdice | Installation | [5 empty] | 20 | A. Sandorfi
| Commissioning | [5 empty] | 8 | A. Sandorfi
| Survey and Alignment |  | 0.5 | 1 |  |  | 1.5 | C. Curtis
[7 empty] | 29.5 |  | 29.5
Phase I - Shielding
Shielding
| Shield Block Prepartion |  |  | 4 |  | 4 | 8 | W. Kellner
| Shield Block Installation |  |  | 8 |  | 8 | 16 | W. Kellner
[7 empty] | 24 |  | 24
Civil Construction
Infrastructure | Sesimic Evaluation for Shield Block Installation |  | 5 |  |  |  | 5 | S. Chandra
| Removal of Wall and Labyrinth in Test Cave |  | 5 |  |  |  | 5 | R. Sperlazza | 10
10
[8 empty] | Total | 277.5
[5 empty] | 44 | weeks/person year |  |  | 6.3068 | years
[5 empty] | 160 | K/person year |  |  | 1009.0909 | k$

## Procurement
Only items that are not available at the lab and are needed to be procured are listed
Task Type | Item | Cost in K$ | PIC |  | Color Code
1. Infrastructure | [5 empty] | FY14 Scope
Infrastructure
| AC power distribution | 150 | P.Powers |  | Total Procurements (K$) |  | 360
| HVAC system: $150 K | 150 | R. Yasky
| Wall removal (includes the stub wall in the cave) | 100 | Facilties
| Cryoline components | 40 | D. Arenius
| Instrumentation Air along the beamline | 5 | P. Adderley
| LCW | 10 | P. Adderley
455
2. Safety Systems
PSS & MPS | Personnel Safety System- gates, electronics, ODH heads | 30 | K.Mahoney
| MPS Electronics -3 BLMs $2K/unit | 6 | K.Mahoney
36
Radiation Controls | CARM base unit with 3 heads | 20 | D. Hamlet | 20
Fire Safety | Fire Protection System | 15 | D. Kausch | 15
Phase I - Section 1: HighVoltage Gun to Aperture A2
1. Beamline Elements | HV Gun |  | J. Hansknecht
| Laser System |  | J. Hansknecht
| Diagnostics (BPMs, Viewers, Harps, Faraday Cup, BCMs) |  | O. Garza
| CAMAC/VME crates and wiring |  | O. Garza
| Vacuum pumps |  | P. Adderley
| Magnets |  | O. Garza
| Wien Filters |  | P. Adderley
| Polarimeter |  | P. Adderley
| Girder for chopper | 15 | M. Bevins
| Chopper |  | P. Adderley
| Beam Dump |  | P. Adderley
15
Phase I - Section 2: Warm RF acceleration - Aperture A2 to Capture
1. Beamline | Girder for capture | 15 | M. Bevins
Capture Cavity | Capture Cavity | 25 | R. Rimmer
| 6 Lenses @ $10K/unit | 60 | P. Adderley
| 6 Correctors @ $1K/unit | 6 | P. Adderley
| 5 Viewers @ $7K/unit | 35 | P. Adderley
| 1 Dipole Magnet | 10 | P. Adderley
| 1 BPM @$3K/unit | 3 | O. Garza
154
Phase I - Section 3: SRF Acceleration - End of Capture to End of 1/4 cryomodule
1. 1/4 cryomodule | 1/4 Cryo |  | J. Preble
| RF components (waveguides, filters, circulators) | 50 | C. Hovater
| LLRF Controls |  | C. Hovater
| Beam Dump |  | P. Adderley
50
Phase I - Section 4: End of 1/4 cryomodule to HDIce
1. HDice | 2 stands @$20K/unit | 20 | M. Bevins
| 2 focusing quads @$10K/unit | 20 | P. Adderley
| 4 Correctors @ $1k/unit | 4 | P. Adderley
| 1 Viewer @ $7K/unit | 7 | P. Adderley
| 2 Beam Position Monitor @$3 K/unit | 6 | O. Garza
| 1 Harp @ $17 K/unit | 17 | O. Garza
| 2 Beam Position Monitors @$3 K/unit | $6k | O. Garza
| 1 Beam current Cavity | 15 | O. Garza
| 1 Raster System @ $20K/unit | 5 | A. Sandorfi
94
|  | Procurement costs (K$) |  | 839

## Labor Fy14
Task Type | Task | Person Weeks | [5 empty] | PIC |  | Color Code
1. Infrastructure |  | Sci. | Eng. | Tech. | Comp. Sci | Other | Total |  |  |  | FY14 Scope
Beamline layout | [10 empty] | FY15 Scope
| Component Layout | 2 |  |  |  | 2 | 4 | R. Kazimi
Infrastructure
| AC Power to the Area |  | 5 |  |  |  | 5 | P.Powers
| HVAC |  | 5 |  |  |  | 5 | R. Yasky
| Distribution of AC power to Instrumentation Racks |  |  | 20 |  |  | 20 | B. Shinault
| LCW to Chopper, capture, HPAs |  |  | 10 |  |  | 10 | P. Adderley
| Instrumentation Air along the beamline |  |  | 2 |  |  | 2 | P. Adderley
| Cryolines to 1/4 Cryo and to Hdice |  | 2 | 8 |  |  | 10 | D. Arenius
| Racks for High Power RF, LLRF and Control systems |  |  | 3 |  |  | 3 | O. Garza
| Trim Racks |  |  | 3 |  |  | 3 | O. Garza | Acc | Eng | Fac. | RadCon | Phy
[7 empty] | 62 |  | 16 | 36 | 5
2. Safety Systems | [10 empty] | 5
PSS & MPS | Personnel Safety System Evaluation |  | 1 |  |  |  | 1 | K.Mahoney
| Personnel Safety System Design, includes ODH |  | 1 |  |  |  | 1 | K.Mahoney
| Personnels Safety System Installation |  |  | 2 |  |  | 2 | K.Mahoney
| Machine Protection System Design |  | 1 |  |  |  | 1 | K.Mahoney
| Machine Protection System Installation |  | 1 | 2 |  |  | 3 | K.Mahoney
Radiation Controls | Radiation Assessment |  | 4 |  |  |  | 4 | V. Vylet
| CARM Installation |  |  | 1 |  |  | 1 | D. Hamlet
Fire Safety | Fire Protection Evaluation |  | 1 |  |  |  | 1 | D. Kausch
| Fire Protection Installation |  | 1 |  |  |  | 1 | D. Kausch
[7 empty] | 15 |  | 0 | 0 | 0 | 4 | 0
Phase I - Section 1: HighVoltage Gun to Aperture A2 | [9 empty] | 8 | 2 | 1
1. Beamline Elements | HV Gun |  | 2 |  |  |  | 2 | J. Hansknecht
| Laser System |  | 22 |  |  |  | 22 | J. Hansknecht
| Diagnostics (BPMs, Viewers, Harps, Faraday Cup, BCMs) | [5 empty] | 4 | O. Garza
| CAMAC/VME crates and wiring |  |  | 7 |  |  | 7 | O. Garza
| Vacuum |  |  | 4 |  |  | 4 | P. Adderley
| Magnets |  |  | 4 |  |  | 4 | O. Garza
| Wien Filters |  |  | 3 |  |  | 3 | P. Adderley
| Polarimeter |  |  | 3 |  |  | 3 | P. Adderley
| Girder Design for chopper |  | 0.5 | 1 |  |  | 1.5 | M. Bevins
| Chopper |  |  | 6 |  |  | 6 | P. Adderley
| RF for Chopper |  | 1 | 4 |  |  | 5 | C. Hovater
| Beam Dump |  |  | 1 |  |  | 1 | P. Adderley
| Survey and Alignment |  | 2 | 4 |  |  | 6 | C. Curtis
2. Control Software | Design |  |  |  | 4 |  | 4 | P.Kjeldsen
| Installation |  |  | 10 |  |  | 10 | P.Kjeldsen
[7 empty] | 82.5 |  | 55 | 27.5 | 0 | 0 | 0
Phase I - Section 2: Warm RF acceleration - Aperture A2 to Capture
1. Beamline | Girder design for capture |  | 1 | 4 |  |  | 5 | M. Bevins
Capture Cavity
| Design | 4 | 2 |  |  | 4 | 10 | R. Rimmer
| Fabrication | 2 | 2 | 4 |  |  | 8 | R. Rimmer
| Testing | 1 | 1 | 4 |  |  | 6 | R. Rimmer
| RF for Capture |  | 0.5 | 1 |  |  | 1.5 | C. Hovater
| Beam Dump |  |  | 1 |  |  | 1 | P. Adderley
| Survey and Alignment |  | 2 | 4 |  |  | 6 | C. Curtis
[7 empty] | 37.5 |  | 25 | 12.5 | 0 | 0 | 0
Phase I - Section 3: SRF Acceleration - End of Capture to End of 1/4 cryomodule
1. 1/4 cryomodule | 1/4 Cryo |  | 2 | 4 |  |  | 6 | J. Preble
| RF for 1/4 Cryo |  | 0.5 | 1 |  |  | 1.5 | C. Hovater
| LLRF Controls |  | 0.5 | 1 |  |  | 1.5 | C. Hovater
| Cryoline hook up |  | 0.5 | 1 |  |  | 1.5 | J. Preble
| Commissioning |  | 2 | 2 |  |  | 4 | J. Preble
| Survey and Alignment |  | 0.5 | 1 |  |  | 1.5 | C. Curtis
| Beam Dump |  |  | 1 |  |  | 1 | P. Adderley
[7 empty] | 17 |  | 6 | 1.5 | 0 | 0 | 0
Phase I - Section 4: End of 1/4 cryomodule to HDIce | [8 empty] | 6.5 | 3
Hdice | Installation | [5 empty] | 20 | A. Sandorfi
| Commissioning | [5 empty] | 8 | A. Sandorfi
| Survey and Alignment |  | 0.5 | 1 |  |  | 1.5 | C. Curtis
29.5
Phase I - Shielding | [9 empty] | 1.5 |  |  | 28
Shielding
| Shield Block Prepartion |  |  | 4 |  | 4 | 8 | W. Kellner
| Shield Block Installation |  |  | 8 |  | 8 | 16 | W. Kellner
24
Civil Construction | [12 empty] | 24
Infrastructure | Sesimic Evaluation for Shield Block Installation |  | 5 |  |  |  | 5 | S. Chandra
| Removal of Wall and Labyrinth in Test Cave |  | 5 |  |  |  | 5 | R. Sperlazza
[7 empty] | 10 |  |  |  | 10
277.5
| FTE Weeks | Acc. | Eng. | Fac. | Rad.con | Phys.
|  | 108.5 | 90 | 22 | 5 | 52 |  | 277.5
| Fy14 Labor | 102 | 77.5 | 5 | 4 | 0 |  | 188.5
| FTE @ 44 Weeks/person | 2.3182 | 1.7614 | 0.11364 | 0.090909 | 0 |  | 4.2841
|  | 6.5 | 12.5 | 7 | 1 | 52 |  | 80.7955
|  | 0.14773 | 0.28409 | 0.15909 | 0.022727 | 1.1818 |  | 1.7955

## Procurement Fy14
Only items that are not available at the lab and are needed to be procured are listed
Task Type | Item | Cost in K$ | PIC |  | Color Code
1. Infrastructure | [5 empty] | FY14 Scope
Infrastructure | [5 empty] | Fy15 Scope
| AC power distribution | 150 | P.Powers |  | FY14 Procurements (K$) |  | 360
| HVAC system: $150 K | 150 | R. Yasky |  | FY15 Procurements (K$) |  | 479
| Wall removal (includes the stub wall in the cave) | 100 | Facilties
| Cryoline components | 40 | D. Arenius
| Instrumentation Air along the beamline | 5 | P. Adderley
| LCW | 10 | P. Adderley
455
2. Safety Systems
PSS & MPS | Personnel Safety System- gates, electronics, ODH heads | 30 | K.Mahoney
| MPS Electronics -3 BLMs $2K/unit | 6 | K.Mahoney
36
Radiation Controls | CARM base unit with 3 heads | 20 | D. Hamlet | 20
Fire Safety | Fire Protection System | 15 | D. Kausch | 15
Phase I - Section 1: HighVoltage Gun to Aperture A2
1. Beamline Elements | HV Gun |  | J. Hansknecht
| Laser System |  | J. Hansknecht
| Diagnostics (BPMs, Viewers, Harps, Faraday Cup, BCMs) |  | O. Garza
| CAMAC/VME crates and wiring |  | O. Garza
| Vacuum pumps |  | P. Adderley
| Magnets |  | O. Garza
| Wien Filters |  | P. Adderley
| Polarimeter |  | P. Adderley
| Girder for chopper | 15 | M. Bevins
| Chopper |  | P. Adderley
| Beam Dump |  | P. Adderley
15
Phase I - Section 2: Warm RF acceleration - Aperture A2 to Capture
1. Beamline | Girder for capture | 15 | M. Bevins
Capture Cavity | Capture Cavity | 25 | R. Rimmer
| 6 Lenses @ $10K/unit | 60 | P. Adderley
| 6 Correctors @ $1K/unit | 6 | P. Adderley
| 5 Viewers @ $7K/unit | 35 | P. Adderley
| 1 Dipole Magnet | 10 | P. Adderley
| 1 BPM @$3K/unit | 3 | O. Garza
154
Phase I - Section 3: SRF Acceleration - End of Capture to End of 1/4 cryomodule
1. 1/4 cryomodule | 1/4 Cryo |  | J. Preble
| RF components (waveguides, filters, circulators) | 50 | C. Hovater
| LLRF Controls |  | C. Hovater
| Beam Dump |  | P. Adderley
50
Phase I - Section 4: End of 1/4 cryomodule to HDIce
1. HDice | 2 stands @$20K/unit | 20 | M. Bevins
| 2 focusing quads @$10K/unit | 20 | P. Adderley
| 4 Correctors @ $1k/unit | 4 | P. Adderley
| 1 Viewer @ $7K/unit | 7 | P. Adderley
| 2 Beam Position Monitor @$3 K/unit | 6 | O. Garza
| 1 Harp @ $17 K/unit | 17 | O. Garza
| 2 Beam Position Monitors @$3 K/unit | $6k | O. Garza
| 1 Beam current Cavity | 15 | O. Garza
| 1 Raster System @ $20K/unit | 5 | A. Sandorfi
94
|  | Procurement costs (K$) |  | 839