## Slide 1: Jefferson Lab – Compton Transmission Polarimeter
Summary of Progress
June 29, 2022
Riad, Joe, Eric, and Matt

## Slide 2: Achievements, Milestones and Timeline
FY22 Q2 (Jan, Feb, Mar)
  IJCLab is responsible for detector design w/ JLab backfilling long-lead components as necessary
  Portable DAQ parts are ordered and/or onsite
  One set of Radiator is ready, need to fabricate second radiator and two Collimators
FY22 Q3: (Apr, May, June)
  Design of magnet with iron core is completed – (2) steel core fabricated, coil winding is underway
  Mechanical design of polarimeter for UITF is nearly complete, finalize w/ BNL then fabricate both
  Complete Portable DAQ
  Installed Wien filter and 200 kV Mott polarimeter – Commission both in July, to calibrate Compton
FY22 Q4 (Jul, Aug, Sep):
  Assemble polarimeter (4 weeks)
  Install polarimeter at UITF (2 weeks)
  Beam tests (2 weeks)
    Commission new beam line
    Calibrate Compton polarimeter against Mott
FY23 Q1 (Oct, Nov, Dec):
  Aim to deliver to BNL
Budget:
  Spent: $190k
  Remaining: $210k
Expecting labor and M&S burn rates to remain high next 6 months

## Slide 3: Polarimeter at IUTF
Here

## Slide 4: Compton Transmission Polarimeter
Detector
Magnet
Collimator
Radiator
Shaun Gregory, Gary Hays

## Slide 5: Magnet Progress
Magnet specifications defined and documented (PMAG0000-0011-S000)
Magnet coil and core geometry developed using TOSCA and MAXWELL
  Peak field 2.2 Tesla
  1005 Steel Core, Flange, Sleeve
Detailed coil layout and manufacturing drawings developed
  Conductor (2.2 mm x 2.2 mm) and insulation dimensions defined
  Coil manufacturing vendor identified and conductor purchased
Detailed core drawings being developed
  1005 Steel material on-hand
Magnet power supply (MPS) requirements defined. Power supplies ordered.
  MPS with 0-10Vdc, 15Adc (150W) 2 quadrant
Compton Magnet Design Overview
Sleeve
Core
Coil
Flange
Probir G, Sandesh G, Joe M, Mike B, Sean G

## Slide 6: Magnet Design
Field variation along the core length at radius of 0, 5 mm, 10 mm, & 12.5 mm. Field on Y axis (Tesla) and core length on X axis (mm)
B field magnitude and vector plots in MAXWELL
Coil layout & Composition
Magnet Manufacturing drawing

## Slide 7
The photon detector part is a cylindrical BGO crystal 15 cm long with a 5 cm diameter previously tested at IJCLab.
The provider is Alpha Spectra Inc. (ASI) (fjwxals@alphaspectra.com).
Shipped two ready-to-install crystals to JLab.
Crystal reception @ JLab (this week)
Integration in the detector assembly
137Cs experimental spectra
Crystals have been tested at ASI and IJCLab to have a 8.5% resolution at 662 keV.
Christine Le Galliard, Thi Nguyen Trung, Eric Voutier
Detector

## Slide 8
Photomultiplier
The selected photomultiplier tube is the R2154-02 from Hamamatsu. Jlab ordered four PMTs.
The PMT socket E678-14W ordering is in progress at IJCLab.
The production of silicon pads for crystal/PMT optical coupling is in progress at IJCLab.
PMT reception @ JLab (? weeks)
Test/troubleshooting (1 week)
Integration in the crystal assembly
PMT socket reception @ IJCLab (? weeks)
Integration with the PMT assembly
Integration in the crystal assembly
PMT base conception @ IJCLab (1.5 week)
Assembly (1.5 week)
Testing (1 week)
The PMT embase conception an construction process will start on June 20th.

## Slide 9
Detector Box
The design of the detector box is completed and the fabrication is underway.
The box will be brass 110x112x440 mm3 with copper absorbers
Fabrication (4 weeks)
Assembly/troubleshooting @ IJCLab (1 week)
Disassembly/packaging and shipping preparation (1 week)
Shipment to JLab (? weeks)
Assembly/testing @ JLab (1 week)

## Slide 10: New Portable Data Acquisition System (DAQ)
DAQ Readout:
  Delayed Helicity, T_Settle and Pattern Sync
  PMT, BCM
  Battery
Remote controllable IHWP
Two systems: one for BNL and one for JLab
DAC
Mini VME Crate
Battery (1 V)
Magnet
Portable Rack
Magnet Power Supply, ±10 Amps
Computer
HV Power Supply, -5kV
PMT
Delayed
Helicity Fiber
Pattern Sync
Helicity TTL 5V Signal to
Pockels Cell
FADC
Helicity
Generator
PMT Signal
Beam Current Monitor (1 V)
T-Settle Fiber
DAC

## Slide 11: DAQ List
Chris Cuevas – Fast Electronics and DAQ

## Slide 12: Controls and DAQ for Compton Polarimeter
Mini-rack
  9 slot 6U VME-64X mini-Crate
  Magnet Power Supply
  DAQ/Slow Controls Server
  Local network switch
  EFADC250
DAQ
  CODA 3 installation and setup
  EFADC250 readout via ethernet
  Online Monitoring
Slow Controls (local + EPICS)
  VME
    Controller (CT VP E24/412-12, Intel Atom + UnivII)
    VME Power Supply / Fans (Weiner 395)
    Detector High Voltage (CAEN v6533N)
    Helicity Generator (JLAB)
  Magnet Power Supply (Ordered two Kepco BOP20-10D-802E supplies )
Bryan Moffit – Fast Electronics and DAQ