## Sheet1
Quarter Year | 10 MeV Polarized e- Injector |  |  | 10 MeV Polarized e- Accumulator/Extractor |  |  | Polarized Positron Source
| Tasks | Procure | L | Tasks | Procure | Labor | Tasks | Procure | Labor
Oct-Dec 2016 | • Develop GPT simulation model of photogun and 10 MeV injector • Explore configurations at UITF and LERF
Jan-Mar 2017 | • Perform GPT multivariate optimization of JLEIC and demo design parameters • Explore configurations at UITF and LERF • Finalize demo parameters (gun HV, laser rep rate, etc) • Model and simulation of diagnostics
Apr-Jun 2017 | • Test gun for operation at HV and with photocathode; e.g. HV condition UITF gun for >300 kV or explore high polarization photocathode at LERF • Order laser amplifer and hardware • Design and fab diagnostics
Jul-Sep 2017 | • Build and assemble laser • Commission gun for demo operation • Commission diagnostics
Oct-Dec 2017 | • Beam tests & model benchmarking at gun votlage • Full demo parameters and beam power at gun voltage
Jan-Mar 2018 | • Beam tests and model benchmarking at 10 MeV • Full demo parameters for injection into figure-8 accumulator at allowed beam power
Apr-Jun 2018 | • Complete data analysis, conclusions, present findings
Jul-Sep 2018 | • Summarize findings for pre-condeptual design report
Oct-Dec 2018 | None
Jan-Mar 2019 | None
Apr-Jun 2019 | None
Jul-Sep 2019 | None
Note on C4: Microsoft Office User: Eliminate?