## Slide 1: Cost Estimate
Group | Labor
Survey & Alignment | 3 wks x 2
Magnet Test | 1 wk x 2
Engineering Design | 16 wks
Software | 3 wks x 2
EES | 6 wk x 2
EH&Q | 4 wks

## Slide 2
Item | Material Procurement | Shop | Labor
New Dipole Magnet | Dipole Magnet ($8,000) Hall Probe ($2,000) |  | Design (2 week) Mapping (1 week) EESDC (1 week) Alignment (2 days)
New Power Supply | Power Supply ($5,000) |  | Software (2 weeks)
New Beamline | 2 Super Harps and Fast Valve ($38,000) | Pipes + Pedestals ($20,000) | Design (6 weeks) Alignment (1 week) Software (4 weeks) EES (6 weeks)
Radiator (cooled ladder, FSD) | 0.02 and 0.10 mm Cu foils ($2,000) | $4,000 | Design (2 week) Alignment (2 days)
Sweep Dipole |  |  | 
Electron Dump | Pure Cu ($5,000) | Dump + Pipes ($15,000) | Design (4 weeks) Alignment (1 day)
Cu Collimator | Pure Cu ($5,000) | Collimator + Stand ($5,000) | Design (1 week) Alignment (1 day)
Photon Dump & Stand | Pure Al ($3,000) | $4,000 | Design (1 week) Alignment (1 day)
Safety Review |  |  | 4 weeks
Install |  |  | 6 weeks
Bubble Chamber |  |  | Alignment (1 week)
Total | $68,000 | $48,000 | $80,000
Indirect G&A (55.65%) | $37,800 | $26,400 | $42,500
Indirect Stat & Fringe (57.15%) |  |  | $45,700
Total | $105,800 | $74,400 | $168,200