## Sheet1
BUBBLE CHAMBER SUMMER 2014 INSTALLATION |  |  | LAST UPDATED: April 7, 2014
Job | Task | Responsible | Status | Start | End
Fast Valve | Vacuum install | Heckman |  |  | 2014-08-01
| FV interlocks | Kortze |  |  | 2014-08-15
| PSS tie-in | Mahoney |  |  | 2014-09-01
Spectrometer | Magnet design | Benesch | 100% |  | 2014-03-15
| Magnet package | Gregory | 90% |  | 2014-04-01
| Magnet build | Vendor TBD |  |  | 2014-07-01
| Fixture design | TBD | 0% |  | 2014-05-01
| Fixture package | Gregory | 0% |  | 2014-07-01
| Fixture build | Vendor TBD | 0% |  | 2014-07-01
| Hall probe | Suleiman | Ordered | 2014-04-02 | 2014-05-15
| Hall probe SW | Software | 0% | 2014-05-15 | 2014-07-01
| Hall probe cable/network | ICN | 0% | 2014-05-15 | 2014-07-15
| Magnet mapping | MagTest | 0% | 2014-07-01 | 2014-08-01
| Magnet install | S&A | 0% | 2014-08-01 | 2014-09-01
5D Beam line | Beamline design | Suleiman |  |  | 2014-05-01
| Beamline package | Gregory |  |  | 2014-06-01
| Modify points | S&A |  |  | 2014-07-15
| Modify girders/feet | Install |  |  | 2014-08-01
| Vacuum install | EGG |  |  | 2014-08-15
| Diagnostics | ICN |  |  | 2014-09-01
| Controls | SW |  |  | 2014-09-01
| Component align | S&A |  |  | 2014-09-01
5D Bubble chamber | Pressure and Mercury Safety | Meekins |  | 2014-05-01 | 2014-09-01
| Chamber ship | Argonne
| Chamber points | S&A
| Chamber install | Install
| Chamber power | FML