## Slide 1
Replace 5/5 QCM with 2/7 BOOSTER
Minimize RF deflection & X/Y coupling
Eliminate capture to simplify setup
Increase Wien Performance (200 keV)
Locate Wiens before pre-buncher
Manage astigmatism/ToF
Increase Gun Voltage (200kV)
Stiffen beam against space charge repulsion
Reduce number ions created by beam
Remove Gun3
Simplify gun/controls/laser
Opportunity for pump/gauge
Upgrade Chopper
Restore independent apertures
Opportunity for improved setup
Improve 200 keV beam line
Improve beam line vacuum
Improve magnets/diags
CEBAF Injector Upgrade : BIG Picture
SUMMER 2017 SUMMER 2018 >= SUMMER 2019

## Slide 2
Preparing 200kV Gun Test
  Pick electrode/shed geometry minimize E-field (<5 MV/m) , linearize along insulator
  Use doped insulator to minimize charging, improve reproducibility with HV off/on
  New *isolated* NEG’s + ground screen, add thermocouple to feedthrough?
  NEG-only bake + calibrate activation current
  Electrode assembly/alignment
  Final assembly bake, NEG activation, hi-pot, measure vacuum/radiation
  Sputter TiVaZr NEG tube, prepare w/ FH solenoid
  Local/EPICS control(Higgins/Johnson) 225kV Spellman + SF6/conditioning resistor
  INJSEG TOSP for Spellman operation : HVPS, 130/200kV control values/limits
Installation/Testing
  Complete present Gun2 beam tests, safe HV, beam line + Prep vacuum, S&A as-found
  Vent, remove/store existing HV chamber in case re-install
  Install HV + NEG tube, bake 250C + activate NEG’s, leak check, check prep/puck alignment, post S&A check
  TOSP + Spellman => Hi-pot (w/o puck, w/ puck), test for radiation/vacuum/FE
  Make photocathode, QE scan, hi-pot, test radiation/vacuum/FE/QE
  Restore beam at 130kV, injector setup to FC1
  Increase gun voltage 200kV, test injector setup to FC1 (magnets, rf, diagnostics)
  Lifetime and PQB beam studies at 200keV vs. 130keV as time permits
  Operate injector w/ Glassman @ 130keV
Remove Gun3
  Safe Gun3 HV, Vacuum
  Vent, remove NEG, Gun table
  Replace w/ bake vacuum station (constant over upgrade): GP500, IP, extractor, pump-out (pinch off)
  Eliminate or cold storage of controls (Higgins)

## Slide 3
# | Week | Priority Job | INJ BP | NL BP | CEBAF Opportunity | Laser Table | 4-LLRF | Bubble | PQB | Injector Upgrade | Brock Cavity
1 | 27-Mar | 4-LLRF Install |  |  | No |  | Install |  |  |  | 
2 | 3-Apr | 4-LLRF/Beam | x | x | Swing/Owl |  | Beam |  |  |  | 
3 | 10-Apr | Laser/Beam | x |  | Swing/Owl | Tune mode |  |  |  |  | 
4 | 17-Apr | PQB/Beam | x |  | No |  |  |  | Spot Size |  | 
5 | 24-Apr | Brock Beam | x |  | Swing/Owl |  |  |  |  |  | Kicker
6 | 1-May | Gun2 Beam | x |  | No |  |  |  |  | Gun2 Studies | 
7 | 8-May | Gun3 Vac. work |  |  | Day/Swing/Owl |  |  |  | Laser Table ??? | Gun3/NEG | 
8 | 15-May | PSS (Swing) |  |  | ? |  |  |  |  | Gun3/NEG | 
9 | 22-May | PSS Cert (Day) |  |  | ? |  |  |  |  |  | 
10 | 29-May | None |  |  | No |  |  |  |  |  | 
11 | 5-Jun | Spellman |  |  | No |  |  |  | Laser Table ??? | Spellman Test | 
12 | 12-Jun | Spellman |  |  | Day/Swing/Owl |  |  |  | Laser Table ??? | Spellman Oper. | 
13 | 19-Jun | Gun2 Vac. work |  |  | No |  |  |  | Laser Table ??? | Gun2 Bake | 
14 | 26-Jun | Gun2 Vac. work |  |  | No |  |  |  | Laser Table ??? | Gun2 Bake | 
15 | 3-Jul | Gun2 @ 200kV | x |  | No |  |  |  |  | Gun2 HiPot | 
16 | 10-Jul | Gun2 @ 200kV | x |  | No |  |  |  |  | 200 keV Demo | 
17 | 17-Jul | Gun2 @ 200kV | x |  | No |  |  |  | 200 keV PQB | 200 keV Demo | 
18 | 24-Jul | Bubble Install |  |  | Swing/Owl |  |  | Install |  |  | 
19 | 31-Jul | Bubble Intstall |  |  | Swing/Owl |  |  | Install |  |  | 
20 | 7-Aug | Bubble Run | x | x | Owl |  |  | Run |  |  | 
21 | 14-Aug | Bubble Run | x | x | Owl |  |  | Run |  |  | 
22 | 21-Aug | PSS Cert |  |  | ? |  |  |  |  |  | 
23 | 28-Aug | INJ setup/ HCO | x |  | Sure |  |  |  |  |  | 
24 | 4-Sep | Restore CEBAF | x | x | Why not |  |  |  |  |  |