## Slide 1: Generation and Characterization of Magnetized Bunched Electron Beam from DC Photogun for MEIC Cooler
Milestones
July 7, 2015
Riad Suleiman and Matt Poelker

## Slide 2
Year 1 Milestones
Q1 (Oct, Nov, Dec):
    HV condition gun at 350 kV and commission k2CsSb preparation chamber
    Design beamline to locate magnets and diagnostics at optimum positions
    Design gun solenoid magnet or Helmholtz coil-pair
    Design skew quad magnets and slits
Q2 (Jan, Feb, Mar):
    Connect existing beamline to gun and complete hot checkout
    Relocate old CEBAF arc dipole power supply to GTS
    Procure gun solenoid magnet or Helmholtz coil-pair
    Procure skew quad magnets and slits
Q3 (Apr, May, Jun):
    Commission exiting beamline with beam
    Measure photocathode lifetime at 5 mA and 350 kV (not magnetized)
Q4 (Jul, Aug, Sep):
    Assemble new beamline and commission with beam
    Install gun solenoid magnet or Helmholtz coil-pair

## Slide 3
Year 2 Milestones
Q1 (Oct, Nov, Dec):
    Generate magnetized beam
    Measure mechanical angular momentum vs magnetization and laser size
    Benchmark simulation against measurements
Q2 (Jan, Feb, Mar):
    Measure mechanical angular momentum vs bunch charge and bunch length
    Benchmark simulation against measurements
Q3 (Apr, May, Jun):
    Generate very high currents magnetized beam and study beam transport vs electron bunch charge
Q4 (Jul, Aug, Sep):
    Measure photocathode lifetime vs magnetization at 5 mA and 350 kV
    Study beam halo and beam loss vs magnetization

## Slide 4
Year 3 Milestones
Q1 (Oct, Nov, Dec):
    Generate flat beam with three skew quads – RTFB Transformer – and measure horizontal and vertical emittances using slit method
Q2 (Jan, Feb, Mar):
    Measure RTFB transformation versus electron bunch charge
    Use simulation to quantify how good or complete RTFB transform
Q3 (Apr, May, Jun):
    Change to HV Supply of 32 mA and 200 kV
Q4 (Jul, Aug, Sep):
    Measure photocathode lifetime vs magnetization at 32 mA and 200 kV
    Study beam halo and beam loss vs magnetization