## Slide 1: Design Update Puck and Gun Magnet
February 16, 2016

## Slide 2
Magnetized Gun
K2CsSb Preparation Chamber
HV Chamber

## Slide 3: Solenoid + Steel Puck
18”
7.5”
12”
6”
0.5”
9.0 cm
Steel Puck
Gun Table
8”
6.4 cm
Moly
10”
Cathode-Anode Gap
Is it possible to replace this 10’’ flange with one that has shorter ports?
Maybe not.

## Slide 5
Steel Puck
Molybdenum and Steel hybrid puck
Designed to enhance field to 2.0kG at cathode
Use 1010 carbon steel
Re-design new Puck Manipulator End Adapter
Order 4 pucks – map with Solenoid
Heat Treatment:
  Un-heated
  200˚C (Sb) and 120˚C (K – Cs) growth
  550˚C Heat Cleaning then 200˚C and 120˚C
  Multiple

## Slide 6
Puck
Puck Manipulator End Adapter

## Slide 7
Steel
Moly
6 mm
10 mm
Design I
Brazed – not screwed

## Slide 8
Steel
Stainless Steel
2 mm
10 mm
Design II
2 mm
4 mm

## Slide 9
Cut this part
2 mm

## Slide 10
Power Supply
Use new spare Dogleg power supply (500A, 80V)
We have Arne’s permission
If needed at CEBAF, we can use an old Dogleg
supply (270A, 50V) to keep going
Need to add polarity switch to be able to degauss
steel

## Slide 11
Solenoid
Not bakable – will be mounted on rails. Push downstream out of oven and run LCW through. Move gate valve after beamline solenoid (in place of BPM). Move HV Chamber front foot upstream
Designed to give 1.4kG at cathode without steel puck
No cylindrical shield/return (only a coil)?
Plan to ask companies for design and cost:
  Everson Tesla
  Buckley Systems
Needs a designer for solenoid mount

## Slide 12
Solenoid Mount
Gun Table
Rails
Allow for small adjustments to center solenoid on beam

## Slide 13
Timeline
Power Supply (new spare Dogleg):
  Being built at Magnet Lab: March
  Test and add polarity switch: April
  Move to GTS: May
  Ready: July 1, 2016
Solenoid:
  Design: February and March
  Procure: April
  Map (with and w/o puck), check hysteresis and forces: July
  Install: August, 2016
All work has to be completed by September 30, 2016.