## Slide 1: Bubble Chamber Summer 2015
https://wiki.jlab.org/ciswiki/index.php/Bubble_Chamber
July 8, 2015
Installation and
Beam Test Schedule

## Slide 2: Test Beamline

## Slide 5: Bubble Chamber
Bubble Chamber at Duke
April 2013
Photon Beam
Entrance

## Slide 6
N2O Bubble Chamber
  T = -10˚C
  P = 50 atm

## Slide 7: Bubble Chamber Safety Reviews
Superheated liquid: N2O, Nitrous oxide (laughing gas)
  At room temperature, it is colorless, non-flammable gas, with slightly sweet odor and taste
High pressure system:
  Design Authority: Dave Meekins
  T = -10˚C, P = 50 atm
Buffer liquid: Mercury
  Closed system
  Volume: 150 mL
Electrical Review: 208 V custom-made electrical distribution box
Temporary Operational Safety Procedure (TOSP)
0
OX
0
2
0
0
3

## Slide 8: Beam Requirement
Electron K.E.
3.0 – 9.5 MeV
0.01 – 100 µA
Al Beam Pipe
Cu
Radiator/Dump
6 mm
Bubble Chamber
Superheated N2O
3 cm long
-10°C, 50 atm
Al Photon Dump
40 cm long
Cu Photon
Collimator
Use isotopic pure copper and aluminum
Radiator/dump isolated and current in EPICS readback
Ceramic
Insulator

## Slide 9
Large Dynamic Range Diagnostic Station (LDRDS) was installed in 5D line for beam test in Spring and Summer
Remove before Bubble Chamber installation

## Slide 10: Schedule
July 29: Remove LDRDS and reassemble 5D line (Adderley + LDRDS crew)
July 30 – 31: Survey and Alignment
End-of-July: Bubble Chamber arrives JLab (shipping list and handling instructions will be provided), move to Injector tunnel (Install Group)
August 3 – 5: Install Chamber in 5D line (Brad DiGiovine + Install Group)
August 6 – 7: Safety review and inspection (Meekins + ESH&Q)
August 10 – 11: Survey and Alignment
August 12 – 30: Chamber ideal
August 31 – September 11: Chamber active for engineering run
September 12 – : Chamber ideal

## Slide 11: Other Tasks
  New laser shutter to terminate beam while Bubble Chamber is processing an event – Chamber will generate a TTL signal that will stay high for period with no beam (Hansknecht)
  Thermal analysis of flange radiator/dump to increase administrative current limit from 10 µA CW to 100 µA CW (ME)
  Identify OPS Liaison to Bubble Chamber

## Slide 12
Beam Studies: August 10 – 15 (swing shift only)
  Momentum measurement (ATLis 13521)
  Increase ¼ Cryounit gradient (ATLis 13523)
  Measure beam charge at different currents (ATLis 13524)
Engineering Run: August 31 – September 11 (day + swing shifts)
  Run plan forthcoming
Beam Operations