## Slide 1: Bubble Chamber Planning Meeting
07 August 2013

## Slide 2: Agenda
Bubble Chamber progress at Argonne
Beamline Layout
Bubble Chamber cost estimate: procurement and labor
Background from 17O(γ,n)16O and subsequent neutron elastic scattering with 16O and 14N nuclei
Background from 13C(γ,n)12C (in case we decide to use CO2 instead of N2O)

## Slide 3: Beamline Layout
HARP to measure beam profile
Fast Valve to protect from vacuum failure
Distance between two BMPs = 55” (was 18” for PEPPo)
Camera for OTR light from Cu foils
Beam Properties at Radiator:
Beam Energy, E (MeV) | 3.0 – 8.5
Beam Current (µA) | 0.01–200
Absolute Beam Energy | 0.1%
Relative Beam Energy | 0.1%
Energy Resolution (Spread), σE /E | 0.06%
Beam Size, σx,y (mm) | 1 – 2

## Slide 4
42”
25°
100”
Valve
Ion
Pump
Viewer
Quad
BPM
Corrector
35”
HARP
Fast
Valve
Quad
BPM
Corrector
Radiator
Viewer
Ion Pump
55”
Sweep
Dipole
25°
Vacuum
Window
Cu Collimator
Electron Dump
Photon
Dump
80”
Bubble
Chamber
76”

## Slide 5: Cost Estimate
Radiator motion and Sweep Dipole must be in FSD
Cooled: Radiator and Electron Dump.
Uncooled: Photon Collimator and Photon Dump
Re-use PEPPo radiator and beamline
New beamline components: HARP + Fast Valve
Summary of labor cost by group:
Group | Labor
Survey & Alignment | 3 wks x 2
Magnet Test | 1 wk x 2
Engineering Design | 12 wks
Software | 3 wks x 2
EES | 4 wk x 2
EH&Q | 4 wks

## Slide 6
Item | Material Procurement | Shop | Labor
New BPM on Spect. line |  | Pipe + BPM ($5,000) | P. Francis (1 week)
New Dipole Magnet | Dipole Magnet ($10,000) |  | Mapping (1 week) EESDC (1 week) Alignment (2 days)
New Power Supply | Power Supply ($5,000) |  | Software (2 weeks)
New Beamline |  | Pipes + Pedestals ($20,000) | Design (6 weeks) Alignment (1 week) Software (4 weeks)
Radiator (cooled ladder, FSD) | 0.02 and 0.10 mm Cu foils ($1,000) | $2,500 | Design (2 week) Alignment (2 days)
Sweep Dipole | ? | ? | ?
Electron Dump | Pure Cu ($5,000) | Dump + Pipes ($10,000) | Design (2 week) Alignment (1 day)
Cu Collimator | Pure Cu ($3,000) | Collimator + Stand ($5,000) | Design (1 week) Alignment (1 day)
Photon Dump & Stand | Pure Al ($1,000) | $2,500 | Design (1 week) Alignment (1 day)
Safety Review |  |  | 4 weeks
Install |  |  | 6 weeks
Bubble Chamber |  |  | Alignment (1 week)
Total | $25,000 | $45,000 | $80,000

## Slide 7: 17O(γ,n)16O Background

## Slide 8: Ion Energy Distribution
Depletion:
  17O depletion=5,000
  18O depletion=5,000
Natural Abundance:
  17O: 0.038%
  18O: 0.205%

## Slide 10: 13C(γ,n)12C Background
Depletion:
  13C depletion=1,000
Natural Abundance:
  13C: 1.07%
For comparison, 17O(γ,n)16O