## Iteration - 1
Week Off | Other | INJ Cryo | INJPSS | S&A | PSS Cert | Bubble Install | Bubble | PQB | BROCK | NEW GUN/NEG | 350KV HVPS
2018-03-26 |  | 2K | RA | x | >3pm | Install day
2018-04-02 |  | ? | RA | x | >3pm | Install day |  | RTP Laser
2018-04-09 |  | 4K trans. | INJ=FC1 |  |  |  |  | RTP/INJTWF (Apr. 11 AM tour)
2018-04-16 |  | 4K trans. | INJ=FC1 |  |  |  |  | Float | Beam (DS)
2018-04-23 |  | 2K | INJ/NL |  |  |  | DSO
2018-04-30 |  | 2K | INJ/NL |  |  |  | DSO
2018-05-07 |  | 2K | RA | x | [5 empty] | INSTALL | INSTALL
2018-05-14 |  | 2K | RA | x | [5 empty] | INSTALL/BAKE | INSTALL
2018-05-21 |  | 2K | INJ | [6 empty] | BAKE/COND @ 150 | INSTALL
2018-05-28 |  | 2K | INJ | [6 empty] | COND @ 150 | INSTALL
2018-06-04 |  | 2K | INJ | [6 empty] | BEAM @ 150 | COMM
2018-06-11 |  | 2K | INJ | [6 empty] | COND @ 200 | OPERATE
2018-06-18 |  | 2K | INJ | [6 empty] | FLOAT | FLOAT
2018-06-25 |  | 2K | INJ | [6 empty] | BEAM @ 200 | OPERATE
2018-07-02 |  | 2K | INJ/NL | [5 empty] | DS | BEAM @ 200 | OPERATE
2018-07-09 |  | 2K | INJ/NL |  |  |  |  | DS | DS | BEAM @ 5 MEV | OPERATE
2018-07-16 | LCLS @2K | 2K | INJ/NL | [5 empty] | DS | BEAM @ 5 MEV | OPERATE
2018-07-23 | LCLS @2K | 2K | INJ/NL | [5 empty] | DS | FLOAT | FLOAT
2018-07-30 | LCLS @2K | 2K | INJ/NL | [5 empty] | DS | FLOAT | FLOAT
2018-08-06 | LCLS @2K | 2K | INJ/NL |  |  |  | DSO
2018-08-13 | LCLS @2K | 2K | INJ/NL |  |  |  | DSO
2018-08-20 | LCLS @2K | 4K trans.
2018-08-27 | LCLS @2K | 4k trans.

## Iteration - 2
Week Off | INJ Cryo | INJPSS | S&A | PSS Cert | Bubble | Tours | PQB | BROCK | NEW GUN/NEG | 350KV HVPS
2018-04-02 | 2K | RA | x | SO | Install day
2018-04-09 | n/a | RA | x | SO | Install day | MIT 4/11 | LASER RTP
2018-04-16 | n/a | INJ |  |  |  |  | BEAM FC1
2018-04-23 | n/a | INJ | x |  |  |  |  | Beam
2018-04-30 | 2K | INJ/NL |  |  | ENG Run
2018-05-07 | 2K | INJ/NL |  |  | ENG Run
2018-05-14 | 2K | INJ/NL |  |  |  |  | BEAM FC2
2018-05-21 | 2K | RA | x | [5 empty] | INSTALL | INSTALL
2018-05-28 | 2K | RA | x | [5 empty] | INSTALL | INSTALL
2018-06-04 | 2K | INJ | [6 empty] | BAKE | COMMISSION
2018-06-11 | 2K | INJ | [6 empty] | BAKE | COMMISSION
2018-06-18 | 2K | INJ | [6 empty] | GAS CONDITION | OPERATE
2018-06-25 | 2K | INJ | [6 empty] | GAS CONDITION | OPERATE
2018-07-02 | 2K | INJ | [6 empty] | FLOAT | FLOAT
2018-07-09 | 2K | INJ | [6 empty] | FLOAT | FLOAT
2018-07-16 | 2K | INJ/NL | [6 empty] | Restore 130 keV to FC2 | OPERATE
2018-07-23 | 2K | INJ/NL | [6 empty] | Setup @ 200 kV to FC2 | OPERATE
2018-07-30 | 2K | INJ/NL |  |  |  |  | PQB 200 kV |  | Beam @ 200 kV to FC2 | OPERATE
2018-08-06 | 2K | INJ | [6 empty] | Lifetime vs. Voltage | OPERATE
2018-08-13 | 2K | INJ | [6 empty] | Lifetime vs. Voltage | OPERATE
2018-08-20 | 2K | INJ/NL |  |  | ENG Run
2018-08-27 | 2K | INJ/NL |  |  | ENG Run

## Iteration - 3
Week Off | CHL | INJPSS | S&A | PSS Cert | Bubble | Tours | PQB | BROCK | NEW GUN/NEG | 350KV HVPS
2018-04-16 | 2K | RA | x | SO | Install day | MIT?
2018-04-23 | 2K | RA | x | SO | Install day | MIT? | Laser
2018-04-30 | Trans | INJ |  |  |  |  | Beam
2018-05-07 | Trans | INJ | x |  |  |  | Float | 1D
2018-05-14 | 2K | INJ/NL |  |  | ENG Run
2018-05-21 | 2K | INJ/NL |  |  | ENG Run
2018-05-28 | 2K | RA | x | [5 empty] | INSTALL | INSTALL
2018-06-04 | 2K | RA | x | [5 empty] | INSTALL | INSTALL
2018-06-11 | 2K | INJ | [6 empty] | BAKE | COMMISSION
2018-06-18 | 2K | INJ | [6 empty] | BAKE | COMMISSION
2018-06-25 | 2K | INJ | [6 empty] | GAS CONDITION | OPERATE
2018-07-02 | 2K | INJ | [6 empty] | GAS CONDITION | OPERATE
2018-07-09 | 2K | INJ/NL | [6 empty] | Restore 130 keV to FC2 | OPERATE
2018-07-16 | 2K | INJ/NL | [6 empty] | Setup @ 200 kV to FC2 | OPERATE
2018-07-23 | 2K | INJ/NL |  |  |  |  | PQB 200 kV |  | Beam @ 200 kV to FC2 | OPERATE
2018-07-30 | 2K | INJ | [6 empty] | Lifetime @ 200 kV to FC1 | OPERATE
2018-08-06 | 2K | INJ/NL |  |  | ENG Run
2018-08-13 | 2K | INJ/NL |  |  | ENG Run
2018-08-20 | Trans | RA |  | SO
2018-08-27 | Trans | RA |  | SO

## Iteration - 4
Week Off | CHL | INJPSS | S&A | PSS Cert | Bubble | PQB | BROCK | NEW GUN/NEG | 350KV HVPS
2018-04-16 | 2K | RA | x | SO | Install day
2018-04-23 | 2K | RA | x | SO | Install day | Laser Table
2018-04-30 | Trans | INJ |  |  |  | Beam FC1
2018-05-07 | Trans | INJ | x |  |  | Float | Beam 1D
2018-05-14 | 2K | INJ/NL |  |  | Beam FC2
2018-05-21 | 2K | INJ/NL |  |  | Beam FC2
2018-05-28 | 2K | RA | x |  |  |  |  | INSTALL | INSTALL
2018-06-04 | 2K | RA | x |  |  |  |  | INSTALL | INSTALL
2018-06-11 | 2K | INJ | [5 empty] | BAKE | COMMISSION
2018-06-18 | 2K | INJ | [5 empty] | BAKE | COMMISSION
2018-06-25 | 2K | INJ | [5 empty] | GAS CONDITION | OPERATE
2018-07-02 | 2K | INJ | [5 empty] | GAS CONDITION | OPERATE
2018-07-09 | 2K | INJ/NL | [5 empty] | Restore 130 keV to FC2 | OPERATE
2018-07-16 | 2K | INJ/NL | [5 empty] | Setup @ 200 kV to FC2 | OPERATE
2018-07-23 | 2K | INJ/NL |  |  |  | PQB 200 kV |  | Beam @ 200 kV to FC2 | OPERATE
2018-07-30 | 2K | INJ | [5 empty] | Lifetime @ 200 kV to FC1 | OPERATE
2018-08-06 | 2K | INJ/NL |  |  | Beam FC2
2018-08-13 | 2K | INJ/NL |  |  | Beam FC2
2018-08-20 | Trans | RA |  | SO
2018-08-27 | Trans | RA |  | SO

## Iteration - 5
Week Off | OPS SUPPORT | CHL | INJPSS | S&A | PSS Cert | Bubble | PQB | BROCK | NEW GUN/NEG | 350KV HVPS
2018-04-16 | Swing PSS | 2K | RA | x | SO | Install day
2018-04-23 | Swing PSS | 2K | RA | x | SO | Install day | Laser Table
2018-04-30 | M-F: 8am-8pm | Trans | INJ |  |  |  | Beam FC1
2018-05-07 | M-F: 8am-8pm | Trans | INJ | x |  |  | Float | Beam 1D
2018-05-14 | S-S: 24/7 | 2K | INJ/NL |  |  | Beam FC2
2018-05-21 | S-S: 24/7 | 2K | INJ/NL |  |  | Beam FC2
2018-05-28 | none | 2K | RA | x |  |  |  |  | INSTALL | INSTALL
2018-06-04 | none | 2K | RA | x |  |  |  |  | INSTALL | INSTALL
2018-06-11 | DAY | 2K | INJ | [5 empty] | BAKE | COMMISSION
2018-06-18 | DAY | 2K | INJ | [5 empty] | BAKE | COMMISSION
2018-06-25 | M-F: 8am-8pm | 2K | INJ | [5 empty] | GAS CONDITION | OPERATE
2018-07-02 | M-F: 8am-8pm | 2K | INJ | [5 empty] | GAS CONDITION | OPERATE
2018-07-09 | DAY, SWING? | 2K | INJ/NL | [5 empty] | Restore 130 keV to FC2 | OPERATE
2018-07-16 | DAY, SWING? | 2K | INJ/NL | [5 empty] | Setup @ 200 kV to FC2 | OPERATE
2018-07-23 | DAY, SWING? | 2K | INJ/NL |  |  |  | PQB 200 kV |  | Beam @ 200 kV to FC2 | OPERATE
2018-07-30 | M-F: 24/7 | 2K | INJ | [5 empty] | Lifetime @ 200 kV to FC1 | OPERATE
2018-08-06 | S-S: 24/7 | 2K | INJ/NL |  |  | Beam FC2
2018-08-13 | S-S: 24/7 | 2K | INJ/NL |  |  | Beam FC2
2018-08-20 | Swing PSS | Trans | RA |  | SO
2018-08-27 | Swing PSS | Trans | RA |  | SO

## Iteration - 6
Week Off | Program | OPS SUPPORT | CHL | PSS | S&A | Installation | Bubble | GUN | HVPS
2018-05-07 | PSS Cert | Swing PSS | Trans | Cert | x | x | Install | INSTALL | Install 350
2018-05-14 | PSS Cert | Swing PSS | 2K | Cert | x | x | Install | INSTALL | Install 350
2018-05-21 |  | DAY? | 2K | INJ |  |  |  | BAKE | Comm. 350
2018-05-28 |  | DAY? | 2K | INJ |  |  |  | BAKE | Comm. 350
2018-06-04 |  | DAY | 2K | INJ |  |  |  | HV Condition | 350 (150 backup)
2018-06-11 |  | DAY | 2K | INJ |  |  |  | HV Condition | 350 (150 backup)
2018-06-18 |  | DAY | 2K | INJ |  |  |  | Beam > 130kV | 350 (150 backup)
2018-06-25 |  | DAY | 2K | INJ |  |  |  | Beam = 200 kV | 350 (150 backup)
2018-07-02 |  | 24/7 | 2K | INJ |  |  |  | Beam @ 200 kV to FC2 | 350 (150 backup)
2018-07-09 |  | 24/7 | 2K | INJ |  |  | ENG Run | Lifetime @ 130 keV | 350 (150 backup)
2018-07-16 |  | TBD | Trans | INJ/NL |  |  | ENG Run 2K/4K? | Float | Float
2018-07-23 | HCO |  | Trans | INJ/NL |  |  |  | Float | Float
2018-07-30 | HCO |  | 2K | INJ/NL
2018-08-06 | Inj Setup |  | 2K | INJ
2018-08-13 | Restore |  | 2K | INJ/NL
2018-08-20 | Physics |  | 2K | INJ/NL