## Plan A Resistor tank
Process to insert conditioning resistor if R30 resistor tank is ready ~ 4 hours
step
1 | Ask Neil to crane the resistor tank & HV cables down to the injector tunnel
2 | Done CAT 2 PPE and disengage Gun2 HVPS disconnect
3 | Apply LOTO to Gun2 HVPS disconnect
4 | Bubba or Carlos to remove R350-R28 cable from HVPS to gun
5 | Plug R350-R30 from HVPS to resistor tank
6 | Plug R30-R28 from resistor tank to gun
7 | Remove LOTO to Gun2 HVPS disconnect
8 | Done CAT 2 PPE and engage Gun2 HVPS disconnect

## Plan B DILO cart
Process to replace short inside HVPS with resistor ~ 10 hours
step
1 | Ask Neil to crane DILO cart down to the injector tunnel
2 | Done CAT 2 PPE and disengage Gun2 HVPS disconnect
3 | Apply LOTO to Gun2 HVPS disconnect
4 | Transfer SF6 from HVPS tank to storage bottles | 5 hours
5 | Vent HVPS and replace short with conditioning resistor | 1 hour
6 | Evacuate HVPS tank | 1 hour
7 | Backfill HVPS to 60 psig of SF6 | 3 hours
8 | Remove LOTO to Gun2 HVPS disconnect
9 | Done CAT 2 PPE and engage Gun2 HVPS disconnect

## T electrode 200kV eval
Tee electrode on white insulator operating at 130kV: Procedure to evaluate at 200kV ~ 8 hours
step
1 | Open Gun2 HVPS controls screen.
2 | Set HV Op limit to 205kV and HVPS current limit to 0.2 mA.
3 | Monitor DecaRad signals, Gun2 vacuum, anode current and HVPS currentas a function of HVPS voltage using LivePlot
4 | Set the HV ramp up rate to 25 kV/min.
5 | Set voltage to 130kV and click HV Go. Soak for a few minutes to onbtain a baseline for all the monitored signals.
6 | Set the HV ramp up rate to 5 kV/min
7 | Increase the voltage by 5 kV and wait for about 1 minute before increasing the voltage again by 5kV.
8 | Continue increasing voltage up to 200kV, keeping track of field emission, anode current, HVPS current and gun vacuum levels.
9 | Record voltage for field emission onset.
10 | High voltage evaluation complete. Input voltage set point to 0 V and click HV Go.
11 | Turn HVPS OFF.

## Wien filter HV eval
Vertical and Horizontal Wien filters connected to 15 kV PS
Objective is to evaluate vacuum response vs applied voltage to one electrode at at time with both polarities
step
1 | Choose one of the Win filter to start with
2 | Monitor Wien filter vacuum using the upstream and downstream ion pumps
3 | Turn Wien filter magnet off
4 | Turn both negative and positive HV PS off
5 | While monitoring vacuum using LivePlot, ramp NEGATIVE PS in steps of 500 volts (or in 1000 "units" steps) until reaching 15 kV
6 | Turn Negative PS off
7 | While monitoring vacuum using LivePlot, ramp POSITIVE PS in steps of 500 volts (or in 1000 "units" steps) until reaching 15 kV
8 | Turn Positive PS off
9 | Switch HV polarities, now the electrode that was biased fist negative will be biased positive and viceversa
10 | Repeat steps 5-8
11 | Repeat procedure for the other Wien filter

## Small shld elec HV processing
Small shield electrode on black insulator: Procedure for HV processing for 200 kV operation w/o field emission
step
1 | Open Gun2 HVPS controls screen.
2 | Set HV Op limit to 250kV and HVPS current limit to 0.2 mA.
3 | Monitor DecaRad signals, Gun2 vacuum, anode current and HVPS currentas a function of HVPS voltage using LivePlot
4 | Set the HV ramp up rate to 25 kV/min.
5 | Set voltage to 25kV and click HV Go. Soak for a few minutes to onbtain a baseline for all the monitored signals.
6 | Set voltage to 50kV and click HV Go. Soak for a few minutes to onbtain a baseline for all the monitored signals.
7 | Be mindful of field emission onset voltage and record it.
8 | Reduce the ramp up rate to 12 kV/min
9 | Set voltage to 75kV and click HV Go. Soak for a few minutes to onbtain a baseline for all the monitored signals.
10 | Set voltage to 100kV and click HV Go. Soak for a few minutes to onbtain a baseline for all the monitored signals.
11 | Reduce the ramp up rate to 5 kV/min
12 | Increase the voltage by 10 kV and soak for a few minutes. See guidelines on observed behavior and what to do pasted here.
13 | When reaching 150 kV, reduce the ramp up rate to 2 kV/min and the voltage increments to 5 kV.
14 | It is very likely that field emission will be present when reaching 200kV, requiring processing to 230kV or more.
15 | If this is the case, reduce ramp uprate to 1 kV per minute
16 | Increase voltage by 1 kV every 15 minutes. The HVPS will trip off serveal times on over-current. Usuall field emission clears off
after a HVPS trip. But the max voltage required to achieve that is unknown.
17 | If 250kV kV have been reached and field emission stil present at 200kV, stop and evaluate for Kr processing.
18 | If there is no field emission at 200kV, soak at that voltage for about 12 hours to ensure no more field emitter develop.