## Slide 1: One Coil Gun Magnet
February 2, 2016

## Slide 2
Magnetized Gun
K2CsSb Preparation Chamber
HV Chamber

## Slide 3: One Coil + Steel Puck
18”
15”
13”
10”
10”
4”
4”
3”
Steel Puck
Counter-wound solenoid (?)

## Slide 5
Similar magnet:
PEPPo
MPT Solenoid

## Slide 6
Timeline
Power Supply:
  Move to Magnet Lab: February
  Test: March
  Move to GTS: April
  Ready: July 1, 2016
Magnet:
  Design: February and March
  Procure: April
  Map (with and w/o puck): July
  Install: August, 2016
All magnet work has to be completed by September 30, 2016.