## Sheet1
Updated 10/15
Status | Task | Lead | Time Required | Beam Required | Comment, Procedure or ATLIS task
| Degauss dump dipole | Grames | 0.25 | No | Hand cycle to zero w/ decreasing current
| Check target ladder motion | Grames | 0.25 | No | Perform home/reset, move to targets
| HiPot VIP3D01 | Grames | 1 | No | Use Gamma SPC, hi-pot mode
Done | Setup 31MHz laser | Hansknecht | 4 | No | Configure B laser divider/seed/pre-amp
| Test 31 MHz beam | Grames | 1 | Yes | On 10/16 test bunch scans to 10uA CW
| Test 62 MHz DAQ reference | Suleiman | 2 | No | Verify RF trigger at Mott DAQ correct
| Verify CODA operation | Suleiman | 0.5 | Yes
| Verify disk space available | Suleiman | 0.5 | No
| Test PMT HVPS operational | Suleiman | 0.25 | No
| Balance E/dE PMT voltages for 5 MeV | Suleiman | 1 | Yes | Beam to Mott
| Set L/R/U/D equal TOF delay | Suleiman | 2 | Yes | Beam to Mott
| Verify L/R/U/D spectra OK | Suleiman | 2 | Yes | Determine if we use Px or Py at Mott
| Set hardware timing veto | Suleiman | 2 | Yes | Beam to Mott
| Set thresholds for thinnest/thickest foils | Suleiman | 2 | Yes | Beam to Mott
| Quad center 0L02,0L03,5D00,5D01 | Grames | 2 | Yes | Todd's or Joe's ?
| Dry Run - Set beam KE=5.0 MeV | Grames | 2 | Yes | Writing now…use simple calc or Joe correction Dry run 10/21 or 10/22 ?
| Dry Run - Measure emittance | Grames | 1 | Yes | Writing now…use qsUtility + zigzag config file Dry run 10/21 or 10/22 ?
| Dry Run - Measure energy spread | Grames | 1 | Yes | Writing now…use IHA2D00 Dry run 10/21 or 10/22 ?
| TOTAL PREP SHIFTS |  | 3.0938
| BCM v. FCUP2 calibration | Grames | 1 | Yes | BCM0L02 vs. FCUP2 calibration
| PITA calibration | Suleiman | 1 | Yes
| Final spin setup with VWien+Solenoids | Grames | 2 | Yes | Just before experiment, choose Px or Py, scan Vwien and Solenoids
| Final setup - beam KE=5.0 MeV | Grames | 1 | Yes | Use procedure, perform 10/23
| Final setup - measure emittance | Grames | 1 | Yes | Use procedure, perform 10/23
| Final setup - measure energy spread | Grames | 1 | Yes | Use procedure, perform 10/23
| Elastic rate | Mott | 4 | Yes | Low deadtime, constant current
| Asymmetry v. energy | Mott | 8 | Yes | Vary +/- 200 keV, 400 keV
| Asymmetry v. target thickness | Mott | 24 | Yes | 10 foils on 25mm mount, 0.2% stat
| TOTAL RUN II SHIFTS |  | 5.375