## Slide 1
Source Planning Meeting - Summer 2016 SAD
January 14, 2016
Agenda
Joe - Quick overview of Arne's program goals and summer SAD time table
John - Addition and plans of 4th laser to polarized source
Roger - SCAM-II requirements and plans, differences from SCAM-I
Tomasz - Plans to deploy new dedicated laser LLRF modules for 4-laser system
Henry – Consideration to reconfigure PSS/HVPS interface for "always on" 4-hall operation
All – Other topics

## Slide 2
The Hall D GlueX program is a cornerstone of the 12 GeV proposal… 
...but, we only have a 3-beam CEBAF to support a 4-hall program... 
...however, Reza has the good idea and proposes how to satisfy 4-halls simultaneously! 
The Story of the CEBAF 4-Laser Upgrade
Through some pretty significant efforts two new systems are designed, fabricated and have been commissioned over the last two years:
750 MHz separators which allow Halls A/B/C to share 5th pass with Hall D
250 MHz lasers which satisfy the linac (1500 MHz), lower pass separators (500 MHz) and new 5th pass separators (750 MHz)
This mode of beam operation was successfully used in December 2015!!! 
So, why are we here now....?
We only have 3 lasers, so we need to add a 4th !!!

## Slide 3
Dates | Activities
Jan 28 – Apr 14, 2016 | 3-laser @ 250 MHz for A/B/D + commission C
Apr 15 – Apr 30, 2016 | CHL transition (configure one CHL for both linacs) PSS certification (static, functional, float)
May 1 – May 28, 2016 | 3-laser @ 250 MHz for Hall B PRAD
May 30 – Jun 20, 2016 | 1-laser @ 499 MHz for Injector Bubble
Jun 20 – Aug 13, 2016 | 4-laser upgrade (table re-work, SCAM-II, LLRF, commissioning)
Aug 15 – Aug 29, 2016 | 1-laser @ 499 MHz for Injector Bubble
Aug 29 – Sep 4, 2016 | 1-laser @ 499 MHz for Hall C commissioning @ 5.5 pass 
Sep 5 – Sep 30, 2016 | CHL transition (configure one CHL per linac) PSS certification (static, functional, float)
Oct 1 – Dec 19, 2016 | 3-laser @ 250 MHz for A/C/D
Dec 19 – Dec 22, 2016 | 4-laser @ 250 MHz for 4-hall demonstration
Dec 22 – Feb 10, 2017 | Winter SAD
Feb 10 – Jun 6, 2017 | 4-laser @ 250 MHz for 4 Hall program
4 Laser Upgrade : Calendar and Plans