## Slide 1: Generation and Characterization of Magnetized Bunched Electron Beam from DC Photogun for MEIC Cooler
Laboratory Directed Research and Development (LDRD) Proposal
June 29, 2016
Riad Suleiman and Matt Poelker

## Slide 2: JLEIC Magnetized Beam LDRD
Generate magnetized electron beam and measure its properties
Explore impact of cathode solenoid on photogun operation
Simulations and measurements will provide insights on ways to optimize JLEIC electron cooler and help design appropriate source
JLab will have direct experience magnetizing high current electron beam

## Slide 3: Magnetized Bunched Electron Beam Requirements
Bunch length | 60 ps (2 cm)
Repetition rate | 476.3 MHz
Bunch charge | 420 pC
Peak current | 7.0 A
Average current | 200 mA
Transverse normalized emittance | 10s microns
Cathode spot radius – Flat-top () | 1.56 mm
Solenoid field at cathode (Bz) | 2 kG
Bunch length | 60 ps (2 cm)
Repetition rate | 476.3 MHz
Bunch charge | 420 pC
Peak current | 7.0 A
Average current | 200 mA
Transverse normalized emittance | 10s microns
 | 1.56 mm
Solenoid field at cathode (Bz) | 2 kG

## Slide 4
Experimental Overview
Generate magnetized beam:
  = 1 – 5 mm, Bz = 0 – 2 kG
  Bunch charge: 1 – 500 pC
  Frequency: 15 Hz – 476.3 MHz
  Bunch length: 10 – 100 ps
  Average beam currents up to 32 mA
  Gun high voltage: 200 – 350 kV

## Slide 5: Planned Measurements
Measure mechanical angular momentum
Measure photocathode lifetime versus solenoid field at high currents (up to 32 mA) and high voltages (200 – 350 kV) limited by in-house HV supplies
Study beam halo and beam loss versus magnetization
Use skew quads – RTFB Transformer – to generate flat beam and measure horizontal and vertical emittances using slit method
Generate very high currents magnetized beam and study beam transport and RTFB versus electron bunch charge
New supply capable of 200 mA and 300 kV costs about $600,000 (such supplies typically cost $10 per Watt)

## Slide 6
LERF Gun Test Stand
June 22, 2016

## Slide 7
October 19, 2015

## Slide 8: GTS Beam: 1 mA
275 kV
(not magnetized)

## Slide 9
K2CsSb Photocathode Preparation Chamber, Gun and Beamline: delivered 1 mA to dump
Lasers: ready (LOSP approved)
Gun Test Stand (GTS) OSP: approved for only 10 nA – working with Radiation Group for approval at full current
  Simulation (Fay Hannon):
  Used ASTRA and GPT simulation to design beamline and to locate magnets and diagnostics at optimum positions
  Simulated magnetized electron beam properties along beamline for various starting conditions
  Simulated a round to flat transformer
Prior Year Accomplishments

## Slide 10
Size | 11.811" ID, 27.559" OD, 6.242" Z
Conductor | L=500 m, A=0.53 cm2 16 layers by 20 turns
Coil Weight | 240 kg
Resistance | 0.18 Ω (65°C average T)
Field at Photocathode | 1.4 kG
Voltage | 72 V
Current | 400 A
  Designed, procured and built. Arrived on-site on June 28, 2016
  Cathode Solenoid Power Supply: Use new spare CEBAF Dogleg magnet power supply (500A, 80V)
Cathode Solenoid Magnet

## Slide 11
  Designed to enhance field to 2.0 kG at cathode. Two types:
    Molybdenum and carbon steel hybrid puck
    Carbon steel puck
New Steel Pucks
Molybdenum
Steel
Steel

## Slide 12
Plans for July – September 2016
Measure photocathode lifetime at 5 mA July
Map cathode magnet (without and with new pucks) June 28 – July 18
Install cathode magnet August
Install slits August
Load new pucks into Preparation Chamber September
Will have to break gun vacuum. Plan to change HV ceramic insulator and HV shed, replace leaky gate valve and add NEG pumps. Improve Preparation Chamber
Expected completion dates

## Slide 13: Budget
Materials and Supplies:
  Cathode solenoid magnet and pucks
  Three skew quadrupoles
  Beamline hardware: steering magnets and slits for beam emittance and magnetization measurements
  Laser components
Labor:
  Cathode magnet design and procurement
  Cathode magnet mapping and installation
  Relocate new CEBAF spare dogleg power supply (500A/80V) and provide 480VAC and LCW
  Mechanical designer for cathode magnet support
  Mechanical designer for pucks, slits and beamline
  ASTRA and GPT modeling (Fay Hannon)
  Postdoc – years 2 and 3
FY16 | $339,211
FY17 | $265,850
FY18 | $212,025
Total | $817,086
As of today, spent 67%

## Slide 14: Milestones

## Slide 15
Year 1 Milestones
Q1 (Oct, Nov, Dec):
    HV condition gun to 350 kV and build K2CsSb preparation chamber 
    Design beamline, locate magnets and diagnostics at optimum positions 
    Design cathode solenoid magnet 
Q2 (Jan, Feb, Mar):
    Connect existing beamline to gun and instrument beamline 
    Procure cathode solenoid magnet 
    Design and procure slits 
Q3 (Apr, May, Jun):
    Commission exiting beamline with beam 
    Measure photocathode lifetime at 5 mA and 350 kV (not magnetized)
    Relocate new spare CEBAF dogleg power supply to GTS 
Q4 (Jul, Aug, Sep):
    Install cathode solenoid magnet
    Assemble new beamline and commission with beam
    Design and procure three skew quads  Postponed to year 2

## Slide 16
Year 2 Milestones
Q1 (Oct, Nov, Dec):
    Generate magnetized beam
    Measure mechanical angular momentum vs magnetization and laser size
    Benchmark simulation against measurements
Q2 (Jan, Feb, Mar):
    Measure mechanical angular momentum vs bunch charge and bunch length
    Benchmark simulation against measurements
Q3 (Apr, May, Jun):
    Generate very high currents magnetized beam and study beam transport vs electron bunch charge
Q4 (Jul, Aug, Sep):
    Measure photocathode lifetime vs magnetization at 5 mA and 350 kV
    Study beam halo and beam loss vs magnetization

## Slide 17
Year 3 Milestones
Q1 (Oct, Nov, Dec):
    Install three skew quads
    Generate flat beam with skew quads – RTFB Transformer – and measure horizontal and vertical emittances using slit method
Q2 (Jan, Feb, Mar):
    Measure RTFB transformation versus electron bunch charge
    Use simulation to quantify how good or complete RTFB transform
Q3 (Apr, May, Jun):
    Change to HV Supply of 32 mA and 200 kV
Q4 (Jul, Aug, Sep):
    Measure photocathode lifetime vs magnetization at 32 mA and 200 kV
    Study beam halo and beam loss vs magnetization

## Slide 18: Backup Slides

## Slide 19
Magnetized Cooling
JLEIC bunched magnetized electron cooler is part of Collider Ring and aims to counteract emittance degradation induced by intra-beam scattering, to maintain ion beam emittance during collisions and extend luminosity lifetime.
Electrons helical motion in strong magnetic field increases electron-ion interaction time, thereby significantly improving cooling efficiency. Electron-ion collisions that occur over many cyclotron oscillations and at distances larger than cyclotron radius are insensitive to electrons transverse velocity.
Cooling rates are determined by electron longitudinal energy spread rather than electron beam transverse emittance as transverse motion of electrons is quenched by magnetic field
This cyclotron motion also provides suppression of electron-ion recombination

## Slide 20
Upon exit of Cathode Solenoid
Upon entering Cooling Solenoid
re= 0.7 mm
Bcool = 1 T
Electrons born in strong uniform Bz
= Rlaser = 1.56 mm
Bz = 2 kG
= 36 µm
Electron beam is being used inside cooling solenoid where it suffers an azimuthal kick when it enters. This kick is cancelled by an earlier kick at exit of cathode solenoid