## Sheet1
MOLLER Task | Topic | Deliverable | CIS/Grames |  | CASA/Roblin |  | OPS-Inj/Kazimi |  | I&C/Rider |  | OPS-SW/Kjeldsen |  | OPS-MCC/Vasil. |  | Milestones |  |  | Comments
|  |  | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FY24 | FY25 | FY26
1 | Helicity Generator | Helicity board with new settings | [12 empty] | 5 boards given to MOLLER coll. Fix two boards
2 | Helicity Decoder | New Boards for delayed helicity reporting | [12 empty] | Build 20 boards and distibute to Halls
3 | RTP Pockels Cell HV | Build, install a new 8-channel driver, with 10 µs risetime, electrically isolated | [12 empty] | Design Bench testing Installation CEBAF beam test | Fabricate spares | Operate Maintain | Might need PR for John Hansknecht, $20k contingency
4 | IA HV Driver | Build, install a new 4-channel driver, with 10 µs risetime, electrically isolated | [12 empty] | Design Bench testing Installation CEBAF beam test | Fabricate spares | Operate Maintain
5 | Helicity Magnets Control | Build, instal new control system, with 10 µs risetime, electrically isolated | [12 empty] | Design Bench testing Installation CEBAF beam test | Fabricate spares | Operate Maintain
6 | Polarization Feedback | Provide feedback mechanism (Wien or energy) to keep PL with 0.25° | [12 empty] | Design Implement CEBAF beam test | Operate Maintain | Operate Maintain
7 | Wien Filter Slow Reversal | Study Wiens Flip-Right and Flip-Left setups | [12 empty] | Model Inj beam test | Inj beam test | Inj beam test
8 | Injector Transmission and PQB | Optimize injector transmission for >95% | [12 empty] | Model Inj beam test | Inj beam test | Inj beam test
9 | Matching and Adiapatic Damping | Deliver matched beam and adquate damping | [12 empty] | Model and tools Beam test | Beam test | Beam test
10 | Fast Feedback | Test and maintain existing system | [12 empty] | Beam test | Beam test | Beam test
11 | Compton Polarimeter | Setup beam thru polarimetor with low halo > 100 Hz/µA | [12 empty] | Beam test | Beam test | Beam test
12 | Beam Modulation | Hot checkout and maintain system | [12 empty] | Hot checkout | Beam test | Beam test
13 | Phase Advance | Design Hall A brsm optics with sufficient phase advance | [12 empty] | Model Beam test | Beam test | Beam test
14 | K-long Beam | Install Hall D low-rep laser, LLRF, IA laser system. Study photocathode effects. Model beam loading in Linacs and test with beam. Write report to Physics Division | [12 empty] | Study K-long beam Write report
15 | Control of Charge Asymmetry | Measure and control charge asymmetry of Halls B, C, D
16 | PQB in Injector and Hall A | Setup PQB in injector and Hall A and erform beam studies
17 | Hallo Monitors in Hall A | Install halo target and detectors and provide FSD and EPICS controls
18 | MOLLER Apparatus Protection | Protect apparatus from beam mis-steering
19 | BPM Receivers | New receivers in Hall A line instead of S/H cards
20 | BCM Receivers | New BCM recivers in Hall A line
21 | PQB Liason | Coordinate MOLLER tasks | 1.8
TOTAL |  |  | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0