## Sheet1
MOLLER Task | Topic | Deliverable | CIS/Grames |  | CASA/Roblin |  | OPS-Inj/Kazimi |  | I&C/Rider |  | OPS-SW/Kjeldsen |  | OPS-MCC/Vasil. |  | SSG/Kowal |  | RCG/Welch |  | FastElec/Cueves |  | Milestones |  |  | Comments
|  |  | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FTE | M&S (k$) | FY24 | FY25 | FY26
1 | Helicity Generator | Helicity board with new settings |  | 1 | [6 empty] | 0.1 | [7 empty] | 0.2 |  | 5 boards given to MOLLER coll. Fix two boards | Maintain | Maintain
2 | Helicity Decoder | New Boards for delayed helicity reporting |  | 4 | [14 empty] | 0.6 | 25 | Build 20 boards and distibute to Halls | Maintain | Maintain
3 | RTP Pockels Cell HV | Build, install a new 8-channel driver, with 10 µs risetime, electrically isolated | 0.7 | [5 empty] | 0.7 | 39 | 0.2 | [9 empty] | Design Bench testing Installation CEBAF beam test | Fabricate spares | Operate Maintain | Need PR for John Hansknecht, $20k contingency
4 | IA HV Driver | Build, install a new 4-channel driver, with 10 µs risetime, electrically isolated | 0.7 | [5 empty] | 0.3 | 25 | 0.1 | [9 empty] | Design Bench testing Installation CEBAF beam test | Fabricate spares | Operate Maintain
5 | Helicity Magnets Control | Build, instal new control system, with 10 µs rise-time, electrically isolated | 0.5 |  | 0.1 |  |  |  | 0.3 | 18 | 0.2 | [9 empty] | Design Bench testing Installation CEBAF beam test | Fabricate spares | Operate Maintain
6 | Polarization Feedback | Provide feedback mechanism (Wiens or energy) to keep PL within 0.25° | 1.3 | 100 | 0.3 |  | 0.3 | [13 empty] | Design Implement CEBAF beam test | Operate Maintain | Operate Maintain | New Wien filter might be needed
7 | Wien Filter Slow Reversal | Study Wiens Flip-Right and Flip-Left setups | 1.3 | 50 |  |  | 0.4 | [13 empty] | Model Inj beam test | Inj beam test | Inj beam test | Repair might be needed
8 | Injector Transmission and PQB | Optimize injector transmission for >95% | 0.3 |  |  |  | 0.4 | [13 empty] | Model Inj beam test | Inj beam test | Inj beam test
9 | Matching and Adiapatic Damping | Deliver matched beam and adquate damping | 0.2 |  | 0.4 |  | 0.3 | [13 empty] | Model and tools Beam test | Beam test | Beam test
10 | Fast Feedback | Test and maintain existing system |  |  | 0.6 |  |  |  | 0.2 |  | 0.1 | [9 empty] | Beam test | Beam test | Beam test
11 | Compton Polarimeter | Setup beam thru polarimetor with low halo > 100 Hz/µA |  |  | 0.3 | [15 empty] | Beam test | Beam test | Beam test
12 | Beam Modulation | Hot checkout and maintain system |  |  | 0.1 |  |  |  | 0.1 |  | 0.1 | [9 empty] | Hot checkout | Beam test | Beam test
13 | Phase Advance | Design Hall A brsm optics with sufficient phase advance |  |  | 0.1 | [15 empty] | Model Beam test | Beam test | Beam test
14 | K-long Beam | Install Hall D low-rep laser, IA laser system. Study photocathode effects. Model beam loading in Linacs and test with beam. Write report to Physics Division | 0.5 | 25 | 0.4 |  | 0.4 | [13 empty] | Study K-long beam Write report
15 | Control of Charge Asymmetry | Measure and control charge asymmetry of Halls B, C, D | [8 empty] | 0.1 | [9 empty] | Beam test | Beam test | Beam test
16 | PQB in Injector and Hall A | Setup PQB in injector and Hall A and perform beam studies | 0.2 |  | 0.2 |  | 0.2 | [13 empty] | Beam test | Beam test | Beam test
17 | Hallo Monitors in Hall A | Install halo target and detectors and provide FSD and EPICS controls | [6 empty] | 0.2 |  | 0.2 |  |  |  | 0.1 | 6 |  |  |  |  | Design | Install
18 | MOLLER Apparatus Protection | Protect apparatus from beam mis-steering | [8 empty] | 0.2 |  | 0.6 |  | 0.1 | 20 | 0.2 |  |  |  | Design | Design | Install
19 | BPM Receivers | New receivers in Hall A line instead of S/H cards | [6 empty] | 0.3 |  | 0.1 | [9 empty] | Design Bench testing | Installation CEBAF beam test | Beam test
20 | BCM Receivers | New BCM recivers in Hall A line | [6 empty] | 1 |  | 0.1 | [9 empty] | Design Bench testing Installation CEBAF beam test | Beam test | Beam test
21 | PQB Liason | Coordinate MOLLER tasks | 1.8
TOTAL |  |  | 7.5 | 180 | 2.5 | 0 | 2 | 0 | 3.1 | 82 | 1.5 | 0 | 0.6 | 0 | 0.2 | 26 | 0.2 | 0 | 0.8 | 25
Task Color Code
Almost done
Did it before, should be straightforward
Working on it, should be able to do
New or hard, could be very complicated