## Slide 1: Bubble Chamber Planning Meeting
04 September 2013

## Slide 2: Agenda
Bubble Chamber progress at Argonne
Superheated Liquids to be used in the experiment
Computer Center support: mailing list, group disk, wiki page
Beamline Layout
Bubble Chamber cost estimate: procurement and labor
Error Analysis

## Slide 3: Superheated Liquids
List of superheated liquids to be used in the experiment:
Readout:
  Digital Camera
  Need Acoustic Signal to discriminate between (γ,α) and (γ,n) events
N2O Targets | 16O | 17O | 18O
Natural Target | 99.757% | 0.038% | 0.205%
16O Target |  | Depleted > 5,000 | Depleted > 5,000
17O Target |  | Enriched > 10% | Depleted > 5,000
18O Target |  | Depleted > 5,000 | Enriched > 10%

## Slide 4: Beamline Layout
Will not install BPM on Spectrometer line
2 Super Harps to measure beam profile and absolute beam position (no need for Quads)
Fast Valve to protect from vacuum failure: on our beamline or just in front of ¼ Cryo-unit
Do we want vacuum pipe to connect vacuum window to chamber?
Beam Properties at Radiator:
Beam Kinetic Energy, (MeV) | 3.0 – 8.5
Beam Current (µA) | 0.01 – 100
Absolute Beam Energy | 0.1%
Relative Beam Energy | 0.1%
Energy Resolution (Spread), σT /T | 0.06%
Beam Size, σx,y (mm) | 1 – 2

## Slide 5
42”
25°
100”
Valve
Ion
Pump
Viewer
BPM
Corrector
35”
Fast
Valve
BPM
Corrector
Radiator
Viewer
Ion Pump
55”
Sweep
Dipole
25°
Vacuum
Window
Cu Collimator
Electron Dump
Photon
Dump
92”
Bubble
Chamber
81”
Faraday
Cup
Super
HARP
Super
HARP
Or in front of ¼ Cryo-unit

## Slide 6: Cost Estimate
Radiator motion and Sweep Dipole must be in FSD
BCM0L02 and Electron Dump in Beam Loss Accounting (BLA)
New beamline components: 2 Super Harps + Fast Valve
Summary of labor cost by group:
Group | Labor
Survey & Alignment | 3 wks x 2
Magnet Test | 1 wk x 2
Engineering Design | 12 wks
Software | 3 wks x 2
EES | 6 wk x 2
EH&Q | 4 wks

## Slide 7
Item | Material Procurement | Shop | Labor
New Dipole Magnet | Dipole Magnet ($8,000) Hall Probe ($2,000) |  | Mapping (1 week) EESDC (1 week) Alignment (2 days)
New Power Supply | Power Supply ($5,000) |  | Software (2 weeks)
New Beamline | 2 Super Harps and Fast Valve ($30,000) | Pipes + Pedestals ($20,000) | Design (6 weeks) Alignment (1 week) Software (4 weeks) EES (5 weeks)
Radiator (cooled ladder, FSD) | 0.02 and 0.10 mm Cu foils ($2,000) | $4,000 | Design (2 week) Alignment (2 days)
Sweep Dipole |  |  | 
Electron Dump | Pure Cu ($5,000) | Dump + Pipes ($15,000) | Design (2 week) Alignment (1 day)
Cu Collimator | Pure Cu ($5,000) | Collimator + Stand ($5,000) | Design (1 week) Alignment (1 day)
Photon Dump & Stand | Pure Al ($3,000) | $4,000 | Design (1 week) Alignment (1 day)
Safety Review |  |  | 4 weeks
Install |  |  | 6 weeks
Bubble Chamber |  |  | Alignment (1 week)
Total | $60,000 | $48,000 | $60,000
Total (with overhead) | $75,000 | $60,000 | $90,000