## Slide 1: Bubble Chamber
Installation and
Beam Test Schedule
https://wiki.jlab.org/ciswiki/index.php/Bubble_Chamber

## Slide 2
Summer 2014 SAD:
  Fast Valve after ¼ Cryounit
  New MBV0L02 Dipole Magnet
  Install Bubble Chamber for Test Run
Safety
Schedule for October 2014 Beam Test

## Slide 3
Fast Valve after ¼ Cryounit:
  Heckman: ordered fast valve
  Kortze: to order controller electronics, complete installation
  Install Group: to move DP station after cryounit to make room for valve
  Survey/Alignment: to check DP station
  MPS: to integrate fast valve in FSD
  Trigger gauge to be installed in 5D line
New Fast Valve to protect from vacuum failure in front of ¼ Cryo-unit

## Slide 4
New MBV0L02 Dipole Magnet
  Benesch/ME: to complete design, find vendor, get quotes, place order
  Suleiman: to order Hall Probe system
  Magnet mapping
  Survey/Alignment
  Power Supply: 10 A Trim Card
5 MeV Dipole

## Slide 5
Install Bubble Chamber for Test Run
  Suleiman/ME: to complete design modifications for 5D line and bubble footprint
  EGG: to do vacuum work
  Install Group: to crane bubble chamber and hardware to tunnel
  Survey/alignment to set points for bubble chamber, support alignment
  Facilities: to provide power to Bubble Chamber Compressor
  EGG: to include “No Beam” signal from Bubble chamber in laser Shutter
  Suleiman/ME: design and build Photon Collimator and Photon Dump
  Suleiman/ME: design cupper for Flange radiator/dump
  ME: Thermal analysis of Flange radiator/dump
  New beamline Components: (1) Corrector (2) Superharps
    Need to have an installation plan, pre-review by late April

## Slide 6
BCM
5 MeV
Dipole
2D
Spectrometer
5D Spectrometer
Bubble
Chamber
location
Mott Polarimeter

## Slide 7
5D Spectrometer
Bubble Chamber at HIGS
April 2013
Photon Beam
Entrance

## Slide 8
First g+O→α+C bubble
April 2013
N2O Bubble Chamber
  T = -5˚C
  P = 60 atm

## Slide 9: Beamline
2 Superharps t o measure
Beam profile and absolute
beam position
New Dipole
Magnet
For 2014 beam test, replace with flange

## Slide 10: Schematics
Electron K.E.
3.0 – 8.7 MeV
0.01 – ? µA
Al Beam Pipe
Flange Cu
Radiator/Dump
? mm
Bubble Chamber
Superheated N2O
3 cm long
-5°C, 60 atm
Al Photon Dump
10 cm long
20 cm diameter
Cu Photon
Collimator
Use pure Copper and Aluminum
Flange isolated and current in EPICS readback

## Slide 11: Beam Requirements
Beam Properties at Radiator:
February 16, 2014: With one trip/hour (all are 0L02-8 ARC trips) GMeas are: 0L02-7 = 10.22 MV/m and 0L02-8 = 10.40 MV/m. Beam Kinetic Energy = 8.7 MeV
We may also need to helium process the ¼-cryounit
Beam Kinetic Energy, (MeV) | 7.9–8.7
Beam Current (µA) | 0.01–?
Absolute Beam Energy Uncertainty | <0.1%
Relative Beam Energy Uncertainty | <0.02%
Energy Resolution (Spread), σT /T | <0.06%
Beam Size, σx,y (mm) | 1–2

## Slide 12: Safety
Superheated liquid: N2O, Nitrous oxide (laughing gas)
  At room temperature, it is colorless, non-flammable gas, with slightly sweet odor and taste
High pressure system:
  Design Authority: Dave Meekins
  T = -5˚C
  P = 60 atm
Buffer liquid: Mercury
  Closed system
  Volume: 135 mL
0
OX
0
2
0
0
3